## Sheet1
Risk Categories | Risk Name | Status | Probability | Impact | Risk Factor | Prevention Strategy | Mitigation Strategy
Technologies | Touch Screen
| Hardware is not Delivered | Preventions, Mitigation | 1 | 7 | 7% | Communication with Sponsor | Simulate Using a Mouse
| Compatibility Issues |  | 3 | 7 | 21% | Tech Lead for Touch screen Integration | Consult with Sponsor
| Hardware Failure/Loss |  | 2 | 5 | 10% | Left in Secure Room | Request Another Touch screen
| Unknown Usage of Interface |  | 5 | 7 | 35% | Tech Lead for Touch screen Integration | Consult with Sponsor
.NET
| Lack of Experience with .NET |  | 9 | 5 | 45% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Lack of C# Knowledge |  | 9 | 4 | 36% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Lack of Experience with Visual Studio |  | 9 | 4 | 36% | Training Meeting with Experienced Team Members | .NET Lead Available to Answer Questions
| Obtaining Proper Version of Tool/Libraries on Work Machines |  | 3 | 8 | 24% | Request from Sys Admin | Use Personal Systems
Windows Embedded
| Obtaining Kodak's Image of Windows Embedded |  | 9 | 7 | 63% | Communication with Sponsor | Approximate Kodak Setup
| Lack of Experience with Windows Embedded |  | 9 | 6 | 54% | Research into Windows Embedded | Request Formal Training from Outside Source
| Obtaining Windows Embedded on a Machine |  | 4 | 7 | 28% | Request from Sys Admin | Consult Sponsor for an Acceptable Solution
GUI
| Localization Issues |  | 7 | 4 | 28% | Research Localization Techniques | Localization Lead Comes up with Solution
| Lack of Usability |  | 8 | 10 | 80% | Early Prototypes and Storyboarding | Communication with Kodak Human Factors Group
| Compatibility with Kodak Standards |  | 5 | 5 | 25% | Early Prototypes, Storyboarding, and Using Kodak Usability Standards | Negotiation of Needs with Sponsor
| Poor Memory Management |  | 7 | 10 | 70% | Make Use of Profiling Software and Metrics | Code Reviews
| Rendering Issues and Speed |  | 8 | 10 | 80% | Research and Making Use of Profiling Software and Metrics | GDI+ Lead Works to Improve Algorithms
| Creation of Specialty Controls |  | 5 | 8 | 40% | High Priority in Development | Adapt Existing Tools
GDI
| Lack of Experience |  | 9 | 8 | 72% | GDI Tech Lead Research | Request Formal Training from Outside Source
| Lack of Support for Tool Algorithms |  | 4 | 10 | 40% | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor
| Possible Tool/Algorithm Development |  | 4 | 7 | 28% | Tool Lead will Develop New Tool Algorithms | Request Compromise from Sponsor
Data Loss
| Version Control Repository Lost |  | 1 | 6 | 6% | Request Recovery from Sys Admin | Back Up on Personal Computers
| Hard Disk Failure |  | 1 | 6 | 6% | Request Recovery from Sys Admin | Back Up on Personal Computers
| Lack of Control Over Resources |  | 6 | 2 | 12% | Request Additional Control from Sys Admin | Use Provided Hardware
Project Management | Schedule Slip
| Senioritis |  | 8 | 6 | 48% | Project Coordinator Ensures that Project is On Track | Rework Schedule
| Code Development Issues |  | 7 | 10 | 70% | Unit Testing and Small Incremental Releases | Code Reviews
| School Workload |  | 10 | 7 | 70% | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Lack of Additional Resources |  | 10 | 10 | 100% | Attempt to Rigidly Follow Schedule in Place | Leave Extra Time in Schedule for Slippage
| Poor Project Planning |  | 6 | 10 | 60% | Project Coordinator Constantly Evaluates Schedule | Consult with Faculty Coach and Reschedule
| Limited Maintenance Time |  | 9 | 4 | 36% | Attempt to Rigidly Follow Schedule in Place | Follow Good Documentation Processes
Project Completion
| Delivery of Nonfunctional Product |  | 3 | 10 | 30% | Make Use of Evolutionary Development Process | Revert to Last Working Increment
| Lack of Proper Documentation |  | 3 | 5 | 15% | Good Documentation Standards | Documentation Reviews
| Unable to Satisfy Requirements |  | 5 | 8 | 40% | Constant Feedback from Sponsor after Every Increment | Renegotiate Requirements with Sponsor
Inexperienced with Project Management
| Team Issues |  | 1 | 8 | 8% | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Lack of Communication |  | 5 | 10 | 50% | Frequent Status Meetings/Emails within the Sponsor | Consult with Sponsor
| Poor Selection of Project Methodology |  | 3 | 8 | 24% | Frequent Status Meetings within the Team | Consult with Faculty Coach
| Poor Implementation of Project Methodology |  | 7 | 8 | 56% | Frequent Status Meetings within the Team | Consult with Faculty Coach