## Sheet1
Task | Estimate
Develop Feature List | N/A
Develop Risk Management Plan | N/A
Develop GUI Storyboard | N/A
Develop Project Schedule | N/A
Develop Project Plan | N/A
Project Planning Milestone | 2007-12-22
Develop Functional Requirements | 35
Develop Nonfunctional Requirements | 20
Develop Use Cases | 30
Requirements Milestone | 2007-01-18
Design Architecture | 50
Unit Test Plan | 10
Integration Test Plan | 10
System Test Plan | 10
Design Milestone | 2007-02-01
Increment Design Review | 20
Implementation | 80
Unit Testing | 15
Implementation Bug Fixes | 15
Implementation Increment 1 Milestone | 2007-02-22
Increment Design Review | 10
Implementation | 50
Unit Testing | 10
Implementation Bug Fixes | 10
Implementation Increment 2 Milestone | 2007-03-22
Increment Design Review | 10
Implementation | 50
Unit Testing | 10
Implementation Bug Fixes | 10
Implementation Increment 3 Milestone | 2007-04-12
Integration Testing | 20
Integration Bug Fixes | 20
System Testing | 35
System Bug Fixes | 35
Verification Milestone | 2007-04-26
Bug Fixes | 30
Customer Training | 20
Final Release Milestone | 2007-05-10