## Earned Value Data
Task | Duration (hrs.) | Earned Value | % Task Complete | % Project Complete
Detail Requirements | 8 | 1.5994 | 100 | 1.5994
Review Requirements | 8 | 1.5994 | 100 | 1.5994
Detail Requirements further | 8 | 1.5994 | 100 | 1.5994
Review Requirements Detail | 8 | 1.5994 | 100 | 1.5994
Determine process for change management | 2 | 0.39984 | 100 | 0.39984
Determine metrics | 5 | 0.9996 | 100 | 0.9996
Priortize Requirements | 2 | 0.39984 | 100 | 0.39984
Update Risks Based on Requirements | 2 | 0.39984 | 100 | 0.39984
Create/gather Testing templates | 4 | 0.79968 | 100 | 0.79968
Create Acceptance Test Plan | 6 | 1.1995 | 100 | 1.1995
Review Acceptance Test Plan | 3 | 0.59976 | 100 | 0.59976
High-level System Design | 4 | 0.79968 | 100 | 0.79968
Review High-level System Design | 1 | 0.19992 | 100 | 0.19992
Create detailed user use cases | 4 | 0.79968 | 100 | 0.79968
Review detailed user use cases | 2 | 0.39984 | 100 | 0.39984
Create System Test Plan | 6 | 1.1995 | 100 | 1.1995
Review System Test Plan | 3 | 0.59976 | 100 | 0.59976
Create Detailed Architecture/Application Design | 17 | 3.3986 | 100 | 3.3986
Review Detailed Architecture/Application Design | 4 | 0.79968 | 100 | 0.79968
Create Integration Test Plan | 7 | 1.3994 | 100 | 1.3994
Review Integration Test Plan | 2 | 0.39984 | 100 | 0.39984
Detailed Component Design | 40 | 7.9968 | 100 | 7.9968
Review Detailed Component Design | 6 | 1.1995 | 100 | 1.1995
Create Unit Test Plan | 12 | 2.399 | 100 | 2.399
Review Unit Test Plan | 3 | 0.59976 | 100 | 0.59976
UI Paper Prototype | 16 | 3.1987 | 100 | 3.1987
Proof of concept with MapPoint.NET | 5 | 0.9996 | 100 | 0.9996
Research/Set-up Nokia IDE | 25 | 4.998 | 100 | 4.998
Proven interaction between the IDE and GPS Hardware | 4 | 0.79968 | 100 | 0.79968
JSR-179 (Subclassing and Server) implementation | 6 | 1.1995 | 100 | 1.1995
Model Component | 3 | 0.59976 | 100 | 0.59976
Test Model Component | 2 | 0.39984 | 100 | 0.39984
Client UI Component | 20 | 3.9984 | 100 | 3.9984
Test Client UI Component | 10 | 1.9992 | 100 | 1.9992
Request Component | 6 | 1.1995 | 100 | 1.1995
Test Request Component | 5 | 0.9996 | 100 | 0.9996
Mediator | 12 | 2.399 | 100 | 2.399
Test Mediator | 7 | 1.3994 | 100 | 1.3994
XML Component | 5 | 0.9996 | 100 | 0.9996
Test XML Component | 2 | 0.39984 | 100 | 0.39984
Servlet Component | 5 | 0.9996 | 100 | 0.9996
Test Servlet Component | 3 | 0.59976 | 100 | 0.59976
Servlet State Component | 15 | 2.9988 | 100 | 2.9988
Test Servlet State Component | 7 | 1.3994 | 100 | 1.3994
MapPoint Component | 12 | 2.399 | 100 | 2.399
Test MapPoint Component | 5 | 0.9996 | 100 | 0.9996
Response Component | 7 | 1.3994 | 100 | 1.3994
Test Response Component | 4 | 0.79968 | 100 | 0.79968
Bug Fixing (after Unit testing) | 18 | 3.5986 | 100 | 3.5986
Integrate each component into system | 10 | 1.9992 | 100 | 1.9992
Integration Testing | 5.2 | 1.0396 | 100 | 1.0396
Bug Fixing (after integration testing) | 6 | 1.1995 | 100 | 1.1995
System test | 4 | 0.79968 | 100 | 0.79968
Bug Fixing (after System testing) | 4 | 0.79968 | 100 | 0.79968
Acceptance test | 4 | 0.79968 | 100 | 0.79968
Bug Fixing (after Acceptance testing) | 2 | 0.39984 | 100 | 0.39984
Put together first quarter presentation | 10 | 1.9992 | 100 | 1.9992
Put together second quarter presentation | 20 | 3.9984 | 100 | 3.9984
Investigate SOAP and MapPoint.NET interaction | 7 | 1.3994 | 100 | 1.3994
Create Users Manual | 15 | 2.9988 | 100 | 2.9988
Determine process for compilation | 2 | 0.39984 | 100 | 0.39984
Compile metrics | 20 | 3.9984 | 100 | 3.9984
Create Technical Report | 20 | 3.9984 | 100 | 3.9984
Total Time
500.2
% Project Completed
100
(Total Points Earned)

## % Project Complete
Time | Total Earned Points
2006-01-01 | 0
2006-01-08 | 3.3613
2006-01-15 | 5.2521
2006-01-22 | 11.3445
2006-01-29 | 16.5546
2006-02-05 | 24.4328
2006-02-12 | 26.5084
2006-02-19 | 29.248
2006-02-26 | 42.0902
2006-03-05 | 42.0902 | Finals
2006-03-12 | 42.0902 | Break
2006-03-19 | 45.4545 | Components Defined - Added hours to schedule
2006-03-26 | 46.4657
2006-04-02 | 54.8794
2006-04-09 | 58.6642
2006-04-16 | 69.564
2006-04-23 | 76.6772
2006-04-30 | 77.9759
2006-05-07 | 91.5034
2006-05-14 | 95.9016
2006-05-21 | 100