### Meeting Minutes

Date: Tuesday January 24, 2006

Time: 4 pm

Persons Present: Lora, Amanda, Nick, Tom, Shawn, Jack Birecree

- Milestone complete  emulator works with the Internet

  - But, only works with Ethernet

  - We should be ok – we shouldn’t have to worry about this

  - Work-around with the laptops – bridge 2 laptops with a crossover cable with Sprint aircard in one laptop

    - Poke around on forums and see if there isn’t something easier – post questions

  - Sprint aircard only needed for testing off-campus, as we have wireless here at RIT

- Schedule:

  - Have decided to go with the Waterfall model – will change docs accordingly

  - Jack’s notes:

    - Nothing completed on schedule – there is a way to tag tasks as being completed

    - High-level system design will be done by this Thursday

      - Jack would like to review it next time we meet

    - Task #18 – detailed component design – 40 hours

      - Is this for all of the platforms (phone, server)?

        - Yes, its just a placeholder for now and will be broken down

        - What are the components?

          - Client – emulator (JSR179 stuff), internet connectivity (probably not)

          - Server – something creating dynamic WML, something processing requests, module to interact with MapPoint

    - Task #23 – UI paper prototype

      - Fairly late in the process

      - In parallel writing code and constructing components and testing

      - We should do it sooner

    - Milestones are good – but need one more:

      - Got server running

      - Server talked to MapPoint

      - Can access the server from Internet Explorer

    - Timeframe to know when schedule has been updated

      - Monday at noon, or something like that

      - Project status doc needs to be up on website by Tues at 10am – we’ll do it then

    - No tasks around the use cases

      - The use cases will be used for acceptance test plans, design, code, UI design

      - Typically use cases are an aid to requirements

- No interaction between emulator and GPS device proven yet

  - Jack is not opposed to us writing other functions and including them (just temporary)

  - Just wants to see that we can run the emulator and call JSR179 – good enough

  - Perhaps we could use a façade to make it less complicated

- Use Cases:

  - General comment – usually use cases written from users point of view

    - We have software components as actors

  - Person opens phone, navigates to main screen, initiates kilo app  now what do they see?

    - We’ve got to include this sort of thing in the use cases

    - Need to include specific user behavior – need to be reworked.

      - Workflows would be ok

- Next week we should spend time talking about launching the emulator

- Storing sessions on server to pre-fetch information

  - Will affect use cases

  - Part of design steps

  - Do they do that in the Kodak.com software?

    - Would be faster

    - But not necessary if it is too complex

    - Less costly – but we shouldn’t worry about that

    - Jack’s inclination would be to say don’t do this. Doesn’t want it to have storage requirements for when they port it.

    - But its our decision

- Jack will get us a crossover cable

- Tracking:

  - Would like us to track the milestones

  - Once a month  chart days (+/-  Up and down) versus time (dates of milestones)

    - Plot milestones according to dates they should show up

    - Allows us to see if we are accomplishing the milestones on time – early or late

    - Original, base lined dates – not with schedule changes

    - We could probably use Excel

    - Jack will send us an example – to use as a template

    - Easy to read synopsis of how project is going

- UI Design:

  - Jack would suggest using workflows - UI Storyboards

    - UI workflow typically on one piece of paper

    - “What happens when I click that button”, etc.

  - Doesn’t want great detail in designing UI – doesn’t need to be that detailed to get the important points across