### Meeting Minutes

Date: Tuesday February 14, 2006

Time: 4 PM

Persons Present: Lora, Amanda, Nick, Tom, Jack Birecree, Dr. Naveda

- Shawn can start integration test plan a bit more now that the design is a bit more complete

  - Nick will detail design more on Friday. Also he will add titles to the diagrams

  - Detailed design could be done by Sunday or Monday

  - Lora will talk with Shawn about the test plans

- Nick will also start work on the definition of the XML schema

Jack Birecree arrived

- Jack is comfortable with the requirements

  - He will sign off electronically

  - Amanda will make the modifications still needed

- UI Workflow

  - Not to scale

  - Should be able to fit 4 kiosks in the list on one screen

  - No more icons on kiosk list – its cleaner now

  - Carry over kiosk information on the Map Directions and Driving Directions screens

  - Up and down arrows are used to scroll through the list

  - Selected item will be highlighted

  - When you first come to a screen the top item will be highlighted as the selected item

  - Map will fit the screen

  - Border around functionality? If there is more space, use it wisely

  - Jack will sign-off on this

    - It is do-able

- Lora will send an email to Jack tonight and Jack will sign-off on it

- Demo – emulator working with GPS

  - Uses GetLocation call

  - Transparent to JSR179

  - GPS retains last known location

  - Good progress

- Nokia IDE is not easy to use

- Next milestone is set for Thursday – MapPoint with Server

  - Pretty confident we can meet it

  - Could be part of our presentation

- Kodak template for ppt?

  - Jack will send us a couple templates plus the new logo

  - New logo has not been trade-dressed yet

  - We can use it if we want. Probably won’t be in use until the summer.

- Jack has sent the team evaluation to Naveda

- Progress against schedule

  - Missed milestone #2 – sign-off on UI design

- Excellent website

- Milestone tracking chart –

  - No good information from what we have.

  - Jack wants to see where we stand on a weekly basis against the project schedule

    - Things are always moving

    - Look at baselined schedule

      - Show weekly how far we are deviating from original schedule

        - Probably some slippage – show this

  - Will be a standing agenda item at Tuesday meetings

- Schedule –

  - Black bar  = completed

  - If things aren’t completed on time – it can’t be completed in the past, must complete in the future

    - Must drag the bar out to where it probably will be completed. It’s a good team activity

      - Has implications for other tasks

      - MS project will recalculate other tasks

    - Concern that we will be pushed out past graduation – we will have to readjust resources

    - Dates on milestones will change

      - Show this on milestone chart

  - Resources still not balanced

    - Lora will look at it

    - “All” is too heavily loaded

- Presentation is at 5:15 pm next Tuesday in room 1550

  - Will demo emulator working with GPS and hopefully the server with MapPoint proof of concept

- Jack is in the process of getting the 2nd laptop fixed

  - Crossover cable is in that laptop bag

  - Don’t need it for the demo