## Instructions
Your Name: | Leight, Jonathon
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1 |  | Attended senion project informational meeting
Y | 0.5 |  | Read the proejct description document
Y | 4 |  | Attended the first weekly project meeting
N | 1 |  | Worked with the current system to try and understand how it works
| 6.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Weekly team meeting
|  | 0.25 | Set up team SE account
|  | 1 | Set up project website
|  | 4 | Do more research on the current application
|  | 9.25 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Weekly team meeting
Y | 0.25 | 0.25 | Set up team SE account
N | 0 | 1 | Set up project website
N | 3 | 4 | Do more research on the current application
| 7.25 | 9.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Do more research on the current application
|  | 0.25 | Pick up the team account information
|  | 2 | Set up the project website
|  | 5 | Weekly team meeting
|  | 8.25 | TOTAL TIME
Issues
Kurt on vacation

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
N | 1 | 1 | Do more research on the current application
Y | 0.5 | 0.25 | Pick up the team account information
N | 5 | 3 | Set up the project website
N | 3 | 3 | Weekly team meeting
N | 2 | 2 | Work on the proposal document
N | 1 | 1 | Learn C#/MVC3
| 12.5 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Finish final draft of project proposal document
|  | 5 | Finish first draft of requirements document
|  | 1 | Add information to the project website
|  | 2 | Weekly team meeting
|  | 2 | Meeting to work on documents
|  | 12 | TOTAL TIME
Issues
Kurt not in his office when we need him

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Finish final draft of project proposal document
Y | 6 | 5 | Finish first draft of requirements document
Y | 0 | 1 | Add information to the project website
Y | 2 | 2 | Weekly team meeting
Y | 2 | 2 | Meeting to work on documents
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Work on second draft of requirements document
|  | 2 | Work on final draft of requirements document
|  | 0.25 | Update the team website with the new documents
|  | 2 | Work on architecture palnning
|  | 2 | Work on setting up VCS correctly
|  | 8.25 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Work on second draft of requirements document
N | 2 | 2 | Work on final draft of requirements document
Y | 0.25 | 0.25 | Update the team website with the new documents
N | 2 | 2 | Work on architecture palnning
Y | 2 | 2 | Work on setting up VCS correctly
| 8.25 | 8.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Finish requirements document for sign off
|  | 0.25 | Update team website with final requirements document
|  | 6 | Work on architecture planning
|  | 2 | Meet with OCECS co-ops for help with technologies
|  | 9.25 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 1 | 1 | Finish requirements document for sign off
Y | 0.5 | 0.25 | Update team website with final requirements document
N | 7 | 6 | Work on architecture planning
Y | 1 | 2 | Meet with OCECS co-ops for help with technologies
Y | 2 | 2 | Meet with sponsor
| 11.5 | 11.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Continue database design
|  | 4 | Meet with team
|  | 4 | Write database scripts
|  | 12 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
N | 4 | 4 | Continue database design
Y | 4 | 4 | Meet with team
Y | 4 | 4 | Write database scripts
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Meet with team
|  | 2 | Meet with sponsor
|  | 2 | Interview users
|  | 4 | Work on architecture doc
|  | 2 | Continue database desgin
|  | 14 | TOTAL TIME
Issues
Database design seems done, but small problems keep coming up

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Meet with team
Y | 2 | 2 | Meet with sponsor
N | 0 | 2 | Interview users
N | 4 | 4 | Work on architecture doc
N | 1 | 2 | Continue database desgin
| 11 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Work on architecture document
|  | 2 | Meet with team
|  | 2 | Work on presentation
|  | 1 | Work on requirements document
|  | 2 | Do presentation
|  | 11 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 3.5 | 4 | Work on architecture document
Y | 2 | 2 | Meet with team
Y | 2 | 2 | Work on presentation
Y | 0.5 | 1 | Work on requirements document
Y | 2 | 2 | Do presentation
N | 1 | 1 | Work on database design
| 11 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Watch presentations
|  | 2 | Meet with sponsor
|  | 8 | Work on architecture document
|  | 1 | Finish database design
|  | 13 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2 | Watch presentations
Y | 1 | 2 | Meet with sponsor
Y | 9 | 8 | Work on architecture document
N | 1 | 1 | Finish database design
Y | 1 | 1 | Meet with team
| 14.5 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meet with coach
|  | 2 | Reflection
|  | 0.5 | Peer reviews
|  | 6 | Start implementation
|  | 9.5 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 2 | 1 | Meet with coach
| 2 | 2 | Reflection
| 0.5 | 0.5 | Peer reviews
| 6 | 6 | Start implementation
| 10.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Continue implementation, specifically UI work
|  | 2 | Meet with team
|  | 2 | Finish setting up tools to help with implementation
|  | 14 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
N | 10 | 10 | Continue implementation, specifically UI work
Y | 2 | 2 | Meet with team
Y | 2 | 2 | Finish setting up tools to help with implementation
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 14 | Continue UI implementation
|  | 14 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
N | 14 | 14 | Continue UI implementation
Y | 1 | 1 | Meet with sponsor
| 15 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 13 | Continue UI and background implementation
|  | 13 | TOTAL TIME
Issues
Not finishing the implementation quite as fast as expected.
No one has a lot of time to spend on this yet.

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
N | 18 | 13 | Continue UI and background implementation
| 18 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 14 | Continue UI and background implementation
|  | 1 | Meet with sponsor
|  | 15 | TOTAL TIME
Issues
Still having trouble finishing the UI.

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
N | 15 | 14 | Continue UI and background implementation
Y | 1 | 1 | Meet with sponsor
| 16 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 14 | Continue implementation
|  | 14 | TOTAL TIME
Issues
Still figuring out new things about MVC3 and having to redo stuff.

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
N | 20 | 14 | Continue implementation
| 20 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 15 | Continue implementation
|  | 1 | Meet with sponsor
|  | 16 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 25 | 15 | Continue implementation
Y | 1 | 1 | Meet with sponsor
| 26 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 15 | Continue implementation
|  | 1 | Meet with sponsor
|  | 16 | TOTAL TIME
Issues
Ended up starting blank project to start cleanup

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
N | 30 | 15 | Continue implementation
Y | 1 | 1 | Meet with sponsor
| 31 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Continue implementation
|  | 1 | Meet with sponsor
|  | 31 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
N | 28 | 30 | Continue implementation
Y | 1 | 1 | Meet with sponsor
| 29 | 31 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Finish up the implementation that we are going to finish
|  | 5 | Work on documents
|  | 1 | Meet with sponsor
|  | 11 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 7 | 5 | Finish up the implementation that we are going to finish
N | 5 | 5 | Work on documents
Y | 1 | 1 | Meet with sponsor
| 13 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Work on more documentation
|  | 2 | Hand-off help
|  | 7 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 5 | Work on more documentation
Y | 1 | 2 | Hand-off help
| 3 | 3 | Presentation
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Documents
|  | 2 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Documents
| 2 | 2 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
6.5 | 9.25 | 7.25 | 10.25 | 12.5 | 12 | 12 | 8.25 | 8.25 | 11.25 | 11.5 | 12 | 12 | 14 | 11 | 12 | 11 | 14 | 14.5 | 9.5 | 10.5
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
14 | 14 | 15 | 15 | 13 | 18 | 15 | 16 | 14 | 20 | 16 | 26 | 16 | 31 | 31 | 29 | 11 | 13 | 10 | 9 | 2 | 2