## Instructions
Your Name: | Maerten, Trevin
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1 |  | View current system
Y | 3 |  | Meeting with sponsor
N | 2 |  | Investigate options for project
Y | 1 |  | Initial senior project meeting
| 7 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Investigate options for project
|  | 2 | Meeting with sponsor
|  | 3 | Team Meeting
|  | 2 | Further research on current state of application
|  | 10 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
N | 1 | 3 | Investigate options for project
Y | 3 | 2 | Meeting with sponsor
N | 0 | 3 | Team Meeting
N | 4 | 2 | Further research on current state of application
Y | 1 |  | Initial work with project synopsis
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with sponsor
|  | 2 | Team Meeting
|  | 2 | Further research on current state of application
|  | 2 | Project Synopsis
|  | 2 | Project Scenario
|  | 10 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2 | Meeting with sponsor
Y | 2 | 2 | Team Meeting
N | 1.25 | 2 | Further research on current state of application
N | 1 | 2 | Project Synopsis
Y | 2.25 | 2 | Project Scenario
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meeting with sponsor
|  | 4 | Team Meeting
|  | 2 | Project Synopsis
|  | 2 | Explore C# and other project tools.
|  | 0.25 | Time Reporting
|  | 0.5 | Set up bitbucket and Mercurial
|  | 11.75 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Meeting with sponsor
| 2 | 4 | Team Meeting
| 1 | 2 | Project Synopsis
| 2 | 2 | Explore C# and other project tools.
| 0.25 | 0.25 | Time Reporting
| 0.75 | 0.5 | Set up bitbucket and Mercurial
| 3 |  | Requirements document
| 11 | 11.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Requirements document
|  | 2 | Team Meeting
|  | 0.25 | Time Reporting
|  | 2 | Architecture planning
|  | 2 | Sponsor Meeting
|  | 10.25 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
N | 2.5 | 4 | Requirements document
Y | 2.5 | 2 | Team Meeting
Y | 0.25 | 0.25 | Time Reporting
N | 2 | 2 | Architecture planning
Y | 2 | 2 | Sponsor Meeting
| 9.25 | 10.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Requirements document, next draft
|  | 0.25 | Time reporting
|  | 4 | Architecture planning
|  | 2 | Meeting with OCECS co-ops
|  | 2 | Sponsor Meeting
|  | 10.25 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 1.25 | 2 | Requirements document, next draft
Y | 0.25 | 0.25 | Time reporting
N | 5 | 4 | Architecture planning
Y | 1 | 2 | Meeting with OCECS co-ops
Y | 2 | 2 | Team meeting
Y | 2 | 2 | Sponsor Meeting
| 11.5 | 12.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Database design
|  | 2 | Team meeting
|  | 2 | Meeting with Sponsor
|  | 7 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
N | 5 | 3 | Database design
Y | 5.5 | 2 | Team meeting
N | 0 | 2 | Meeting with Sponsor
Y | 1 |  | Meeting with Jacqueline Mozrall
| 11.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team meeting
|  | 2 | Meeting with sponsor
|  | 4 | Interviews
|  | 1 | Database Design
|  | 2 | Mockups
|  | 11 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | Team meeting
|  | 2 | Meeting with sponsor
|  | 4 | Interviews
|  | 1 | Database Design
|  | 2 | Mockups
| 0 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Work on architecture
|  | 2 | Team Meeting
|  | 1 | Presentation preparation
|  | 2 | Present
|  | 2 | Continue requirements document
|  | 11 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Work on architecture
| 2 | 2 | Team Meeting
| 1 | 1 | Presentation preparation
| 2 | 2 | Present
| 2 | 2 | Continue requirements document
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Attend presentations
|  | 2 | Sponsor meeting
|  | 5 | Architecture document
|  | 2 | Make final changes to requirements document
|  | 11 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Attend presentations
| 1.5 | 2 | Sponsor meeting
| 6 | 5 | Architecture document
| 1 | 2 | Make final changes to requirements document
| 10.5 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Reflection with coach
|  | 3 | Reflection document
|  | 1 | Peer reviews
|  | 5 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Reflection with coach
| 4 | 3 | Reflection document
| 1 | 1 | Peer reviews
| 6 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Team Meeting for Implementation
|  | 2 | Sponsor Meeting
|  | 5 | Architecture Document
|  | 12 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 4 | 5 | Team Meeting for Implementation
| 2 | 2 | Sponsor Meeting
Y | 3 | 5 | Architecture Document
| 9 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Continue Implementation
|  | 2 | Meeting
|  | 12 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 8 | 10 | Continue Implementation
| 1 | 2 | Meeting
| 9 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Continue Implementation
|  | 10 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 10 | 10 | Continue Implementation
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Begin Project Poster
|  | 5 | Begin Technical Report
|  | 4 | Continue Implementation
|  | 2 | Meeting with Sponsor
|  | 15 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 2 | 4 | Begin Project Poster
| 4 | 5 | Begin Technical Report
| 3 | 4 | Continue Implementation
| 1 | 2 | Meeting with Sponsor
| 10 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meet with Sponsor
|  | 5 | Continue Poster
|  | 4 | Continue Implementation
|  | 10 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 1 | Meet with Sponsor
| 4 | 5 | Continue Poster
| 4 | 4 | Continue Implementation
| 8 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Continue Poster
|  | 3 | Continue Technical Report
|  | 5 | Continue Implementation
|  | 11 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Continue Poster
| 3 | 3 | Continue Technical Report
| 3 | 5 | Continue Implementation
| 9 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Finish Poster
|  | 5 | Start Presentation
|  | 5 | Continue Implementation
|  | 15 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 3 | 5 | Finish Poster
| 3 | 5 | Start Presentation
| 2 | 5 | Continue Implementation
| 1 |  | Meeting with sponsor
| 9 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Final touches on Poster
|  | 4 | Continue Presentation
|  | 4 | Continue Implementation
|  | 12 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Final touches on Poster
| 3 | 4 | Continue Presentation
| 3 | 4 | Continue Implementation
| 1 |  | Meeting with sponsor
Y | 2 |  | Poster Day
| 13 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Finish Presentation
|  | 1.5 | Poster Signing
|  | 9.5 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 6 | 8 | Finish Presentation
Y | 1.5 | 1.5 | Poster Signing
| 1 |  | Meeting with sponsor
| 8.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Presentations
|  | 3 | Final touches on Presentation
|  | 2 | Meeting with Jim's co-ops
|  | 9 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 4 | 4 | Presentations
Y | 2 | 3 | Final touches on Presentation
| 2 | 2 | Meeting with Jim's co-ops
| 1.5 |  | Dinner with Sponsor
| 9.5 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meeting with Coach
|  | 1 | Hand off project
|  | 5 | Finish reflection and other documents
|  | 7 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Meeting with Coach
Y | 1 | 1 | Hand off project
Y | 6 | 5 | Finish reflection and other documents
| 8 | 7 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
7 | 10 | 9 | 10 | 9 | 11.75 | 11 | 10.25 | 9.25 | 12.25 | 11.5 | 7 | 11.5 | 11 | 0 | 11 | 11 | 11 | 10.5 | 5 | 6
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
12 | 9 | 12 | 9 | 10 | 10 | 15 | 10 | 10 | 8 | 11 | 9 | 15 | 9 | 12 | 13 | 9.5 | 8.5 | 9 | 9.5 | 7 | 8