## Sheet1
Museum Experience Survey
ID | Risk | Description | Probability of occurence | Impact Loss or Cost in Weeks | Risk Exposure in Weeks | Warning Signs | Mitigation approach
1 | Incomplete Requirements | We may do a bad job at thinking of all the questions we need to ask the sponsor and getting all of the requirements. Missing something may mean the sponsor is unhappy and/or we have to redo some work. | 0.4 | 3 | 1.2 | The customer is often unhappy with what we have done so far or complains about missing things we weren't aware of. | We should take the time in the begining to go over every detail we can think of and come up with a requirements document. We should go over the document with the customer to make sure he agrees. Also we should pay attention to changing requirements as the project progresses and document all changes.
2 | Defined requirements turn out to be impossible to implement (perhaps due to other constraints) | As we get into the project and get more experienced we may find some things that were requested will not be possible | 0.05 | 2 | 0.1 | We plan out development work and start to relize one or more things won't be able to be done as we originally planned | Try to plan out things completely and early. Hopefully we can make sure everything is going to be able to be done before we start working.
3 | Scope creep as project progresses | Stakeholders in this project may think of more and more things that would be nice to have in the project | 0.25 | 2 | 0.5 | Customer starts asking for more things after requirements have been agreed upon, or developers start to work on new things that would be "cool" to have but weren't part of the requirements. | As a development team we must stay on task and accomplish only what we planned and leaves extras for the end if we have more time. Also we cannot be afraid to tell the sponsor no if adding new requirements is not doable.
4 | Poor estimation | A planned phase of development may take longer than expected due to poor estimation of tasks. | 0.5 | 3 | 1.5 | Development on certain things takes longer than expected. | We can do our best at estimating but it's very hard to be correct. As things change we should look at the rest of the schedule and make sure it will still work, and if not make appropriate changes and discuss with the customer if needed.
5 | Team’s other commitments get in the way | Multiple team members have jobs and other responsibilities that may cause conflicts with the scheduling of the project. | 0.1 | 1 | 0.1 | Team members fall behind in scheduled work because they didn't have time | Individual time management is crucial for each member. Everyone has to be aware of how much they're capable of doing and look at their other responsibilities before agreeing to do anything. If someone does start falling behind communication is important. We may be able to shift the work load around to make up for lag.
6 | Not enough time dedicated to testing | Dedicating all of our time to deliverables and development may lead to skimping on fully testing things out. The later bugs are found the more costly they are. | 0.25 | 2 | 0.5 | Bugs start coming up more and more as we start development | We should schedule time to perform testing and not just test as we go (unless testing as you go involves writing formal tests). We want to find bugs early as there is usually less cost to fix a bug earlier than later.
7 | Problems setting up tools for tracking and posting project progress (website/third partying tracking tools) | The team website may be harder to set up the way we want then we first thought, or we may get more involved with it than we should. Tools we decide to use to track progress may take time to set up or get licenses for. | 0.025 | 1 | 0.025 | We are in need of setting up a tool after we've begun tasks that should be tracked | Set up the tools early so we have something to work with and don't procrastinate
8 | Third party tools and applications have problems or become unavailable | Hosted repository, google docs, diagram tools, documentation tools. These all have the potential to go down or not work as expected. | 0.08 | 1 | 0.08 | Development is blocked because of a 3rd party tool being unavailable or not working | Have backups for some of the tools, like other documenting tools than google docs for example. If something critical goes down, communicate with the rest of the team what is happening.
9 | Problems emulating customer hardware | The windows based virtual machine provided by the SE department is not the same as the hardware the museum uses. This may cause issues to arise when testing it out on their machines. Also if the customer ends up running this on an Android Tablet, we won't be able to test that early, if at all, since the customer does not yet own such devices. | 0.15 | 2 | 0.3 | We run into hardware specific probelms. | Take note of anything that's causing issues that's dependent on the operating system or hardware being used, as it may not be that way on the hardware/OS the customer has. Try to use technologies that are less hardware/OS dependent.
10 | Getting answers to questions from the museum staff may take longer than expected | Currently we don’t have direct contact with the museum staff. If the project sponsor does not know the answer to a question we must wait for him to ask the museum staff and get back to us. | 0.75 | 2 | 1.5 | We are blocked because we are waiting on a response from the museum staff. | Work on other parts that aren't dependent on the staff's answers so that we are not completely blocked. Also we could assume the most likely answer if it is something that is easily changed once we get our answer.
11 | Questions for the project sponsor may take longer than expected. | Our project sponsor does not live close to RIT so our only forms of contact are email and scheduled phone calls. He also has many other responsibilities so getting back to us quickly is not always possible. | 0.4 | 2 | 0.8 | We are blocked because we are waiting on a response from the sponsor | Again, work on other parts that aren't dependent on the sponsor's answers. Try to ask as many questions as we can during our scheduled meetings.
12 | Developers will have to learn some new technologies for this project | Getting everyone educated to start developing and working with the chosen technologies may take longer than expected. | 0.8 | 1 | 0.8 | Developers are late to start a task or taking longer than planned because they are still learning how to use the chosen technology | Try to choose technologies at least some of the team members have experience with, or choose technologies that are similar to things the team does have experience with (like familiar languages but a new framework, rather than a new framework and a new language)
13 | Trying to create something that is usable on many different sized devices and browsers | Our goal is to be compatible with the default browsers of Andoird and iOS devices, the most popular desktop browsers, along with fitting 3 very different screen sizes (desktops, tablets, smartphones). Being compatible with so many different things may be challenging. | 0.1 | 1 | 0.1 | We start to see our product behaving odd or just not working on certain devices/browsers | Test early and often. Try to get our hands on as many different devices as we can to try out our system so we don't leave the surprises until the end. Also make reccommendations to the customer on what works best with our system if they have the freedom to choose their hardware/software.
14 | Unfamiliarity with install software | Installing a certain version of java or other language, a web server, and perhaps a database and setting up any other parts of the environment may be more work than anticipated since we dont know installer code. | 0.25 | 2 | 0.5 | The work involved to install our product looks like it will be challenging. | Think about this early and let it influence our technology choices. Some things may be easier to auto-install than others (languages, web servers, databases). Also some may work better/ be easier to install on windows, which is our target OS for the sever.
|  |  |  | Total Risk Exposure: | 8.005