## Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Strategy | Status
1 | Not finish the project on time due to team's lack of proficiency in Java. | 0.05 | high | 0.5 | development | ALL | Seek help from team memebers and project advisors.
2 | Scope of the project is too large to finish on time. | 0.35 | high | 3.5 | requirements | RB | Talk to the customers to better understand the scope of the project and also make sure the customers understand how certain requirements can affect the scope of the project.
3 | Losing a team member during the lifetime of the project. | 0.1 | high | 1 | development | ALL | Team roles will vary and overlap so that no one is solely responsible for key elements of the project. Project files are stored in a central repository.
4 | The development team do not understand the problem's domain which leads to incorrect implementation of the system. | 0.35 | high | 3.5 | requirements | DR | Talk to the customers to better understand the problem and discuss and review artifacts with the customers every iteration of the project.
5 | The system does not run fast enough to handle a large volume of data. | 0.2 | low | 0.2 | development | DR, AKL | Allocate time to perform system optimization
6 | System is difficult to use due to poor documentation. | 0.3 | med | 1.5 | documentation | BG | Follow Java coding standard to generate javadocs. Allocate time to create documentations during planning.
7 | Poor requirements and specifications lead to difficulty developing the system. | 0.2 | high | 2 | requirements | MH | Review within the team and get customer feedback on unclear specifications.
8 | Changing requirements during the project lifetime. | 0.2 | med | 1 | requirements | RB | Talk to the customers to better understand the requirements of the project gathered by the team and also make sure the customers understand how changing certain requirements can affect the project.
9 | Loss of data and files due of human and machine failures | 0.1 | high | 1 | all phases | RB | Use a central repository to backup data. Periodically back up that repository.
10 | Testing fails to cover all requirements and use cases. | 0.25 | med | 1.25 | testing | BG | Document test cases to ensure the coverage of all requirements and use cases.
11 | Configurations of all software components (such as MySQL, CVS) involved in the system. | 0.1 | med | 0.5 | development | RB, AKL | Setup the software components before the start of the development. Get help from administrators in SE department.
12 | Test data is not diverse enough to cover all equivalence partitions. | 0.15 | med | 0.75 | testing | BG | Figure out different equivalence partitions and manually create records for each partition type
13 | Team neglects certain test cases. | 0.15 | med | 0.75 | testing | BG | Document and track the status of each test case.
14 | Personnel problems within the team. | 0.2 | high | 2 | all phases | ALL | Implement time outs.
15 | Not finish the project on time due to team's lack of proficiency in SQL. | 0.2 | med | 1 | development | AKL | Seek help from team memebers and project advisors.
16 | Not finish the project on time due to team's lack of proficiency in XML. | 0.2 | med | 1 | development | MH | Seek help from team memebers and project advisors.
17 | Time conflicts among team members and customers which makes it difficult to meet. | 0.25 | med | 1.25 | all phases | ALL | Plan ahead. Document available time of team members. Divide up workload to reduce meeting time.
18 | Project slippage prevents deliving system by end date | 0.25 | high | 2.5 | all phases | RB | Setting reasonable, aggressive deadline to mitigate against slipping the project delieverables.
19 | Not finish the project on time due to team's lack of proficiency in Hibernate | 0.2 | high | 2 | development | DR | Allocate time to learn Hibernate
20 | Poor performance | 0.3 | med | 1.5 | development | DR | Optimize program for multiprocessor systems
21 |  |  |  | 0
22 |  |  |  | 0
23 |  |  |  | 0
24 |  |  |  | 0
25 |  |  |  | 0
26 |  |  |  | 0
27 |  |  |  | 0
28 |  |  |  | 0
0
0
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Exposure = Probability * risk This is the primary sort field.
Note on F1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on G1: Responsible person working to mitigate the risk.
Note on H1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.
Note on I1: History of the status of the risk.