## Instructions
Your Name: | Chris Nurre
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
| 0 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Thursday Meeting (with sponsor)
Y | 1 | 1 | Caught up with documentation
Y | 2 | 2 | worked on use cases
| 5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sunday Meeting / More Use Case Diagrams
|  | 2 | Tuesday Meeting / Meeting with group, finish up documents
|  | 2 | Thursday Meeting (meet with sponser)
|  | 6 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | Sunday Meeting / More Use Case Diagrams
|  | 2 | Tuesday Meeting / Meeting with group, finish up documents
|  | 2 | Thursday Meeting (meet with sponser)
| 0 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
N | 8 | 5 | SRS Document
Y | 2 | 2 | Tuesday Meeting
Y | 2 | 2 | Meeting with Co-Op (authentication)
Y | 2 | 2 | Thursday meeting with Customer
Y | 1 | 1 | Meet with customer to discuss SRS
| 15 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Finish SRS
|  | 2 | Tuesday Presentations
|  | 2 | Thursday Presentation
|  | 4 | Prepare for presentation
|  | 11 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 5 | 3 | Finish SRS
| 2 | 2 | Tuesday Presentations
| 2 | 2 | Thursday Presentation
| 10 | 4 | Prepare for presentation
| 19 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
N | 6 | 6 | Student Service
N | 3 | 3 | Authentication Module
N | 3 | 3 | Datasource Connection
Y | 6 | 6 | Tuesday, Thursday, Sunday
| 18 | 18 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Authentication Module
|  | 5 | Datasource Connection
|  | 10 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
N | 3 | 5 | Authentication Module
N | 3 | 5 | Datasource Connection
Y | 3 | 3 | Student Service
Y | 6 | 6 | Tuesday, Thursday, Sunday
| 15 | 19 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 6 | Authentication Module
|  | 6 | Datasource Connection
|  | 6 | Student Service
|  | 6 | Tuesday, Thursday, Sunday
|  | 24 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
N | 15 | 6 | Authentication Module
N | 1 | 6 | Datasource Connection
N | 6 | 6 | Student Service
Y | 6 | 6 | Tuesday, Thursday, Sunday
| 28 | 24 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Authentication Module
|  | 3 | Datasource Connection
|  | 5 | Authorization Module
|  | 6 | Tuesday, Thursday, Sunday
|  | 5 | Test Plan
|  | 24 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
|  | 5 | Authentication Module
|  | 3 | Datasource Connection
|  | 5 | Authorization Module
|  | 6 | Tuesday, Thursday, Sunday
|  | 5 | Test Plan
| 0 | 24 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem