## Instructions
Your Name: | Juan Obes
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
| 2 |  | Initial presentation
| 2 |  | Meet with group
| 4 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 4 |  | Meet with group and client
| 1 |  | Write project synopsis
| 5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Start initial project planning
|  | 3 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Start initial project planning
| 3 | 3 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | research technologies
|  | 2 | plan project process
|  | 2 | client meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | research technologies
| 2 | 2 | plan project process
| 2 | 2 | client meeting
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Start high level architecture
|  | 2 | Use cases
|  | 2 | Client meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Start high level architecture
| 2 | 2 | Use cases
| 2 | 2 | Client meeting
| 2 |  | Plan XML contract
| 8 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Client meeting
|  | 2 | Use cases
|  | 2 | XML, WSDL document
|  | 6 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Client meeting
| 2 | 2 | Use cases
| 2 | 2 | XML, WSDL document
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Use cases
|  | 2 | Study database info
|  | 2 | Client meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Use cases
| 2 | 2 | Study database info
| 2 | 2 | Client meeting
| 1.5 |  | Friday user meeting
| 0.5 |  | Meeting with Co-ops
| 8 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Tuesday meeting with co-ops
|  | 2 | Client meeting
|  | 3 | review SCRUM process
|  | 6 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 1 | Tuesday meeting with co-ops
| 2 | 2 | Client meeting
| 3 | 3 | review SCRUM process
| 3 |  | SCRUM documents
| 8 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | SCRUM documents
|  | 4 | Project presentations
|  | 2 | Presentation work
|  | 10 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | SCRUM documents
| 4 | 4 | Project presentations
| 8 | 2 | Presentation work
| 16 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Team meetings
|  | 2 | Customer meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Team meetings
| 2 | 2 | Customer meeting
| 6 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Finals week meeting
|  | 1 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Finals week meeting
| 0 | 1 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem