## Instructions
Your Name: | Michael Yatzkanic
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
| 0 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Create high level system architecture diagram
| 2 | 2 | Study xml document format
|  | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | study xml document format
|  | 2 | continue use cases
|  | 2 | draft system architecture document
|  | 7 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
n | 2 | 3 | study xml document format
n | 0 | 2 | draft system architecture document
y | 1 | 2 | drew up example sequence diagrams - part of team meeting
| 3 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | 5 use cases - external use
|  | 1 | look at database placement info
|  | 2 | draft up arch document
|  | 5 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
y | 1.5 | 2 | 5 use cases - external use
y | 1 | 1 | look at database placement info
| 2 |  | met with chris to talk about function points and xml document
| 2 | 2 | tuesday team meeting
| 0.5 |  | meeting with co-ops on tuesday
| 2 | 2 | meeting sunday
| 0 | 2 | thursday meeting
| 9 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | powerpoint for presentation
|  | 2 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | project presenation (in progress)
| 0 | 2 | sunday meeting
| 2 | 2 | tuesday meeting
| 2 | 2 | thursday meeting
| 2 | 3 | self studying of code base
| 8 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 4 | 2 | sunday meeting
| 2 | 2 | tuesday meeting (presentations)
| 2 | 2 | thursday meeting
| 2 | 3 | finish presentation (work in progress, 2 on monday)
| 2 |  | presentation meeting & talk with dan after se presentations
| 2 |  | team meeting after presentations
| 3.5 |  | team presentation wrapup
| 17.5 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | sunday meeting
y | 2 | 2 | tuesday meeting
y | 1 | 2 | thursday meeting
n | 2 | 3 | redesign and update website to include all scrum artifacts
| 7 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | wrap up website update
|  | 1.5 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1.5 | finish up website redesign
y | 2 | 2 | sunday meeting
|  | 1 | tuesday meeting
| 3 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
spring break
use cases
|  | 0 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 1.5 | 2 | Tuesday meeting
Y | 2 | 2 | Thursday meeting
N | 1 | 1 | Looked into how vs.net 2005 xml comments work
| 4.5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
Work on student web service
Create format for documenting code
make sure svn is fully working and check in code
|  | 0 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Sunday meeting with dan (started service work, setting up environments)
| 5 | 3 | Sunday independant work - setup local copy of code, tried to get student service going but could not figure out what tables are used for the 'student status' report, installed visio (perosnal copy from msdn) so i could generate uml of database tables
| 2 | 2 | Tuesday meeting
| 2 | 2 | Thursday meeting
| 1 |  | talked with Jim about db setup
N | 4.5 | 4 | setup project on my computer, created uml for all tables required for student status, other misc things. Started mapping out placement service
| 14.5 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | map out placement service (all required database tables, functions, etc)
|  | 4 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
y | 3 | 4 | map out placement service (all required database tables, functions, etc)
y | 0 | 0 | Sunday meeting - missed due to Easter
y | 4 | 4 | Tuesday meeting (including time spent with co-ops)
y | 2 | 2 | Thursday meeting
y | 0.75 | 1 | Updated team website with team minutes and scrum minutes that were not published yet.
| 9.75 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | sunday meeting
y | 2 | 2 | tuesday meeting
y | 2 | 2 | thursday meeting
y | 1 | 1 | stub out placement service
n | 2 | 3 | start coding functionality into placement service
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 7 | 5 | sunday team meeting - spent all day coding placement service. ran into a bug in the old code, tried to resolve it
| 2 | 2 | tuesday team meeting
| 3.5 | 4 | personal coding
| 2 | 2 | thursday meeting
| 14.5 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | get draft of poster to Dan by the 17th in pdf format
|  | 4 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | sunday meeting - poster draft design
y | 1 | 1 | fill in my sections for the poster draft
| 2 | 2 | tuesday meeting - poster draft and coding
| 4 | 3 | placement service - addition of 2nd level functions to the service
| 2 | 2 | thursday meeting
| 11 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | sunday meeting
| 2 | 2 | tuesday
| 2 | 2 | thursday
| 4 | 3 | sunday self coding
| 10 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
sunday meeting
tuesday meeting
thursday meeting
thursday after meeting with Phil
Thursday coding changes to placement
Friday finish changes to placement
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 2 |  | sunday meeting
| 3 |  | sunday self coding
| 11.5 | 8 | monday coding session
| 2 | 2 | tuesday presentations
| 1 | 2 | wednesday presentation prep
| 2 | 2 | thursday presentations
| 21.5 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | update website
| 1 | 2 | start technical report
| 1 | 1 | tuesday team meeting
| 3 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 3 | finish technical report and other odds and ends
| 0 | 3 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem