## Team Reporting
NOBY | Project |  | Winter |  | Spring |  | Winter Term | [20 empty] | Spring Term
| Act | Est | Act | Est | Act | Est | Wk1Act | Wk2Est | Wk2Act | Wk3Est | Wk3Act | Wk4Est | Wk4Act | Wk5Est | Wk5Act | Wk6Est | Wk6Act | Wk7Est | Wk7Act | Wk8Est | Wk8Act | Wk9Est | Wk9Act | Wk10Est | Wk10Act | FinalsEst | FinalsAct | Wk1Act | Wk2Est | Wk2Act | Wk3Est | Wk3Act | Wk4Est | Wk4Act | Wk5Est | Wk5Act | Wk6Est | Wk6Act | Wk7Est | Wk7Act | Wk8Est | Wk8Act | Wk9Est | Wk9Act | Wk10Est | Wk10Act | FinalsEst | FinalsAct
J. Daniel Behun | 144 | 116.5 | 91 | 71 | 53 | 36 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 8 | 6 | 7 | 7 | 10.5 | 7.5 | 7.5 | 9 | 17.5 | 6 | 6 | 4.5 | 7 | 7 | 6 | 7.5 | 8 | 8 | 7 | 9 | 8 | 10 | 7 | 11.5
Chris Nurre | 84 | 62 | 84 | 62 | 0 | 0 | 4 | 4 | 4 | 6 | 6 |  |  |  |  | 6 | 6 | 6 | 15 | 12 | 15 | 11 | 19 | 6
Juan Obes | 75.5 | 63 | 75.5 | 63 | 0 | 0 | 6 | 4 | 5 | 3 | 3 | 6 | 6 | 6 | 8 | 6 | 6 | 6 | 8 | 6 | 8 | 10 | 17.5 | 6
Michael Yatzkanic | 197.5 | 176 | 87 | 80.5 | 110.5 | 95.5 | 4 | 4 | 5 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 8 | 9 | 9 | 11 | 8 | 9 | 16 | 9 | 7 | 4.5 | 3 | 4.5 | 12 | 14.5 | 11 | 9.75 | 10 | 9 | 13 | 14.5 | 10 | 11 | 9 | 10 | 9.5 | 12.75 | 14 | 21.5 | 4 | 3 | 3
Team totals | 501 | 417.5 | 337.5 | 276.5 | 163.5 | 131.5 | 18 | 16 | 18 | 22 | 22 | 18 | 18 | 18 | 22 | 24 | 27 | 28 | 42.5 | 36.5 | 38.5 | 39 | 70 | 27 | 13 | 9 | 10 | 11.5 | 18 | 22 | 19 | 17.75 | 17 | 18 | 21 | 24.5 | 17 | 22.5 | 9 | 10 | 9.5 | 12.75 | 14 | 21.5 | 4 | 3 | 3 | 0

## Instructions
Team Name: | NOBY
Individual reporting file names: | J. Daniel Behun
Chris Nurre
Juan Obes
Michael Yatzkanic
Instructions
Fill in your team name above.
Fill in the name of each team member's weekly reporting file above including the .xls extension.
Each week report time/effort worked by individual team members and aggregate for the team.
You need to have all team member's individual files open to update the information in the weekly team file. If you do not you will get a #REF! error.