Senior Project RED Flags

(Compiled from observations of past senior projects)

1.      Team over commits, experiences early project burn-out or late project frustration.

(Scope, scope, scope – realistically scope your project and establish reasonable deliverables given the fixed constraints of time and resources,)

2.      Team creates a well written project plan – and then never looks at it again.

(The project plan is a living document that needs to be tracked and tuned as the project progresses)

3.      Team tracks progress using the following phrases:

a.       “…investigating new technologies…”

b.      “…spent time playing with new tools…”

c.       “…researching alternatives to problem X…”

(Identify and track project outcomes (deliverables). Use small incremental milestones to better communicate and understand your progress.)

4.      Team devotes time and resources to creating home-grown tools – bug trackers, etc.

(There is an abundance of available project tools, use them. Do not squander project resources on non-project related tasks.)

5.      Major project deliverables scheduled for end of Spring quarter. (a.k.a. - "Dump and Run")

(In reality you should plan on significant deliveries of software no later than mid-April. This allows for training and support issues as they arise over the last month. May is a crazy month – plan accordingly.)

6.      Team’s only project deliverables to the sponsor are scheduled for the end of Spring quarter.

(Even if the sponsor doesn’t request it, plan for incremental releases – as frequently as possible to get feedback and insure you are meeting the sponsors expectations.)

7.      Team defines process and metrics the night before the first project presentation.

(Don’t fake it – it’s obvious when teams are doing so. Take time in the beginning of the project to identify a sufficient development methodology in your project plan.)

8.      Team complains in the Spring about all the “extra” work required of them in the form of project reports and poster presentations.

(There is no extra work. These are course deliverables that are defined at the start of the project and should be accounted for in the team’s schedule. They are also items that can be worked on incrementally throughout the project.)

9.      Senioritis sets in as May approaches.

(This is a natural phenomena and much like a marathon runner hitting the wall, it takes a little self discipline and support from your team members to get over the hump. Sign a team contract that allows team members to “intervene” when another member is displaying senioritis symptoms.)