## BPP Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Strategy | Status
1 | OBEX layer must be implemented from scatch. | 1 | Med | 5 | Research | All | Find open source OBEX implementations to guide development. | Unresolved
2 | 3Com dongles are not compatible with Windows XP SP2 Bluetooth stack. | 0.5 | High | 5 | Research | All |  | Partially resolved. Research indicates that steps may be taken to make the 3Com dongles compatible.
3 | OPP and FTP may be within the project scope. | 1 | Med | 5 | Requirement | Kyle | Contact Kodak ASAP to define project scope. | Resolved, we are respsonsible for implementing OPP and FTP
4 | The Windows XP SP2 Bluetooth C++ API must interact with C#. | 1 | Med | 5 | Development | All | TBD at the design phase. | Unresolved
5 | Lack of experience with Bluetooth programming among the development team. | 1 | High | 10 | Development | All | Study the documentation provided by Kodak as well as any appropriate supplemental resources. | Partially resolved. Sof documentation and tutorials have been found and utilized.
6 | Kodak does not give us the API that they will use to access the protocol stack | 0.3 | Med | 1.5 | Requirement | Kyle | If we don't receive it by 01/28/05 we will write the API ourselves. | Unresolved
7 | There may not be SOAP support in C#? | 0.1 | Med | 0.5 | Development | All | Verify .NET Framework support for SOAP | resolved
8 | We don't know how to utilize SDP | 1 | High | 10 | Research | All | Find documentation | Unresolved
9 | We don't know how to use the Merlin Bluetooth Analyzer | 1 | Low | 1 | Research | All | Read user manual | Resolved, we figured out how to utilize this tool.
10 | Stack is responsible for session management instead of the Kiosk application. | 0.5 | High | 5 | Requirement | All | We have to include session management in our stack implementation. | Unresolved - we are waiting for a response from Kodak
11 | We are responsible for restricting the access to the Kiosk to one user at a time. | 0.3 | High | 3 | Requirement | All | We have to include security measures in our stack to ensure that only one user sends data to the Kiosk at one time | Unresolved - we are waiting for a response from Kodak
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Exposure = Probability * risk This is the primary sort field.
Note on F1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on G1: Responsible person working to mitigate the risk.
Note on H1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.
Note on I1: History of the status of the risk.