## BPP Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Strategy | Status | Date of Resolution
1 | OBEX layer must be implemented from scatch. | 1 | Med | 5 | Research | All | Find open source OBEX implementations to guide development. | Unresolved
2 | 3Com dongles are not compatible with Windows XP SP2 Bluetooth stack. | 0.5 | High | 5 | Research | All |  | Partially resolved. Research indicates that steps may be taken to make the 3Com dongles compatible.
3 | OPP and FTP may be within the project scope. | 1 | Med | 5 | Requirement | Kyle | Contact Kodak ASAP to define project scope. | Resolved, we are respsonsible for implementing OPP and FTP
4 | The Windows XP SP2 Bluetooth C++ API must interact with C#. | 1 | Med | 5 | Development | All | TBD at the design phase. | Unresolved
5 | Lack of experience with Bluetooth programming among the development team. | 1 | High | 10 | Development | All | Study the documentation provided by Kodak as well as any appropriate supplemental resources. | Partially resolved. Sof documentation and tutorials have been found and utilized.
6 | Kodak does not give us the API that they will use to access the protocol stack | 0.3 | Med | 1.5 | Requirement | Kyle | If we don't receive it by 01/28/05 we will write the API ourselves. | Resolved, We have the API
7 | There may not be SOAP support in C#? | 0.1 | Med | 0.5 | Development | All | Verify .NET Framework support for SOAP | resolved
8 | We don't know how to utilize SDP | 1 | High | 10 | Research | Kyle and Ray | Find documentation, Use MSDN support | Resolved, Microsoft provided us with the information we needed to get SDP working. | 2005-02-03
9 | We don't know how to use the Merlin Bluetooth Analyzer | 1 | Low | 1 | Research | All | Read user manual | Resolved, we figured out how to utilize this tool.
10 | Stack is responsible for session management instead of the Kiosk application. | 0.5 | High | 5 | Requirement | Kyle and Ray | We have to include session management in our stack implementation. | Resolved - Kiosk App is responsible
11 | We are responsible for restricting the access to the Kiosk to one user at a time. | 0.3 | High | 3 | Requirement | Kyle and Ray | We have to include security measures in our stack to ensure that only one user sends data to the Kiosk at one time | Resolved | 2005-02-01
12 | We never solve our technology issues and can't get bluetooth working. | 0.7 | High | 7 | Technical | Kyle and Ray | Implement it over TCP instead so that we can still complete our senior project. | Unresolved
14 | We need to adapt our software to work with the COM interface defined by Kodak. | 1 | Low | 1 | Development | All | We need to learn a little bit about COM and COM interfaces so we know how to do this | Unresolved
13 | The scope explosion that has occurred in this project will increase the time and amount of work required to complete the product to be greater than we can handle. | 0.4 | High | 4 | Schedule | Lorien | We need to work with Kodak to define the least important aspects of the project that can be omitted if necessary. | Unresolved
15 | There are complexities in the Protocol Stack that we don't fully understand and as a result come up with an architecture that doesn't fully meet our needs. | 0.7 | High | 7 | Development | Lorien | We will develop an architecture document that shows several views of the system including component interaction, layer view, and thread view to help us fully understand the problem and define an appropriate architecture. | Unresolved
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Exposure = Probability * risk This is the primary sort field.
Note on F1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on G1: Responsible person working to mitigate the risk.
Note on H1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.
Note on I1: History of the status of the risk.