## BPP Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Mitigation Strategy | Status | Date of Resolution
1 | OBEX layer must be implemented from scatch. | 1 | Med | 5 | Research | All | Find open source OBEX implementations to guide development. | Resolved, it does
2 | 3Com dongles are not compatible with Windows XP SP2 Bluetooth stack. | 0.5 | High | 5 | Research | All |  | Resolved, steps were taken to make the 3COM dongles compatible
3 | OPP and FTP may be within the project scope. | 1 | Med | 5 | Requirement | Kyle | Contact Kodak ASAP to define project scope. | Resolved, we are respsonsible for implementing OPP and FTP
4 | The Windows XP SP2 Bluetooth C++ API must interact with C#. | 1 | Med | 5 | Development | All | TBD at the design phase. | Unresolved
5 | Lack of experience with Bluetooth programming among the development team. | 1 | High | 10 | Development | All | Study the documentation provided by Kodak as well as any appropriate supplemental resources. | Partially resolved. Sof documentation and tutorials have been found and utilized.
6 | Kodak does not give us the API that they will use to access the protocol stack | 0.3 | Med | 1.5 | Requirement | Kyle | If we don't receive it by 01/28/05 we will write the API ourselves. | Resolved, We have the API
7 | There may not be SOAP support in C#? | 0.1 | Med | 0.5 | Development | All | Verify .NET Framework support for SOAP | resolved
8 | We don't know how to utilize SDP | 1 | High | 10 | Research | Kyle and Ray | Find documentation, Use MSDN support | Resolved, Microsoft provided us with the information we needed to get SDP working. | 2005-02-03
9 | We don't know how to use the Merlin Bluetooth Analyzer | 1 | Low | 1 | Research | All | Read user manual | Resolved, we figured out how to utilize this tool.
10 | Stack is responsible for session management instead of the Kiosk application. | 0.5 | High | 5 | Requirement | Kyle and Ray | We have to include session management in our stack implementation. | Resolved - Kiosk App is responsible
11 | We are responsible for restricting the access to the Kiosk to one user at a time. | 0.3 | High | 3 | Requirement | Kyle and Ray | We have to include security measures in our stack to ensure that only one user sends data to the Kiosk at one time | Resolved, we will provide API methods for the Kiosk App to restrict access to one device at a time. | 2005-02-01
12 | We never solve our technology issues and can't get bluetooth working. | 0.7 | High | 7 | Technical | Kyle and Ray | Implement it over TCP instead so that we can still complete our senior project. | Unresolved
14 | We need to adapt our software to work with the COM interface defined by Kodak. | 1 | Low | 1 | Development | All | We need to learn a little bit about COM and COM interfaces so we know how to do this | Partially resolved, have solved SDP
13 | The scope explosion that has occurred in this project will increase the time and amount of work required to complete the product to be greater than we can handle. | 0.4 | High | 4 | Schedule | Lorien | We are doing a fine grained task time estimate to show a clear picture of how much work is required. If we see too much work we will work with the customer to identify requirements that can be dropped if need arises. | Unresolved
15 | There are complexities in the Protocol Stack that we don't fully understand and as a result come up with an architecture that doesn't fully meet our needs. | 0.7 | High | 7 | Development | Lorien | We will develop an architecture document that shows several views of the system including component interaction, layer view, and thread view to help us fully understand the problem and define an appropriate architecture. | Unresolved
16 | We need a device that supports FTP and we may not be able to get one. | 0.7 | High | 7 | Technical |  | The customer is working on this now, may need to use a laptop that has FTP client | Unresolved
17 | The BPP requires support for XML with embedded binary data. This data format will be difficult to deal with and delay completion of the BPP. | 0.4 | High | 4 | Implementation | Paul | We will determine if this format is required, and if so, determine if available libraries may ease this burden. If it is required and implementation will dramatically delay release, the feature may be dropped. | Unresolved
18 | The BPP requires a feature that makes client requests to the client device. This feature will require development of a client subsystem that may be difficult to implement in the alotted time. | 0.4 | High | 4 | Design & Implementation | Paul | TBD | Unresolved
19 | Individual requirements are too vaguely defined to be the only source for acceptance tests. Some acceptance criteria will be neglected. | 0.4 | High | 4 | Implementation | All | The Bluetooth Specification will be an input to the Test Plan. | Unresolved
Note on A1: The risk ID is the sequential order of risk entry.
Note on B1: Identify the Risk.
Note on C1: Likelihood that the risk will occur. 1 means the risk will definitely occur.
Note on D1: What will be the impact on the program if the risk occurs. Relative ranking: low = 1 med = 5 high = 10
Note on E1: Exposure = Probability * risk This is the primary sort field.
Note on F1: Where will the biggest impact of the risk occur? Examples: Technical Schedule Reliability Cost/UMC
Note on G1: Responsible person working to mitigate the risk.
Note on H1: Plan or strategy to minimize the impact and/or reduce the probability that the risk occurs.
Note on I1: History of the status of the risk.