Preliminary Project Plan

PaeTec E911 System

2002-12-17

Royal Flush Software

Kevin Francis

Jason Plaisted

Michael O’Connor

Jessica St. Croix

Derrick Hudson

# Introduction

This project plan will outline the scope of our senior project, the roles of the team members, planned deliverables and milestones, and a tentative schedule.

The senior project for PaeTec Corporation entails rewriting their existing E911 provisioning system.  A new web-based user interface will be created using JSP Pages and shall support searching functionality and the entry of new/changed customer information.  Problems elicited from use of the current system will be addressed in the new user interface and the new UI will more effectively match the customer’s needs.  Enterprise Java Beans (EJB's) will be created for accessing PaeTec's local database. The data model shall also be improved by removing unnecessary data and more accurately modeling the real world information.  In addition, existing C++ code for outputting flat data files of E911 information to incumbent local exchange carriers will be rewritten in Java.  The main deliverable will be a multi-faceted Java software solution running on Microsoft Windows NT based system.

# Team Organization

## 2.1 Kevin Francis – Team Leader

Kevin will guide the organization of the team and meetings and ensure that the project progresses as planned.  He is the primary intermediary to provide communication between the team and Jon Templin, PaeTec’s representative.

## 2.2 Jason Plaisted – Planning Leader

Jason will oversee the planning of the project and ensure that schedules are reasonable and maintained.  He records meeting minutes and disseminates information to the team.

## 2.3 Michael O’Connor – Configuration Manager

Michael will support all the necessary tools for the project and handle configuration management issues.  He will maintain the web site and application server.

## 2.4 Jessica St. Croix – Development Leader

Jessica is responsible for supporting the development team, making development decisions, and ensuring the integration of the components will be successful.

## 2.5 Derrick Hudson – Testing Leader

Derrick will ensure that test cases are created, that the system has an automated test system, and that testing is performed successfully.

# Deliverables

  - Requirements document for enhancements to the user interface

  - Requirements document for improvements to the data model

  - A new J2EE-based user interface

  - Oracle-based implementation of the improved data model

  - A new Java implementation for propagating data changes to E911 system

  - A test report indicating the correctness level of the implementation

# Schedule

| Date | Action / Deliverable |
| --- | --- |
| Weeks1-3 | Review existing system and documentation |
| Week 3 | Create Project Plan |
| Weeks 4-6 | Gather Requirements / Deliver Requirements Document |
| Week 7 | Deliver Revised Data Model & Documentation |
| Week 8 | Architecture Document |
| Week 9 | Design Document |
| Week 10 | Begin Implementation |
| Week 12 | Begin Testing |
| Week 18 | Software Complete |
| Week 19 | Conclude Testing |
| Week 20 | Deliver Product |
| Week 20 | Presentation & Post Mortem |