## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-03-12 | 30 | Documentation | SAD (Data Model) | Updated the figure | Derrick
2003-03-12 | 30 | Coding | Data Model | Managed to create a table in Oracle | Derrick
2003-03-14 | 140 | Other | Oracle | Restored the ability to connect to oracle | Derrick
2003-03-10 | 60 | Team Meeting |  | Discussed SAD | Jason
2003-03-12 | 30 | Team Meeting |  | Discussed SAD | Jason
2003-03-12 | 150 | Documentation | SAD | Requirements Matrix | Jason
2003-03-13 | 90 | Documentation | SAD | Requirements Matrix | Jason
2003-03-13 | 30 | Documentation | Project Tracking | Meeting Minutes | Jason
2003-03-14 | 60 | Coding | Servlets | Stubbed out servlets | Jason
2003-03-14 | 160 | Design |  | Defining interface betweeen JSP's and servlets | Jason
2003-03-15 | 180 | Coding | Servlets | Worked on servlets | Jason
2003-03-15 | 60 | Design |  | Defining interface betweeen JSP's and servlets | Jason
2003-03-11 | 60 | Coding | EJB's | Made empty files for all of the EJB's and began work on the CustomerBean. | Jessica
2003-03-12 | 30 | Team Meeting |  | Discussed SAD | Jessica
2003-03-12 | 120 | Documentation | SAD | Editted the domain package diagram. | Jessica
2003-03-12 | 120 | Coding | EJB's | Made a first run at completing the Customer Bean. | Jessica
2003-03-12 | 45 | Coding | EJB's | Made a first run at completing the User Bean. | Jessica
2003-03-13 | 60 | Website |  | Added the 3/10 & 3/12 minutes, SRS, & updated schedule. | Jessica
2003-03-13 | 60 | Coding | EJB's | Made a first run at completing the Location Bean. | Jessica
2003-03-12 | 40 | Meeting | Architecture & Design | Meeting to discuss the necessary changes to the SAD. | Kevin
2003-03-12 | 120 | Documentation | SAD | Fixing diagrams updating SAD with changes. | Kevin
2003-03-14 | 160 | Design | JSPs & Servlets | Defining how JSPs and Servlets will work together and defining an interface between them. | Kevin
2003-03-14 | 120 | Coding | JSPs | Creating msagsearch.jsp and refining datatable to use java Vector | Kevin
2003-03-15 | 30 | Coding | JSPs | Fixing problems with msagsearch.jsp | Kevin
2003-03-15 | 130 | Coding | Servlets | Writing doGetfunction for MSAGSearchServlet | Kevin
2003-03-15 | 100 | Coding | ESBs | Writing SQL for MSAGBean.selectByAttributes | Kevin
2003-03-13 | 30 | Meeting | SAD | Team meeting | Mike
2003-03-13 | 60 | Documentation | SAD | Requirements Matrix - Schedules | Mike
2003-03-14 | 230 | Configuration | ALL | Configuration of webserver and generation of build scripts. Attempting to make this as easy as possible. Research for any special ejb deployment issues | Mike
2003-03-14 | 60 | Configuration | Server Side | Other server maintence. | Mike
2003-03-15 | 240 | Database | Database | Worked on the database and other misc tools. | Mike
Total Work Minutes for Week Ending On
| 2003-03-15 | 2003-03-22 | 2003-03-29
Kevin | 760
Jason | 820
Derrick | 200
Jessica | 535
Mike | 620

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Summary by Package
2003-03-12 | 30 | Coding | Data Model | Managed to create a table in Oracle | Derrick |  | Actual Man/Days | Expected Man/Days | Minutes
2003-03-11 | 60 | Coding | EJB's | Made empty files for all of the EJB's and began work on the CustomerBean. | Jessica | Data Model | 0.125 | 4 | 30
2003-03-12 | 120 | Coding | EJB's | Made a first run at completing the Customer Bean. | Jessica | EJB's | 2.4583 | 6 | 590
2003-03-12 | 45 | Coding | EJB's | Made a first run at completing the User Bean. | Jessica | JSP's | 1.4792 | 8 | 355
2003-03-13 | 60 | Coding | EJB's | Made a first run at completing the Location Bean. | Jessica | Servlets | 2.3958 | 9 | 575
2003-03-15 | 100 | Coding | ESBs | Writing SQL for MSAGBean.selectByAttributes | Kevin | UI Testing | 0 | 7 | 0
2003-03-14 | 120 | Coding | JSPs | Creating msagsearch.jsp and refining datatable to use java Vector | Kevin | C++ Code Conversion | 0 | 6 | 0
2003-03-15 | 30 | Coding | JSPs | Fixing problems with msagsearch.jsp | Kevin | Unit Testing | 0 | 6 | 0
2003-03-14 | 60 | Coding | Servlets | Stubbed out servlets | Jason | Normalization & Validation | 0 | 1 | 0
2003-03-15 | 180 | Coding | Servlets | Worked on servlets | Jason | Stored Procedures | 0 | 2 | 0
2003-03-15 | 130 | Coding | Servlets | Writing doGetfunction for MSAGSearchServlet | Kevin | Triggers | 0 | 2 | 0
2003-03-14 | 230 | Configuration | ALL | Configuration of webserver and generation of build scripts. Attempting to make this as easy as possible. Research for any special ejb deployment issues | Mike | Data Creation | 0 | 2 | 0
2003-03-14 | 60 | Configuration | Server Side | Other server maintence. | Mike
2003-03-15 | 240 | Database | Database | Worked on the database and other misc tools. | Mike
2003-03-14 | 160 | Design | JSPs & Servlets | Defining how JSPs and Servlets will work together and defining an interface between them. | Kevin
2003-03-14 | 160 | Design | JSPs & Servlets | Defining interface betweeen JSP's and servlets | Jason
2003-03-15 | 60 | Design | JSPs & Servlets | Defining interface betweeen JSP's and servlets | Jason | Server Side Config | 0.25 |  | 60
2003-03-13 | 30 | Documentation | Project Tracking | Meeting Minutes | Jason | Database | 1 |  | 240
2003-03-12 | 150 | Documentation | SAD | Requirements Matrix | Jason | Project Tracking | 0.125 |  | 30
2003-03-13 | 90 | Documentation | SAD | Requirements Matrix | Jason | SAD | 3.7917 |  | 910
2003-03-12 | 120 | Documentation | SAD | Editted the domain package diagram. | Jessica | Other | 1.2083 |  | 290
2003-03-12 | 120 | Documentation | SAD | Fixing diagrams updating SAD with changes. | Kevin
2003-03-13 | 60 | Documentation | SAD | Requirements Matrix - Schedules | Mike
2003-03-12 | 30 | Documentation | SAD (Data Model) | Updated the figure | Derrick
2003-03-12 | 40 | Meeting | Architecture & Design | Meeting to discuss the necessary changes to the SAD. | Kevin
2003-03-13 | 40 | Meeting | SAD | Team meeting | Mike
2003-03-14 | 140 | Other | Oracle | Restored the ability to connect to oracle | Derrick
2003-03-10 | 60 | Team Meeting | SAD | Discussed SAD | Jason
2003-03-12 | 30 | Team Meeting | SAD | Discussed SAD | Jason
2003-03-12 | 30 | Team Meeting | SAD | Discussed SAD | Jessica
2003-03-13 | 60 | Website |  | Added the 3/10 & 3/12 minutes, SRS, & updated schedule. | Jessica
Summary by Phase/Task
Coding | 935
Configuration | 290
Database | 240
Design | 380
Documentation | 600
Team Meeting | 200
Website | 60
Other | 140