## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-03-17 | 20 | Configuration | Oracle | Solicited assistance from a DBA | Derrick | Total Work Minutes for Week Ending On
2003-03-17 | 70 | Coding | Data Model | Experimentally discovered quirks of Oracle and adjusted SQL code accordingly | Derrick |  | 2003-03-15 | 2003-03-22 | 2003-03-29 | Total Time
2003-03-18 | 300 | Coding | Data Model | Most of the table structure is in place | Derrick | Kevin | 760 | 930 |  | 1690
2003-03-19 | 90 | Documentation | Data Model | Creating extra diagrams ( :-) ) | Derrick | Jason | 820 | 360 |  | 1180
2003-03-22 | 80 | Coding | Data Model | All of the tables are created and data is inserted into some of them | Derrick | Derrick | 200 | 615 |  | 815
2003-03-22 | 55 | Coding | "Batch Job" | Getting started :-) | Derrick | Jessica | 535 | 0 |  | 535
2003-03-19 | 60 | Documentation |  | Week 1 time log summary sheet | Jason | Mike | 620 | 220 |  | 840
2003-03-21 | 60 | Documentation |  | Week 1 time log summary sheet | Jason
2003-03-22 | 240 | Coding | Servlets | Worked on FindCustomerServlet | Jason
2003-03-17 | 115 | Coding | Servlets | Writing customer NPA-NXX-XXXX search | Kevin
2003-03-17 | 130 | Coding | EJBs | Adding E911Entity to abstract out functions | Kevin
2003-03-17 | 15 | Operations / Overhead |  | Emailing team members | Kevin
2003-03-17 | 20 | Documentation |  | Updating Arch figures, JSP interface document | Kevin
2003-03-19 | 40 | Operations / Overhead |  | Responding to Judy, emailing. | Kevin
2003-03-19 | 50 | Documentation |  | Fixing SAD and Domain Entities diagram | Kevin
2003-03-20 | 40 | Coding | Servlets | Fixing up Customer Search servlet | Kevin
2003-03-20 | 140 | Coding | JSPs | Finishing off MSAG search and Customer Search JSPs and starting debugging. | Kevin
2003-03-21 | 150 | Testing |  | Trying to get first JSP/Servlet/Bean to work together | Kevin
2003-03-22 | 230 | Coding | JSPs | Finishing findcustomer, wrote all of customerdataentry, mainmenu | Kevin
2003-03-20 | 20 | Updating | Website | Updated the SE version of the website with our current one | Mike
2003-03-20 | 200 | Config/Debug | Resin/EJB/JSP | Configuring resin and the ejb's and jsps and servlets to play nicely | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Summary by Package
2003-03-22 | 55 | Coding | "Batch Job" | Getting started :-) | Derrick |  | Actual Man/Days | Expected Man/Days | Minutes
2003-03-17 | 70 | Coding | Data Model | Experimentally discovered quirks of Oracle and adjusted SQL code accordingly | Derrick | Data Model | 2.375 | 4 | 570
2003-03-18 | 300 | Coding | Data Model | Most of the table structure is in place | Derrick | EJB's | 3 | 6 | 720
2003-03-22 | 80 | Coding | Data Model | All of the tables are created and data is inserted into some of them | Derrick | JSP's | 3.0208 | 8 | 725
2003-03-17 | 130 | Coding | EJBs | Adding E911Entity to abstract out functions | Kevin | Servlets | 4.0417 | 9 | 970
2003-03-20 | 140 | Coding | JSPs | Finishing off MSAG search and Customer Search JSPs and starting debugging. | Kevin | UI Testing | 0 | 7 | 0
2003-03-22 | 230 | Coding | JSPs | Finishing findcustomer, wrote all of customerdataentry, mainmenu | Kevin | C++ Code Conversion | 0 | 6 | 0
2003-03-22 | 240 | Coding | Servlets | Worked on FindCustomerServlet | Jason | Unit Testing | 0 | 6 | 0
2003-03-17 | 115 | Coding | Servlets | Writing customer NPA-NXX-XXXX search | Kevin | Normalization & Validation | 0 | 1 | 0
2003-03-20 | 40 | Coding | Servlets | Fixing up Customer Search servlet | Kevin | Stored Procedures | 0 | 2 | 0
2003-03-20 | 200 | Config/Debug | Resin/EJB/JSP | Configuring resin and the ejb's and jsps and servlets to play nicely | Mike | Triggers | 0 | 2 | 0
2003-03-17 | 20 | Configuration | Oracle | Solicited assistance from a DBA | Derrick | Data Creation | 0 | 2 | 0
2003-03-19 | 90 | Documentation | Data Model | Creating extra diagrams ( :-) ) | Derrick
2003-03-19 | 60 | Documentation |  | Week 1 time log summary sheet | Jason
2003-03-21 | 60 | Documentation |  | Week 1 time log summary sheet | Jason
2003-03-17 | 20 | Documentation |  | Updating Arch figures, JSP interface document | Kevin
2003-03-19 | 50 | Documentation |  | Fixing SAD and Domain Entities diagram | Kevin
2003-03-17 | 15 | Operations / Overhead |  | Emailing team members | Kevin
2003-03-19 | 40 | Operations / Overhead |  | Responding to Judy, emailing. | Kevin
2003-03-21 | 150 | Testing |  | Trying to get first JSP/Servlet/Bean to work together | Kevin
2003-03-20 | 20 | Updating | Website | Updated the SE version of the website with our current one | Mike
Summary by Phase/Task
Task | 2003-03-15 | 2003-03-22 | Total
Coding | 935 | 1400 | 2335
Configuration | 290 | 120 | 410
Database | 240 | 0 | 240
Debugging | 0 | 100 | 100
Design | 380 | 0 | 380
Documentation | 600 | 280 | 880
Operations | 0 | 55 | 55
Other | 140 | 0 | 140
Team Meeting | 200 | 0 | 200
Website | 60 | 20 | 80
Testing | 0 | 150 | 150