## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-03-25 | 200 | Coding | Triggers and Stored Procedures | Validation of MSAG data before entry in Locations | Derrick | Total Work Minutes for Week Ending On
2003-03-28 | 120 | Coding | Triggers and Stored Procedures | Learning how to debug functions | Derrick |  | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | Total Time
2003-03-29 | 180 | Coding | Triggers and Stored Procedures | Determined that NULL<>NULL! (and fixed the MSAG validation functions) | Derrick | Kevin | 760 | 930 | 1060 |  | 2750
2003-03-23 | 60 | Documentation |  | Week 2 time log summary sheet | Jason | Jason | 820 | 360 | 870 |  | 2050
2003-03-24 | 60 | Documentation |  | Week 2 time log summary sheet | Jason | Derrick | 200 | 615 | 500 |  | 1315
2003-03-24 | 150 | Coding | Servlets | Customer Data Entry Servlet | Jason | Jessica | 535 | 0 | 695 |  | 1230
2003-03-25 | 60 | Meeting |  | Team meeting | Jason | Mike | 620 | 220 | 980 |  | 1820
2003-03-26 | 60 | Documentation |  | Typing up meeting minutes | Jason
2003-03-27 | 120 | Coding | Servlets | Customer Data Entry Servlet | Jason
2003-03-28 | 60 | Coding | Servlets | Customer Data Entry Servlet | Jason
2003-03-29 | 180 | Coding | Servlets | Fixing code for exeption handling | Jason
2003-03-29 | 120 | Coding | Servlets | Started work on the Location Data Entry Servlet | Jason
2003-03-27 | 90 | Other | EJB's | Trying to get the MSAGHome to work. | Jessica
2003-03-27 | 45 | Coding | EJB's | Fixed the MSAGBean types. | Jessica
2003-03-27 | 30 | Coding | EJB's | Fixed the CustomerBean types. | Jessica
2003-03-27 | 30 | Coding | EJB's | Fixed the LocationBean types. | Jessica
2003-03-28 | 30 | Coding | EJB's | Fixed the TNBean types. | Jessica
2003-03-28 | 30 | Other | Javadoc | Added a javadoc target to the build file. | Jessica
2003-03-28 | 20 | Coding | EJB's | Fixed the UserBean types. | Jessica
2003-03-28 | 30 | Coding | EJB's | Wrote the CityMSAGBean. | Jessica
2003-03-28 | 30 | Other | Website | Updated the website with the latest minutes. | Jessica
2003-03-28 | 60 | Misc | EJB's | Verified that the interfaces match the implementation and wrote a few functions that had not been implemented in the Location and TN beans yet. | Jessica
2003-03-29 | 300 | Debugging | EJB's | Lots of debugging to make the MSAG search work. | Jessica
2003-03-24 | 90 | Documentation |  | Writing JSP/Servlet interface, tweaking SAD | Kevin
2003-03-24 | 50 | Coding | JSPs | Updating CustomerDataEntry and beginning to code LocationDataEntry | Kevin
2003-03-25 | 60 | Meeting |  | Meeting with Jon | Kevin
2003-03-25 | 30 | Coding | JSPs | Debugging | Kevin
2003-03-25 | 30 | Coding | Servlets | Debugging | Kevin
2003-03-26 | 40 | Documentation |  | Working on interfaces | Kevin
2003-03-27 | 180 | Debugging |  | Trying to straighten out JSPs and Servlets to work properly and fix Bean problem | Kevin
2003-03-28 | 60 | Coding | Servlets | Fixing compile problems | Kevin
2003-03-28 | 240 | Coding | JSPs | Debugging, writing location data entry | Kevin
2003-03-29 | 80 | Coding | EJBs | Debugging MSAG Bean | Kevin
2003-03-29 | 60 | Coding | JSPs | Debugging, making acct ID changes | Kevin
2003-03-29 | 140 | Debugging |  | Working on MSAG Search to get it all working together | Kevin
2003-03-25 | 120 | Configuration | EJB | Configuration of Resin | Mike
2003-03-25 | 20 | Updating | Website |  | Mike
2003-03-27 | 420 | Configuration | EJB | Configuration/Research for resin | Mike
2003-03-28 | 360 | Configuration | EJB | Configuration/Research for resin | Mike
2003-03-28 | 60 | Testing | EJB | Testing to ensure that it worked/minor debugging | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package
2003-03-25 | 200 | Coding | Triggers and Stored Procedures | Validation of MSAG data before entry in Locations | Derrick |  | Actual Man/Days | Expected Man/Days | Minutes
2003-03-28 | 120 | Coding | Triggers and Stored Procedures | Learning how to debug functions | Derrick | Data Model | 2.375 | 4 | 570
2003-03-29 | 180 | Coding | Triggers and Stored Procedures | Determined that NULL<>NULL! (and fixed the MSAG validation functions) | Derrick | EJB's | 9.9792 | 6 | 2395
2003-03-29 | 80 | Coding | EJBs | Debugging MSAG Bean | Kevin | JSP's | 4.6042 | 8 | 1105
2003-03-27 | 45 | Coding | EJB's | Fixed the MSAGBean types. | Jessica | Servlets | 7.0417 | 9 | 1690
2003-03-27 | 30 | Coding | EJB's | Fixed the CustomerBean types. | Jessica | UI Testing | 0 | 7 | 0
2003-03-27 | 30 | Coding | EJB's | Fixed the LocationBean types. | Jessica | C++ Code Conversion | 0 | 6 | 0
2003-03-28 | 30 | Coding | EJB's | Fixed the TNBean types. | Jessica | Unit Testing | 0 | 6 | 0
2003-03-28 | 20 | Coding | EJB's | Fixed the UserBean types. | Jessica | Normalization & Validation | 0 | 1 | 0
2003-03-28 | 30 | Coding | EJB's | Wrote the CityMSAGBean. | Jessica | Stored Procedures | 1.0417 | 2 | 250
2003-03-24 | 50 | Coding | JSPs | Updating CustomerDataEntry and beginning to code LocationDataEntry | Kevin | Triggers | 1.0417 | 2 | 250
2003-03-25 | 30 | Coding | JSPs | Debugging | Kevin | Data Creation | 0 | 2 | 0
2003-03-28 | 240 | Coding | JSPs | Debugging, writing location data entry | Kevin
2003-03-29 | 60 | Coding | JSPs | Debugging, making acct ID changes | Kevin
2003-03-24 | 150 | Coding | Servlets | Customer Data Entry Servlet | Jason | Summary by Phase/Task
2003-03-27 | 120 | Coding | Servlets | Customer Data Entry Servlet | Jason | Task | 2003-03-15 | 2003-03-22 | 2003-03-29 | Total
2003-03-28 | 60 | Coding | Servlets | Customer Data Entry Servlet | Jason | Coding | 935 | 1400 | 1865 | 4200
2003-03-29 | 180 | Coding | Servlets | Fixing code for exeption handling | Jason | Configuration | 290 | 120 | 900 | 1310
2003-03-29 | 120 | Coding | Servlets | Started work on the Location Data Entry Servlet | Jason | Database | 240 | 0 | 0 | 240
2003-03-25 | 30 | Coding | Servlets | Debugging | Kevin | Debugging | 0 | 100 | 320 | 420
2003-03-28 | 60 | Coding | Servlets | Fixing compile problems | Kevin | Design | 380 | 0 | 0 | 380
2003-03-25 | 120 | Configuration | EJB | Configuration of Resin | Mike | Documentation | 600 | 280 | 310 | 1190
2003-03-27 | 420 | Configuration | EJB | Configuration/Research for resin | Mike | Operations | 0 | 55 |  | 55
2003-03-28 | 360 | Configuration | EJB | Configuration/Research for resin | Mike | Other | 140 | 0 |  | 140
2003-03-29 | 300 | Debugging | EJB's | Lots of debugging to make the MSAG search work. | Jessica | Team Meeting | 200 | 0 |  | 200
2003-03-27 | 180 | Debugging |  | Trying to straighten out JSPs and Servlets to work properly and fix Bean problem | Kevin | Website | 60 | 20 |  | 80
2003-03-29 | 140 | Debugging |  | Working on MSAG Search to get it all working together | Kevin | Testing | 0 | 150 |  | 150
2003-03-23 | 60 | Documentation |  | Week 2 time log summary sheet | Jason
2003-03-24 | 60 | Documentation |  | Week 2 time log summary sheet | Jason
2003-03-26 | 60 | Documentation |  | Typing up meeting minutes | Jason
2003-03-24 | 90 | Documentation |  | Writing JSP/Servlet interface, tweaking SAD | Kevin
2003-03-26 | 40 | Documentation |  | Working on interfaces | Kevin
2003-03-25 | 60 | Meeting |  | Team meeting | Jason
2003-03-25 | 60 | Meeting |  | Meeting with Jon | Kevin
2003-03-28 | 60 | Misc | EJB's | Verified that the interfaces match the implementation and wrote a few functions that had not been implemented in the Location and TN beans yet. | Jessica
2003-03-27 | 90 | Other | EJB's | Trying to get the MSAGHome to work. | Jessica
2003-03-28 | 30 | Other | Javadoc | Added a javadoc target to the build file. | Jessica
2003-03-28 | 30 | Other | Website | Updated the website with the latest minutes. | Jessica
2003-03-28 | 60 | Testing | EJB | Testing to ensure that it worked/minor debugging | Mike
2003-03-25 | 20 | Updating | Website |  | Mike