## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-03-31 | 120 | Coding | C++ Code Conversion | String formatting, supporting beans framework | Derrick | Total Work Minutes for Week Ending On
2003-03-31 | 120 | Coding | C++ Code Conversion | Continuation | Derrick |  | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | Total Time | % of Total
2003-04-02 | 45 | Coding | C++ Code Conversion | Continuation | Derrick | Kevin | 760 | 930 | 1060 | 980 | 3730 | 28.09%
2003-04-03 | 45 | Documentation | Test Plan | Reading template, begging to fill it in | Derrick | Jason | 820 | 360 | 870 | 930 | 2980 | 22.44%
2003-04-03 | 10 | Coding | Data Model | s/NVARCHAR2/VARCHAR2/g | Derrick | Derrick | 200 | 615 | 500 | 550 | 1865 | 14.04%
2003-04-04 | 180 | Documentation | Test Plan | Setting up templates for test cases and reporting | Derrick | Jessica | 535 | 0 | 695 | 875 | 2105 | 15.85%
2003-04-04 | 30 | Coding | C++ Code Conversion | Supporting beans ... (should this be billed to beans or c++?) | Derrick | Mike | 620 | 220 | 980 | 780 | 2600 | 19.58%
2003-03-30 | 60 | Documentation |  | Weekly time log summary | Jason | [5 empty] | 13280
2003-03-31 | 120 | Coding | Servlets | MSAGSearchServlet and LocationDataEntry | Jason
2003-04-03 | 60 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-03 | 90 | Documentation |  | Meeting minutes and issue tracking | Jason
2003-04-04 | 270 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-05 | 30 | Documentation |  | Updating week 3 summaries based on new info | Jason
2003-04-05 | 300 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-03-31 | 150 | Development |  | Trying to get MSAG search fully functional and make two beans work at once. | Kevin
2003-04-02 | 15 | Coding | EJB's | Adding CustomerBean.findByAccountNumber function | Kevin
2003-04-02 | 245 | Coding | JSP's | Fixing bugs in FindCustomer.jsp and improving the DataTable.js object to handle hidden columns | Kevin
2003-04-03 | 40 | Coding | Servlets | Fixing acct Number vs Cust ID problems in CustomerDataEntryServlet | Kevin
2003-04-03 | 30 | Coding | EJB's | Fixing create functions in Customer, remove bugs | Kevin
2003-04-03 | 20 | Coding | JSP's | Tweaking findcustomer and locationdataentry | Kevin
2003-04-04 | 180 | Development |  | Fixing problems, organizational issues | Kevin
2003-04-05 | 110 | Coding | EJB's | Creating ComboBuilder bean | Kevin
2003-04-05 | 110 | Coding | JSP's | Using auto combo boxes, adding activeOnly and fixing bugs | Kevin
2003-04-05 | 80 | Coding | Servlets | Adding activeOnly handling to customer search servlet | Kevin
2003-03-31 | 20 | Coding | Servlets | Wrote the community search. | Jessica
2003-03-31 | 105 | Other |  | Trying to get Resin to work on my machine :( | Jessica
2003-04-02 | 60 | Testing | EJB's/Servlets | Got the community names search working :) | Jessica
2003-04-02 | 90 | Testing | EJB's/Servlets | Got the find customer page up! :) | Jessica
2003-04-03 | 60 | Coding | EJB's | Worked on making a singleton for the connection object. | Jessica
2003-04-04 | 30 | Other | Website | Updated the website. | Jessica
2003-04-04 | 120 | Testing | EJB's | Worked on the connectionmanager | Jessica
2003-04-04 | 90 | Coding | EJB's | Worked on the CustomerBean. | Jessica
2003-04-05 | 300 | Testing | EJB's | CustomerBean again :( | Jessica
2003-03-31 | 120 | Other |  | Experimenting with some ejb / servlet / jsp stuff | Mike
2003-04-01 | 60 | Other | Misc | poking around and playin with stuff | Mike
2003-04-03 | 30 | Coding | Servlets | misc code stuff and magic | Mike
2003-04-04 | 270 | Coding | Servlets | writing code | Mike
2003-04-05 | 300 | Coding | Servlets | hand waving (and some code) and someother misc maintenance | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 4/5/2003
2003-03-31 | 120 | Coding | C++ Code Conversion | String formatting, supporting beans framework | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-03-31 | 120 | Coding | C++ Code Conversion | Continuation | Derrick | Data Model | 580 | 2.4167 | 4 | 3 | 80.56% | Weeks Completed | 4
2003-04-02 | 45 | Coding | C++ Code Conversion | Continuation | Derrick | EJB's | 2700 | 11.25 | 6 | 16 | 70.31% | Average Actual Man-Days/Week | 10.0052
2003-04-04 | 30 | Coding | C++ Code Conversion | Supporting beans ... (should this be billed to beans or c++?) | Derrick | JSP's | 1480 | 6.1667 | 8 | 11 | 56.06%
2003-04-03 | 10 | Coding | Data Model | s/NVARCHAR2/VARCHAR2/g | Derrick | Servlets | 3180 | 13.25 | 9 | 22 | 60.23% | Total Weeks Avail. | 10
2003-04-02 | 15 | Coding | EJB's | Adding CustomerBean.findByAccountNumber function | Kevin | UI Testing | 0 | 0 | 7 | 7 | 0% | % Weeks Passed | 40%
2003-04-03 | 30 | Coding | EJB's | Fixing create functions in Customer, remove bugs | Kevin | C++ Conv. | 370 | 1.5417 | 6 | 6 | 25.69% | % Estimated Man/Days Spent | 49.41%
2003-04-05 | 110 | Coding | EJB's | Creating ComboBuilder bean | Kevin | Unit Testing | 795 | 3.3125 | 6 | 10 | 33.12%
2003-04-03 | 60 | Coding | EJB's | Worked on making a singleton for the connection object. | Jessica | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 8.0958
2003-04-04 | 90 | Coding | EJB's | Worked on the CustomerBean. | Jessica | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-04 | 120 | Testing | EJB's | Worked on the connectionmanager | Jessica | Triggers | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-05 | 300 | Testing | EJB's | CustomerBean again :( | Jessica | Data Creation | 0 | 0 | 2 | 2 | 0%
2003-04-02 | 60 | Testing | EJB's/Servlets | Got the community names search working :) | Jessica | Total | 9605 | 40.0208 | 53 | 81 | 49.41% | Proj. Slack Man/Days at Current Rate of Work | 19.0521
2003-04-02 | 90 | Testing | EJB's/Servlets | Got the find customer page up! :) | Jessica | % Expended to Date |  |  | 75.51% | 49.41%
2003-04-02 | 245 | Coding | JSP's | Fixing bugs in FindCustomer.jsp and improving the DataTable.js object to handle hidden columns | Kevin
2003-04-03 | 20 | Coding | JSP's | Tweaking findcustomer and locationdataentry | Kevin
2003-04-05 | 110 | Coding | JSP's | Using auto combo boxes, adding activeOnly and fixing bugs | Kevin
2003-04-01 | 60 | Other | Misc | poking around and playin with stuff | Mike
2003-03-31 | 120 | Coding | Servlets | MSAGSearchServlet and LocationDataEntry | Jason
2003-04-03 | 60 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-04 | 270 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-05 | 300 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-03 | 40 | Coding | Servlets | Fixing acct Number vs Cust ID problems in CustomerDataEntryServlet | Kevin
2003-04-05 | 80 | Coding | Servlets | Adding activeOnly handling to customer search servlet | Kevin
2003-03-31 | 20 | Coding | Servlets | Wrote the community search. | Jessica
2003-04-03 | 30 | Coding | Servlets | misc code stuff and magic | Mike
2003-04-04 | 270 | Coding | Servlets | writing code | Mike
2003-04-05 | 300 | Coding | Servlets | hand waving (and some code) and someother misc maintenance | Mike
2003-04-03 | 45 | Documentation | Test Plan | Reading template, begging to fill it in | Derrick
2003-04-04 | 180 | Documentation | Test Plan | Setting up templates for test cases and reporting | Derrick
2003-04-04 | 30 | Other | Website | Updated the website. | Jessica
2003-03-31 | 150 | Development |  | Trying to get MSAG search fully functional and make two beans work at once. | Kevin
2003-04-04 | 180 | Development |  | Fixing problems, organizational issues | Kevin
2003-03-30 | 60 | Documentation |  | Weekly time log summary | Jason
2003-04-03 | 90 | Documentation |  | Meeting minutes and issue tracking | Jason
2003-04-05 | 30 | Documentation |  | Updating week 3 summaries based on new info | Jason
2003-03-31 | 105 | Other |  | Trying to get Resin to work on my machine :( | Jessica
2003-03-31 | 120 | Other |  | Experimenting with some ejb / servlet / jsp stuff | Mike