## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-04-07 | 120 | Documentation | Test Plan | Test Plan | Derrick | Total Work Minutes for Week Ending On
2003-04-08 | 240 | Documentation | Test Plan | Test Plan | Derrick |  | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | 2003-04-12 | Total Time | % of Total
2003-04-09 | 10 | Coding | Data Model | Fixed a table and column name (fixed column name in docs as well) | Derrick | Kevin | 760 | 930 | 1060 | 980 | 1260 | 4990 | 27.58%
2003-04-10 | 30 | Coding | Triggers | Changed the semantics of an assignment | Derrick | Jason | 820 | 360 | 870 | 930 | 810 | 3790 | 20.95%
2003-04-11 | 160 | Documentation | Test Plan | Test Plan | Derrick | Derrick | 200 | 615 | 500 | 550 | 940 | 2805 | 15.51%
2003-04-11 | 40 | Testing | Data Model | Tracing some “phantom” problems | Derrick | Jessica | 535 | 0 | 695 | 875 | 1110 | 3215 | 17.77%
2003-04-11 | 40 | Configuration | Resin | HTTP AUTH | Derrick | Mike | 620 | 220 | 980 | 780 | 690 | 3290 | 18.19%
2003-04-12 | 300 | Coding | C++ Code Conversion | Converting more file generators, rudimentary testing, and coercing ant into using the correct classpath when compiling and running | Derrick | [6 empty] | 18090
2003-04-07 | 60 | Documentation |  | Time log summary | Jason
2003-04-09 | 160 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-09 | 30 | Coding | EJB's | Fixed create on Location and Home | Jason
2003-04-10 | 150 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-11 | 150 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-12 | 240 | Coding | Servlets | LocationDataEntry and CustomerDataEntry | Jason
2003-04-12 | 20 | Coding | EJB's | TNHome and TNBean | Jason
2003-04-07 | 150 | Coding | JSP's | Fixing bugs on find customer page. Finishing the combo box builder class. | Kevin
2003-04-07 | 40 | Planning |  | Analyzing weekly summary and calculating project progress | Kevin
2003-04-09 | 190 | Coding | JSP's | debugging find customer and customer data entry | Kevin
2003-04-10 | 210 | Coding | JSP's | Working on dynamic contect for location data entry | Kevin
2003-04-11 | 115 | Coding | JSP's | Working on functions for client-side scripting in locationdataentry.jsp | Kevin
2003-04-11 | 45 | Documentation |  | Reviewing and modifying test plan with Derrick | Kevin
2003-04-11 | 200 | Integration |  | Finding bugs and trying out different aspects of the system. Helping other problem-solve their issues. | Kevin
2003-04-12 | 210 | Testing | UI Testing | Integration and debugging | Kevin
2003-04-12 | 100 | Coding | JSP's | Remembering search values and trying some things for batching | Kevin
2003-04-08 | 210 | Coding | EJB's | Trying to fix CustomerBean and findByCompanyName stuff. | Jessica
2003-04-09 | 100 | Coding | EJB's/Servlets | Fixing up all the beans & some bugs in the servlets. | Jessica
2003-04-09 | 260 | Integration |  | Trying to get the add customer stuff to work. | Jessica
2003-04-10 | 210 | Integration |  | Working on addcustomer etc. | Jessica
2003-04-11 | 330 | Integration |  | Working on the msag searches | Jessica
2003-04-08 | 90 | Other |  | Preparing JBOSS for use as a test platform | Mike
2003-04-10 | 120 | Other |  | misc maintenance | Mike
2003-04-11 | 300 | Other |  | Research/Configuration of resin for authentication and some other stuff | Mike
2003-04-12 | 180 | Coding | Servlets | Coding user servlets | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 4/12/2003
2003-04-12 | 300 | Coding | C++ Code Conversion | Converting more file generators, rudimentary testing, and coercing ant into using the correct classpath when compiling and running | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-04-09 | 10 | Coding | Data Model | Fixed a table and column name (fixed column name in docs as well) | Derrick | Data Model | 630 | 2.625 | 4 | 3 | 87.5% | Weeks Completed | 5
2003-04-11 | 40 | Testing | Data Model | Tracing some “phantom” problems | Derrick | EJB's | 3010 | 12.5417 | 6 | 16 | 78.39% | Average Actual Man-Days/Week | 10.7958
2003-04-09 | 30 | Coding | EJB's | Fixed create on Location and Home | Jason | JSP's | 1480 | 6.1667 | 8 | 11 | 56.06%
2003-04-12 | 20 | Coding | EJB's | TNHome and TNBean | Jason | Servlets | 4110 | 17.125 | 9 | 22 | 77.84% | Total Weeks Avail. | 10
2003-04-08 | 210 | Coding | EJB's | Trying to fix CustomerBean and findByCompanyName stuff. | Jessica | UI Testing | 210 | 0.875 | 7 | 7 | 12.5% | % Weeks Passed | 50%
2003-04-09 | 100 | Coding | EJB's/Servlets | Fixing up all the beans & some bugs in the servlets. | Jessica | C++ Conv. | 670 | 2.7917 | 6 | 6 | 46.53% | % Estimated Man/Days Spent | 60.65%
2003-04-07 | 150 | Coding | JSP's | Fixing bugs on find customer page. Finishing the combo box builder class. | Kevin | Unit Testing | 1315 | 5.4792 | 6 | 10 | 54.79%
2003-04-09 | 190 | Coding | JSP's | debugging find customer and customer data entry | Kevin | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 8.2439
2003-04-10 | 210 | Coding | JSP's | Working on dynamic contect for location data entry | Kevin | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-11 | 115 | Coding | JSP's | Working on functions for client-side scripting in locationdataentry.jsp | Kevin | Triggers | 280 | 1.1667 | 2 | 2 | 58.33%
2003-04-12 | 100 | Coding | JSP's | Remembering search values and trying some things for batching | Kevin | Data Creation | 0 | 0 | 2 | 2 | 0%
2003-04-11 | 40 | Configuration | Resin | HTTP AUTH | Derrick | Integration | 1000 | 4.1667 | 0 | 8 | 52.08% | Proj. Slack Man/Days at Current Rate of Work | 18.9583
2003-04-09 | 160 | Coding | Servlets | LocationDataEntryServlet | Jason | Total | 12955 | 53.9792 | 53 | 89 | 60.65%
2003-04-10 | 150 | Coding | Servlets | LocationDataEntryServlet | Jason | % Expended to Date |  |  | 101.8% | 60.65%
2003-04-11 | 150 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-12 | 240 | Coding | Servlets | LocationDataEntry and CustomerDataEntry | Jason
2003-04-12 | 180 | Coding | Servlets | Coding user servlets | Mike
2003-04-07 | 120 | Documentation | Test Plan | Test Plan | Derrick
2003-04-08 | 240 | Documentation | Test Plan | Test Plan | Derrick
2003-04-11 | 160 | Documentation | Test Plan | Test Plan | Derrick
2003-04-10 | 30 | Coding | Triggers | Changed the semantics of an assignment | Derrick
2003-04-12 | 210 | Testing | UI Testing | Integration and debugging | Kevin
2003-04-07 | 60 | Documentation |  | Time log summary | Jason
2003-04-11 | 45 | Documentation |  | Reviewing and modifying test plan with Derrick | Kevin
2003-04-11 | 200 | Integration |  | Finding bugs and trying out different aspects of the system. Helping other problem-solve their issues. | Kevin
2003-04-09 | 260 | Integration |  | Trying to get the add customer stuff to work. | Jessica
2003-04-10 | 210 | Integration |  | Working on addcustomer etc. | Jessica
2003-04-11 | 330 | Integration |  | Working on the msag searches | Jessica
2003-04-08 | 90 | Other |  | Preparing JBOSS for use as a test platform | Mike
2003-04-10 | 120 | Other |  | misc maintenance | Mike
2003-04-11 | 300 | Other |  | Research/Configuration of resin for authentication and some other stuff | Mike
2003-04-07 | 40 | Planning |  | Analyzing weekly summary and calculating project progress | Kevin