## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-04-17 | 150 | Coding | C++ Code Conversion | More conversion stuff (stricter format checking) | Derrick | Total Work Minutes for Week Ending On
2003-04-18 | 60 | Coding | C++ Code Conversion | Converted more generator(s) | Derrick |  | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | 2003-04-12 | 2003-04-19 | Total Time | % of Total
2003-04-19 | 180 | Coding | C++ Code Conversion and Bean Stuff | Converted final generators. Deployed generator bean and working on accessing remotely | Derrick | Kevin | 760 | 930 | 1060 | 980 | 1260 | 1050 | 6040 | 26.92%
2003-04-13 | 60 | Documentation |  | Time log summary | Jason | Jason | 820 | 360 | 870 | 930 | 810 | 1050 | 4840 | 21.57%
2003-04-14 | 30 | Coding | Servlets | LocationDataEntryServlet | Jason | Derrick | 200 | 615 | 500 | 550 | 940 | 390 | 3195 | 14.24%
2003-04-14 | 60 | Documentation |  | Checking time log summaries for mistakes | Jason | Jessica | 535 | 0 | 695 | 875 | 1110 | 1020 | 4235 | 18.87%
2003-04-15 | 60 | Team Meeting |  |  | Jason | Mike | 620 | 220 | 980 | 780 | 690 | 840 | 4130 | 18.4%
2003-04-16 | 240 | IAB Presentation |  | Created initial presentation | Jason | [7 empty] | 22440
2003-04-17 | 120 | IAB Presentation |  | Added to presentation | Jason
2003-04-17 | 30 | Documentation |  | Typing meeting minutes and doing issue tracking | Jason
2003-04-17 | 30 | IAB Presentation |  | Reviewed presentation with Kevin | Jason
2003-04-17 | 180 | IAB Presentation |  | Reviewed presentation with Patnawon | Jason
2003-04-18 | 60 | IAB Presentation |  | The actual presentation | Jason
2003-04-18 | 180 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-14 | 90 | Integration |  |  | Jessica
2003-04-15 | 60 | Meeting |  |  | Jessica
2003-04-16 | 180 | Testing |  | Trying to fix up the test case model. | Jessica
2003-04-16 | 120 | IAB |  | Presentation. | Jessica
2003-04-17 | 120 | Testing |  | Figured out the macros and made some test cases. | Jessica
2003-04-17 | 30 | IAB |  | Fixed up the presentation. | Jessica
2003-04-18 | 120 | IAB |  | Presentation. | Jessica
2003-04-19 | 60 | Documentation |  | Test Cases | Jessica
2003-04-19 | 240 | Coding/Debugging | EJB's | got the batching fixed | Jessica
2003-04-13 | 60 | Integration |  | Fixing deploy on main server | Kevin
2003-04-14 | 120 | Integration |  | Making editing of location data entry work | Kevin
2003-04-14 | 30 | Design |  | Figuring out how to handle batching with Mike | Kevin
2003-04-16 | 100 | Documentation | Test Plan | Finishing test plan | Kevin
2003-04-16 | 150 | Coding | JSP's | Upgrading DataTable to allow manual batching, and implementing batching in MSAG search. | Kevin
2003-04-17 | 60 | Coding | JSP's | Fixing missed parts of batching | Kevin
2003-04-17 | 60 | Coding | Servlets | Debugging LocationDataEntryServlet | Kevin
2003-04-17 | 170 | Coding | Integration | Getting location data entry creation and editing to work | Kevin
2003-04-18 | 60 | Coding | JSP's | Getting batching to work on MSAG search | Kevin
2003-04-18 | 240 | Integration |  | Various batching work and problem solving | Kevin
2003-04-14 | 120 | Coding | Servlet | Batching | Mike
2003-04-15 | 180 | Coding | Servlet |  | Mike
2003-04-17 | 120 | Coding | ejb |  | Mike
2003-04-18 | 150 | Coding | ejb | Batching | Mike
2003-04-18 | 150 | Coding | Servlet | Batching | Mike
2003-04-19 | 120 | Coding | Servlet | user stuff | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 4/26/2003
2003-04-17 | 150 | Coding | C++ Code Conversion | More conversion stuff (stricter format checking) | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-04-18 | 60 | Coding | C++ Code Conversion | Converted more generator(s) | Derrick | Data Model | 630 | 2.625 | 4 | 3 | 87.5% | Weeks Completed | 6
2003-04-19 | 180 | Coding | C++ Code Conversion and Bean Stuff | Converted final generators. Deployed generator bean and working on accessing remotely | Derrick | EJB's | 3520 | 14.6667 | 6 | 16 | 91.67% | Average Actual Man-Days/Week | 11.1424
2003-04-17 | 120 | Coding | ejb |  | Mike | JSP's | 1750 | 7.2917 | 8 | 11 | 66.29%
2003-04-18 | 150 | Coding | ejb | Batching | Mike | Servlets | 4950 | 20.625 | 9 | 22 | 93.75% | Total Weeks Avail. | 10
2003-04-19 | 240 | Coding/Debugging | EJB's | got the batching fixed | Jessica | UI Testing | 210 | 0.875 | 7 | 7 | 12.5% | % Weeks Passed | 60%
2003-04-17 | 170 | Coding | Integration | Getting location data entry creation and editing to work | Kevin | C++ Conv. | 1060 | 4.4167 | 6 | 6 | 73.61% | % Estimated Man/Days Spent | 68.92%
2003-04-16 | 150 | Coding | JSP's | Upgrading DataTable to allow manual batching, and implementing batching in MSAG search. | Kevin | Unit Testing | 1715 | 7.1458 | 6 | 10 | 71.46%
2003-04-17 | 60 | Coding | JSP's | Fixing missed parts of batching | Kevin | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 8.7055
2003-04-18 | 60 | Coding | JSP's | Getting batching to work on MSAG search | Kevin | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-14 | 120 | Coding | Servlet | Batching | Mike | Triggers | 280 | 1.1667 | 2 | 2 | 58.33%
2003-04-15 | 180 | Coding | Servlet |  | Mike | Data Creation | 0 | 0 | 2 | 2 | 0%
2003-04-18 | 150 | Coding | Servlet | Batching | Mike | Integration | 1680 | 7 | 0 | 16 | 43.75% | Proj. Slack Man/Days at Current Rate of Work | 14.4236
2003-04-19 | 120 | Coding | Servlet | user stuff | Mike | Total | 16045 | 66.8542 | 53 | 97 | 68.92%
2003-04-14 | 30 | Coding | Servlets | LocationDataEntryServlet | Jason | % Expended to Date |  |  | 126.1% | 68.92%
2003-04-18 | 180 | Coding | Servlets | LocationDataEntryServlet | Jason
2003-04-17 | 60 | Coding | Servlets | Debugging LocationDataEntryServlet | Kevin
2003-04-16 | 100 | Documentation | Test Plan | Finishing test plan | Kevin
2003-04-14 | 30 | Design |  | Figuring out how to handle batching with Mike | Kevin
2003-04-13 | 60 | Documentation |  | Time log summary | Jason
2003-04-14 | 60 | Documentation |  | Checking time log summaries for mistakes | Jason
2003-04-17 | 30 | Documentation |  | Typing meeting minutes and doing issue tracking | Jason
2003-04-19 | 60 | Documentation |  | Test Cases | Jessica
2003-04-16 | 120 | IAB |  | Presentation. | Jessica
2003-04-17 | 30 | IAB |  | Fixed up the presentation. | Jessica
2003-04-18 | 120 | IAB |  | Presentation. | Jessica
2003-04-16 | 240 | IAB Presentation |  | Created initial presentation | Jason
2003-04-17 | 120 | IAB Presentation |  | Added to presentation | Jason
2003-04-17 | 30 | IAB Presentation |  | Reviewed presentation with Kevin | Jason
2003-04-17 | 180 | IAB Presentation |  | Reviewed presentation with Patnawon | Jason
2003-04-18 | 60 | IAB Presentation |  | The actual presentation | Jason
2003-04-14 | 90 | Integration |  |  | Jessica
2003-04-13 | 60 | Integration |  | Fixing deploy on main server | Kevin
2003-04-14 | 120 | Integration |  | Making editing of location data entry work | Kevin
2003-04-18 | 240 | Integration |  | Various batching work and problem solving | Kevin
2003-04-15 | 60 | Meeting |  |  | Jessica
2003-04-15 | 60 | Team Meeting |  |  | Jason
2003-04-16 | 180 | Testing |  | Trying to fix up the test case model. | Jessica
2003-04-17 | 120 | Testing |  | Figured out the macros and made some test cases. | Jessica