## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-04-21 | 90 | Coding | EJBs | Finally managed to get the SetGenerator up and ready for continued development. It compiles and deploys correctly and can be found by the batch job. | Derrick | Total Work Minutes for Week Ending On
2003-04-22 | 210 | Coding | C++ Code Conversion, Triggers | Rearranged batch job (no more beans, not entirely necessary and resin is too slow) and tried debugging the Location trigger. | Derrick | Name | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | 2003-04-12 | 2003-04-19 | 2003-04-26 | 2003-05-03 | Total Time | % of Total
2003-04-23 | 120 | Coding | C++ Code Conversion | Some refactoring of java. Arguing with Oracle and JDBC about SQL queries. | Derrick | Kevin | 760 | 930 | 1060 | 980 | 1260 | 1050 | 1050 |  | 7090 | 26.42%
2003-04-24 | 60 | Coding | C++ Code Conversion | Pull the entire record from the database. Now we have real record generation! | Derrick | Jason | 820 | 360 | 870 | 930 | 810 | 1050 | 660 |  | 5500 | 20.5%
2003-04-25 | 60 | Documentation | Test Plan | Incorporated changes suggested by Judy | Derrick | Derrick | 200 | 615 | 500 | 550 | 940 | 390 | 540 |  | 3735 | 13.92%
2003-04-21 | 60 | Documentation |  | Time log summaries | Jason | Jessica | 535 | 0 | 695 | 875 | 1110 | 1020 | 1005 |  | 5240 | 19.53%
2003-04-21 | 180 | Coding | Servlets | ChangePasswordServlet | Jason | Mike | 620 | 220 | 980 | 780 | 690 | 840 | 1140 |  | 5270 | 19.64%
2003-04-24 | 60 | Documentation |  | Verifying Time Log Summary information | Jason | Totals | 2935 | 2125 | 4105 | 4115 | 4810 | 4350 | 4395 |  | 26835
2003-04-25 | 300 | Coding | Servlets | CustomerDataEntryServlet | Jason
2003-04-26 | 60 | Documentation |  | Time log summaries | Jason
2003-04-20 | 30 | Coding | EJB | Added batching to the CityMSAGBean | Jessica
2003-04-20 | 30 | Integration |  | Tested batching for citymsag | Jessica
2003-04-20 | 30 | Coding | EJB | Added batching to the CustomerBean | Jessica
2003-04-20 | 30 | Coding | Servlet | Added batching to the findcustomerservlet | Jessica
2003-04-20 | 120 | Integration |  | Tested batching for customers | Jessica
2003-04-20 | 60 | Coding | Servlet | Trying to fix locationdataentry | Jessica
2003-04-20 | 30 | Coding | EJB | Fixed TNBean | Jessica
2003-04-20 | 120 | Integration |  | Can now add phone numbers to a customer | Jessica
2003-04-21 | 45 | Coding | EJB | Fixed TNBean | Jessica
2003-04-23 | 240 | Documentation | Test Cases | Generating test cases :( | Jessica
2003-04-26 | 30 | Other | Website | Updated the minutes. | Jessica
2003-04-26 | 60 | Other |  | Getting everything up on my home machine… | Jessica
2003-04-26 | 180 | Other | Research | Researching design changes. | Jessica
2003-04-20 | 60 | Coding | JSPs | Fixing bugs, adding batching to customer search page | Kevin
2003-04-20 | 60 | Integration |  | Helping Jess track down bugs | Kevin
2003-04-21 | 60 | Coding | JSPs | Fix some data checking bugs in Location page | Kevin
2003-04-21 | 60 | Planning |  | Create new issue and bug tracking excel sheet | Kevin
2003-04-21 | 120 | Integration |  | Debugging handling of MSAG matching | Kevin
2003-04-22 | 90 | Integration |  | Debugging handling of MSAG matching | Kevin
2003-04-23 | 240 | Integration |  | Added authorization, fixing problems w/ changing locations. | Kevin
2003-04-24 | 120 | Integration |  | Fixing problems with Location data entry | Kevin
2003-04-25 | 240 | Integration |  | Debugging location submission of new and edited TNs. | Kevin
2003-04-21 | 120 | Coding | EJB | adjusting a bean and testing it | Mike
2003-04-22 | 120 | Coding | Servlet | Admin stuff for e911 | Mike
2003-04-23 | 180 | Coding | Servlet | Admin stuff for e911 | Mike
2003-04-24 | 300 | Coding | EJB/Servlet/JSP | About 1/3 this time for each… | Mike
2003-04-25 | 150 | Coding | JSP | Password stuff | Mike
2003-04-26 | 150 | Coding | Servlet | you get the idea | Mike
2003-04-26 | 120 | Integration |  | yep, that’s it | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 4/26/2003
2003-04-23 | 120 | Coding | C++ Code Conversion | Some refactoring of java. Arguing with Oracle and JDBC about SQL queries. | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-04-24 | 60 | Coding | C++ Code Conversion | Pull the entire record from the database. Now we have real record generation! | Derrick | Data Model | 740 | 3.0833 | 4 | 3 | 102.8% | Weeks Completed | 7
2003-04-22 | 210 | Coding | C++ Code Conversion, Triggers | Rearranged batch job (no more beans, not entirely necessary and resin is too slow) and tried debugging the Location trigger. | Derrick | EJB's | 2600 | 10.8333 | 6 | 16 | 67.71% | Average Actual Man-Days/Week | 11.7054
2003-04-20 | 30 | Coding | EJB | Added batching to the CityMSAGBean | Jessica | JSP's | 2580 | 10.75 | 8 | 12 | 89.58%
2003-04-20 | 30 | Coding | EJB | Added batching to the CustomerBean | Jessica | Servlets | 5715 | 23.8125 | 9 | 30 | 79.38% | Total Weeks Avail. | 10
2003-04-20 | 30 | Coding | EJB | Fixed TNBean | Jessica | UI Testing | 840 | 3.5 | 7 | 7 | 50% | % Weeks Passed | 70%
2003-04-21 | 45 | Coding | EJB | Fixed TNBean | Jessica | C++ Conv. | 1450 | 6.0417 | 6 | 9 | 67.13% | % Estimated Man/Days Spent | 69.44%
2003-04-21 | 120 | Coding | EJB | adjusting a bean and testing it | Mike | Unit Testing | 490 | 2.0417 | 6 | 10 | 20.42%
2003-04-24 | 300 | Coding | EJB/Servlet/JSP | About 1/3 this time for each… | Mike | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 10.0809
2003-04-21 | 90 | Coding | EJBs | Finally managed to get the SetGenerator up and ready for continued development. It compiles and deploys correctly and can be found by the batch job. | Derrick | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-25 | 150 | Coding | JSP | Password stuff | Mike | Triggers | 280 | 1.1667 | 2 | 2 | 58.33%
2003-04-20 | 60 | Coding | JSPs | Fixing bugs, adding batching to customer search page | Kevin | Data Creation | 0 | 0 | 2 | 2 | 0%
2003-04-21 | 60 | Coding | JSPs | Fix some data checking bugs in Location page | Kevin | Application Configuration | 1150 | 4.7917 | 0 | 5 | 95.83% | Proj. Slack Man/Days at Current Rate of Work | -0.94643
2003-04-26 | 180 | Other | Research | Researching design changes. | Jessica | Integration | 3570 | 14.875 | 0 | 20 | 74.38%
2003-04-20 | 30 | Coding | Servlet | Added batching to the findcustomerservlet | Jessica | Total | 19665 | 81.9375 | 53 | 118 | 69.44%
2003-04-20 | 60 | Coding | Servlet | Trying to fix locationdataentry | Jessica | % Expended to Date |  |  | 154.6% | 69.44%
2003-04-22 | 120 | Coding | Servlet | Admin stuff for e911 | Mike | Other | 6400 | 26.6667
2003-04-23 | 180 | Coding | Servlet | Admin stuff for e911 | Mike
2003-04-26 | 150 | Coding | Servlet | you get the idea | Mike
2003-04-21 | 180 | Coding | Servlets | ChangePasswordServlet | Jason
2003-04-25 | 300 | Coding | Servlets | CustomerDataEntryServlet | Jason
2003-04-23 | 240 | Documentation | Test Cases | Generating test cases :( | Jessica
2003-04-25 | 60 | Documentation | Test Plan | Incorporated changes suggested by Judy | Derrick
2003-04-26 | 30 | Other | Website | Updated the minutes. | Jessica
2003-04-21 | 60 | Documentation |  | Time log summaries | Jason
2003-04-24 | 60 | Documentation |  | Verifying Time Log Summary information | Jason
2003-04-26 | 60 | Documentation |  | Time log summaries | Jason
2003-04-20 | 30 | Integration |  | Tested batching for citymsag | Jessica
2003-04-20 | 120 | Integration |  | Tested batching for customers | Jessica
2003-04-20 | 120 | Integration |  | Can now add phone numbers to a customer | Jessica
2003-04-20 | 60 | Integration |  | Helping Jess track down bugs | Kevin
2003-04-21 | 120 | Integration |  | Debugging handling of MSAG matching | Kevin
2003-04-22 | 90 | Integration |  | Debugging handling of MSAG matching | Kevin
2003-04-23 | 240 | Integration |  | Added authorization, fixing problems w/ changing locations. | Kevin
2003-04-24 | 120 | Integration |  | Fixing problems with Location data entry | Kevin
2003-04-25 | 240 | Integration |  | Debugging location submission of new and edited TNs. | Kevin
2003-04-26 | 120 | Integration |  | yep, that’s it | Mike
2003-04-26 | 60 | Other |  | Getting everything up on my home machine… | Jessica
2003-04-21 | 60 | Planning |  | Create new issue and bug tracking excel sheet | Kevin