## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-04-27 | 165 | Coding | Triggers | Automatically adjust the TN status as appropriate | Derrick | Total Work Minutes for Week Ending On
2003-04-27 | 165 | Testing | Data Creation | Convert Jon's test data to the new data model for testing the batch job | Derrick | Name | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | 2003-04-12 | 2003-04-19 | 2003-04-26 | 2003-05-03 | Total Time | % of Total
2003-04-28 | 180 | Coding | Triggers | Worked around what appears to be an oracle defect in get_msag_id. Retested TNs_IU_B trigger and it seems to work now. | Derrick | Kevin | 760 | 930 | 1060 | 980 | 1260 | 1050 | 1050 | 2590 | 9680 | 25.92%
2003-04-29 | 60 | Team Meeting |  | Weekly meeting at 0800 | Derrick | Jason | 820 | 360 | 870 | 930 | 810 | 1050 | 660 | 2175 | 7675 | 20.55%
2003-04-29 | 90 | Misc | Test Plan, Database | Updated test plan with new feedback. Created new db instance for demo purposes. | Derrick | Derrick | 200 | 615 | 500 | 550 | 940 | 390 | 540 | 960 | 4695 | 12.57%
2003-05-02 | 120 | Coding | C++ Code Conversion | Working on infrastructure to test this | Derrick | Jessica | 535 | 0 | 695 | 875 | 1110 | 1020 | 1005 | 2810 | 8050 | 21.55%
2003-05-05 | 180 | Coding | C++ Code Conversion | Tested all generators on all markets. They work, apart from a handful of minor issues to ask Jon about | Derrick | Mike | 620 | 220 | 980 | 780 | 690 | 840 | 1140 | 1980 | 7250 | 19.41%
2003-04-27 | 150 | Documentation |  | Time log summary | Jason | Totals | 2935 | 2125 | 4105 | 4115 | 4810 | 4350 | 4395 | 10515 | 37350
2003-04-28 | 180 | Coding | Servlets | Removing sendError function and adding calls to ServletErrorHandler class | Jason
2003-04-28 | 180 | Documentation | Test Cases | Started creating test cases for Locaiton Data Entry | Jason
2003-04-29 | 60 | Team Meeting |  |  | Jason
2003-04-29 | 90 | Documentation |  | Issue tracking and meeting minutes | Jason
2003-04-29 | 60 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-04-30 | 120 | Documentation |  | Project planning | Jason
2003-04-30 | 60 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-04-30 | 75 | Meeting |  | Poster workshop | Jason
2003-04-30 | 150 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-05-01 | 60 | Documentation |  | Project planning | Jason
2003-05-01 | 270 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-05-02 | 360 | Documentation | Test Cases | Location Data Entry, CustomerDataEntry, Find Customer | Jason
2003-05-03 | 300 | Documentation | Test Cases | Find Customer | Jason
2003-05-03 | 60 | Documentation |  | Time log summary | Jason
2003-04-27 | 120 | Other | Research | More research :-p | Jessica
2003-04-27 | 120 | Coding | EJB's/Servlets | Split time in half for each :) Created the CityMSAGServicesBean and updated the servlet. | Jessica
2003-04-27 | 210 | Integration |  | Got the session stuff working. | Jessica
2003-04-27 | 60 | Other | Research | Researching session implementation. | Jessica
2003-04-27 | 120 | Coding | EJB's/Servlets | Split time in half for each :) Created the MSAGServicesBean and updated the servlet. | Jessica
2003-04-28 | 45 | Coding | Servlets | Reupdated the MSAGSearchServlet :( | Jessica
2003-04-28 | 120 | Coding | EJB's | Created CustomerServicesBean | Jessica
2003-04-28 | 120 | Coding | Servlets | Fixed the servlets that were using CustomerEntity | Jessica
2003-04-28 | 210 | Integration |  | Got the customer session working. | Jessica
2003-04-29 | 60 | Other | Meeting | Team meeting | Jessica
2003-04-29 | 45 | Coding | EJB | Created LocationServicesBean | Jessica
2003-04-29 | 45 | Coding | Servlets | Updated servlets to use locationservicesbean | Jessica
2003-04-29 | 60 | Coding | Integration | Trying to get LocationServices working | Jessica
2003-04-29 | 45 | Coding | EJB | Created TNServicesBean | Jessica
2003-04-29 | 45 | Coding | Servlets | Updated servlets to use tnservicesbean | Jessica
2003-04-29 | 120 | Coding | Integration | Got TNServices mostly working. | Jessica
2003-04-30 | 60 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-04-30 | 30 | Planning | Gantt Chart | Brainstormed gantt chart with Jay. | Jessica
2003-04-30 | 120 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-04-30 | 75 | Other | Meeting | Poster Workshop | Jessica
2003-04-30 | 60 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-04-30 | 60 | Other | Research | Researching ways to fix the servlets. | Jessica
2003-05-01 | 60 | Other | Research | Researching ways to fix the servlets. | Jessica
2003-05-01 | 30 | Coding | Servlets | Rearranged the msagsearchservlet | Jessica
2003-05-01 | 20 | Other | Website | Added the minutes to the website. | Jessica
2003-05-01 | 90 | Coding | Servlets | Rearranged the customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed nulls in customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed the rest of the servlets | Jessica
2003-05-02 | 60 | Coding | Integration | Figured out why msag wasn't working | Jessica
2003-05-02 | 120 | Other | Research | Researching connection stuff and other random things.. Sorry its not more explicit :) | Jessica
2003-05-02 | 390 | Other | Test Data | Generated a sql script for test data. | Jessica
2003-04-27 | 240 | Coding | Integration | Adding sorts to queries, and find customer. Various other fixes and changes. | Kevin
2003-04-28 | 60 | Coding | Servlets | Fixing problem with order of customer search results. | Kevin
2003-04-28 | 60 | Coding | JSPs | Cleaning up user pages. | Kevin
2003-04-28 | 90 | Coding | Servlets | Helping debug servlet changes because of new beans | Kevin
2003-04-28 | 270 | Coding | EJBs | Making details objects, helping debug new ejbs | Kevin
2003-04-28 | 90 | Coding | Integration |  | Kevin
2003-04-28 | 60 | Meeting |  | Meeting with Jon & Judy | Kevin
2003-04-29 | 160 | Coding | Servlets | Cleaning up servlets, separating doGet and doPost methods | Kevin
2003-04-29 | 30 | Coding | Servlets | Finish fixing up find customer servlet | Kevin
2003-04-29 | 30 | Coding | JSPs | Fix some bugs from the changes to using bean Details objects in location data entry | Kevin
2003-04-30 | 20 | Coding | JSPs | Fix bug w/ linking of TN on serach results | Kevin
2003-04-30 | 60 | Coding | Servlets | Finish adding env.close() | Kevin
2003-04-30 | 90 | Meeting | Poster Workshop | Poster Workshop | Kevin
2003-04-30 | 60 | Coding | Servlets | Fix bugs and clean up | Kevin
2003-04-30 | 60 | Coding | Integration | Fix bugs | Kevin
2003-05-01 | 40 | Design |  | Evaluating methods of cleaning up servlets and return statements | Kevin
2003-05-01 | 210 | Coding | Servlets | Cleaned up and re-wrote location data entry servlet | Kevin
2003-05-01 | 60 | Coding | Servlets | Cleaned up and re-wrote location data entry servlet | Kevin
2003-05-02 | 60 | Coding | JSPs | Make msag link open new window, fix error page bugs | Kevin
2003-05-02 | 360 | Coding | Integration | Transaction work, batching of updates in location data entry, bug fixes. | Kevin
2003-05-03 | 150 | Coding | Servlets | Fixing bug w/ submitting two location pages at once because of global collections. | Kevin
2003-05-03 | 40 | Coding | JSPs | Write code for useraccount page | Kevin
2003-05-03 | 130 | Coding | Servlets | Clean up and debug | Kevin
2003-05-03 | 130 | Documentation | Test Cases | Non functional and add'l msag cases | Kevin
2003-05-03 | 30 | Documentation | Test Cases | Non functional | Kevin
2003-04-28 | 450 | coding | integration | Coding/Tweaking/Re-coding of UserBean (and new Session bean) | Mike
2003-04-29 | 120 | coding | integration | all | Mike
2003-04-30 | 60 | Coding | EJB | user | Mike
2003-04-30 | 60 | Coding | JSP | stuff | Mike
2003-04-30 | 30 | coding | Servlet | all | Mike
2003-05-02 | 200 | coding | JSP | the | Mike
2003-05-02 | 20 | Coding | Servlet | time | Mike
2003-05-02 | 200 | coding | ejb | and | Mike
2003-05-02 | 420 | coding | integration | some other stuff | Mike
2003-05-03 | 420 | coding | integration | you get the idea | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 5/3/2003
2003-05-02 | 120 | Coding | C++ Code Conversion | Working on infrastructure to test this | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-05-05 | 180 | Coding | C++ Code Conversion | Tested all generators on all markets. They work, apart from a handful of minor issues to ask Jon about | Derrick | Data Model | 740 | 3.0833 | 4 | 3 | 102.8% | Weeks Completed | 8
2003-04-29 | 45 | Coding | EJB | Created LocationServicesBean | Jessica | EJB's | 3340 | 13.9167 | 6 | 16 | 86.98% | Average Actual Man-Days/Week | 13.4948
2003-04-29 | 45 | Coding | EJB | Created TNServicesBean | Jessica | JSP's | 3050 | 12.7083 | 8 | 13 | 97.76%
2003-04-30 | 60 | Coding | EJB | user | Mike | Servlets | 7465 | 31.1042 | 9 | 33 | 94.26% | Total Weeks Avail. | 10
2003-04-28 | 270 | Coding | EJBs | Making details objects, helping debug new EJB'ss | Kevin | UI Testing | 840 | 3.5 | 7 | 7 | 50% | % Weeks Passed | 80%
2003-05-02 | 200 | Coding | EJB's | and | Mike | C++ Conv. | 1750 | 7.2917 | 6 | 9 | 81.02% | % Estimated Man/Days Spent | 84.34%
2003-04-28 | 120 | Coding | EJB's | Created CustomerServicesBean | Jessica | Unit Testing | 490 | 2.0417 | 6 | 10 | 20.42%
2003-04-27 | 120 | Coding | EJB's/Servlets | Split time in half for each :) Created the CityMSAGServicesBean and updated the servlet. | Jessica | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 9.4851
2003-04-27 | 120 | Coding | EJB's/Servlets | Split time in half for each :) Created the MSAGServicesBean and updated the servlet. | Jessica | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-04-29 | 60 | Coding | Integration | Trying to get LocationServices working | Jessica | Triggers | 460 | 1.9167 | 2 | 2 | 95.83%
2003-04-29 | 120 | Coding | Integration | Got TNServices mostly working. | Jessica | Data Creation | 165 | 0.6875 | 2 | 2 | 34.38%
2003-05-02 | 60 | Coding | Integration | Figured out why msag wasn't working | Jessica | Application Configuration | 1150 | 4.7917 | 0 | 5 | 95.83% | Proj. Slack Man/Days at Current Rate of Work | 6.9479
2003-04-27 | 240 | Coding | Integration | Adding sorts to queries, and find customer. Various other fixes and changes. | Kevin | Integration | 6210 | 25.875 | 0 | 26 | 99.52%
2003-04-28 | 90 | Coding | Integration |  | Kevin | Total | 25910 | 107.9583 | 53 | 128 | 84.34%
2003-04-30 | 60 | Coding | Integration | Fix bugs | Kevin | % Expended to Date |  |  | 203.7% | 84.34%
2003-05-02 | 360 | Coding | Integration | Transaction work, batching of updates in location data entry, bug fixes. | Kevin | Other | 10550 | 43.9583
2003-04-28 | 450 | Coding | integration | Coding/Tweaking/Re-Coding of UserBean (and new Session bean) | Mike
2003-04-29 | 120 | Coding | integration | all | Mike
2003-05-02 | 420 | Coding | integration | some other stuff | Mike
2003-05-03 | 420 | coding | integration | you get the idea | Mike
2003-04-30 | 60 | Coding | JSP | stuff | Mike
2003-05-02 | 200 | Coding | JSP | the | Mike
2003-04-28 | 60 | Coding | JSPs | Cleaning up user pages. | Kevin
2003-04-29 | 30 | Coding | JSPs | Fix some bugs from the changes to using bean Details objects in location data entry | Kevin
2003-04-30 | 20 | Coding | JSPs | Fix bug w/ linking of TN on serach results | Kevin
2003-05-02 | 60 | Coding | JSPs | Make msag link open new window, fix error page bugs | Kevin
2003-05-03 | 40 | Coding | JSPs | Write code for useraccount page | Kevin
2003-04-30 | 30 | Coding | Servlet | all | Mike
2003-05-02 | 20 | Coding | Servlet | time | Mike
2003-04-28 | 180 | Coding | Servlets | Removing sendError function and adding calls to ServletErrorHandler class | Jason
2003-04-28 | 45 | Coding | Servlets | Reupdated the MSAGSearchServlet :( | Jessica
2003-04-28 | 120 | Coding | Servlets | Fixed the servlets that were using CustomerEntity | Jessica
2003-04-29 | 45 | Coding | Servlets | Updated servlets to use locationservicesbean | Jessica
2003-04-29 | 45 | Coding | Servlets | Updated servlets to use tnservicesbean | Jessica
2003-05-01 | 30 | Coding | Servlets | Rearranged the msagsearchservlet | Jessica
2003-05-01 | 90 | Coding | Servlets | Rearranged the customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed nulls in customerdataentry servlet | Jessica
2003-05-02 | 30 | Coding | Servlets | Fixed the rest of the servlets | Jessica
2003-04-28 | 60 | Coding | Servlets | Fixing problem with order of customer search results. | Kevin
2003-04-28 | 90 | Coding | Servlets | Helping debug servlet changes because of new beans | Kevin
2003-04-29 | 160 | Coding | Servlets | Cleaning up servlets, separating doGet and doPost methods | Kevin
2003-04-29 | 30 | Coding | Servlets | Finish fixing up find customer servlet | Kevin
2003-04-30 | 60 | Coding | Servlets | Finish adding env.close() | Kevin
2003-04-30 | 60 | Coding | Servlets | Fix bugs and clean up | Kevin
2003-05-01 | 210 | Coding | Servlets | Cleaned up and re-wrote location data entry servlet | Kevin
2003-05-01 | 60 | Coding | Servlets | Cleaned up and re-wrote location data entry servlet | Kevin
2003-05-03 | 150 | Coding | Servlets | Fixing bug w/ submitting two location pages at once because of global collections. | Kevin
2003-05-03 | 130 | Coding | Servlets | Clean up and debug | Kevin
2003-04-27 | 165 | Coding | Triggers | Automatically adjust the TN status as appropriate | Derrick
2003-04-28 | 180 | Coding | Triggers | Worked around what appears to be an oracle defect in get_msag_id. Retested TNs_IU_B trigger and it seems to work now. | Derrick
2003-05-01 | 40 | Design |  | Evaluating methods of cleaning up servlets and return statements | Kevin
2003-04-28 | 180 | Documentation | Test Cases | Started creating test cases for Locaiton Data Entry | Jason
2003-04-29 | 60 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-04-30 | 60 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-04-30 | 150 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-05-01 | 270 | Documentation | Test Cases | Locaton Data Entry | Jason
2003-05-02 | 360 | Documentation | Test Cases | Location Data Entry, CustomerDataEntry, Find Customer | Jason
2003-05-03 | 300 | Documentation | Test Cases | Find Customer | Jason
2003-04-30 | 60 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-04-30 | 120 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-04-30 | 60 | Documentation | Test Cases | Wrote a few test cases. | Jessica
2003-05-03 | 130 | Documentation | Test Cases | Non functional and add'l msag cases | Kevin
2003-05-03 | 30 | Documentation | Test Cases | Non functional | Kevin
2003-04-27 | 150 | Documentation |  | Time log summary | Jason
2003-04-29 | 90 | Documentation |  | Issue tracking and meeting minutes | Jason
2003-04-30 | 120 | Documentation |  | Project planning | Jason
2003-05-01 | 60 | Documentation |  | Project planning | Jason
2003-05-03 | 60 | Documentation |  | Time log summary | Jason
2003-04-27 | 210 | Integration |  | Got the session stuff working. | Jessica
2003-04-28 | 210 | Integration |  | Got the customer session working. | Jessica
2003-04-30 | 90 | Meeting | Poster Workshop | Poster Workshop | Kevin
2003-04-30 | 75 | Meeting |  | Poster workshop | Jason
2003-04-28 | 60 | Meeting |  | Meeting with Jon & Judy | Kevin
2003-04-29 | 90 | Misc | Test Plan, Database | Updated test plan with new feedback. Created new db instance for demo purposes. | Derrick
2003-04-29 | 60 | Other | Meeting | Team meeting | Jessica
2003-04-30 | 75 | Other | Meeting | Poster Workshop | Jessica
2003-04-27 | 120 | Other | Research | More research :-p | Jessica
2003-04-27 | 60 | Other | Research | Researching session implementation. | Jessica
2003-04-30 | 60 | Other | Research | Researching ways to fix the servlets. | Jessica
2003-05-01 | 60 | Other | Research | Researching ways to fix the servlets. | Jessica
2003-05-02 | 120 | Other | Research | Researching connection stuff and other random things.. Sorry its not more explicit :) | Jessica
2003-05-02 | 390 | Other | Test Data | Generated a sql script for test data. | Jessica
2003-05-01 | 20 | Other | Website | Added the minutes to the website. | Jessica
2003-04-30 | 30 | Planning | Gantt Chart | Brainstormed gantt chart with Jay. | Jessica
2003-04-29 | 60 | Team Meeting |  | Weekly meeting at 0800 | Derrick
2003-04-29 | 60 | Team Meeting |  |  | Jason
2003-04-27 | 165 | Testing | Data Creation | Convert Jon's test data to the new data model for testing the batch job | Derrick