## By Name
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person
2003-05-05 | 195 | Documentation | Test Cases | Writing Test Cases | Kevin | Total Work Minutes for Week Ending On
2003-05-05 | 80 | Coding | Servlets | Clean up user stuff error handling | Kevin | Name | 2003-03-15 | 2003-03-22 | 2003-03-29 | 2003-04-05 | 2003-04-12 | 2003-04-19 | 2003-04-26 | 2003-05-03 | 2003-05-10 | Total Time | % of Total
2003-05-05 | 10 | Coding | JSPs | Fix bug | Kevin | Kevin | 760 | 930 | 1060 | 980 | 1260 | 1050 | 1050 | 2590 | 1965 | 11645 | 25.43%
2003-05-05 | 35 | UI Testing | MSAG | running test cases | Kevin | Jason | 820 | 360 | 870 | 930 | 810 | 1050 | 660 | 2175 | 1830 | 9505 | 20.76%
2003-05-06 | 60 | Meeting |  | Team meeting w/ Jon and Judy | Kevin | Derrick | 200 | 615 | 500 | 550 | 940 | 390 | 540 | 960 | 1560 | 6255 | 13.66%
2003-05-06 | 60 | Coding | JSPs | Add extra links for navigation, remove Logout | Kevin | Jessica | 535 | 0 | 695 | 875 | 1110 | 1020 | 1005 | 2810 | 1385 | 9435 | 20.6%
2003-05-07 | 165 | Documentation | Javadoc | Commenting code | Kevin | Mike | 620 | 220 | 980 | 780 | 690 | 840 | 1140 | 1980 | 1700 | 8950 | 19.55%
2003-05-07 | 180 | Coding | Integration | Bug fixes,etc. | Kevin | Totals | 2935 | 2125 | 4105 | 4115 | 4810 | 4350 | 4395 | 10515 | 8440 | 45790
2003-05-08 | 100 | Coding | JSPs | Fixing user related stuff, adding client-side scripting to it, cleaning up appearance. | Kevin
2003-05-08 | 60 | UI Testing | MSAG | running test cases | Kevin
2003-05-08 | 50 | Coding | EJBs | Fix bugs with rownum ordering | Kevin
2003-05-09 | 80 | Documentation |  |  | Kevin
2003-05-09 | 120 | UI Testing |  | run test cases | Kevin
2003-05-09 | 300 | Coding | Integration | Bug fixes,etc. | Kevin
2003-05-10 | 220 | Coding | Integration | Bug fixes,etc. | Kevin
2003-05-10 | 180 | UI Testing |  | running test cases | Kevin
2003-05-10 | 70 | Documentation |  | poster | Kevin
2003-05-04 | 60 | Documentation |  | Time Log Summaries | Jason
2003-05-04 | 60 | Documentation | Test Cases | User Accounts | Jason
2003-05-05 | 60 | Documentation | Test Cases | User Accounts | Jason
2003-05-05 | 270 | Documentation | Test Cases | Location Data Entry, Customer Data Entry, Data Dictionary | Jason
2003-05-05 | 30 | Other |  | Meeting preperation. | Jason
2003-05-06 | 60 | Team Meeting |  |  | Jason
2003-05-06 | 30 | Documentation |  | Updating Time Log Summaries | Jason
2003-05-06 | 30 | Documentation |  | Typing up meeting minutes and adding to issue tracking | Jason
2003-05-07 | 30 | Other |  | Setting up my machiene for ant and resin | Jason
2003-05-07 | 90 | Testing | UI Testing | Location Data Entry Find Customer | Jason
2003-05-07 | 120 | Documentation |  | Poster Presentation | Jason
2003-05-08 | 180 | Documentation |  | Poster Presentation | Jason
2003-05-09 | 180 | Documentation |  | Poster Presentation | Jason
2003-05-09 | 210 | Testing | UI Testing |  | Jason
2003-05-09 | 120 | Documentation |  | User Documentation | Jason
2003-05-10 | 60 | Documentation |  | User Documentation | Jason
2003-05-10 | 180 | Documentation |  | User Documentation | Jason
2003-05-10 | 30 | Documentation |  | Test Summary | Jason
2003-05-10 | 30 | Team Meeting |  | Went over layout of poster | Jason
2003-05-04 | 210 | Documentation | Test Cases | Formally typed test cases for 5xx requirements. | Derrick
2003-05-05 | 60 | Coding | C++ Code Conversion | Minor tweaks and recording open issues. | Derrick
2003-05-05 | 60 | Coding | Resin | Encrypted passwords. Simply plug the code into the app! | Derrick
2003-05-06 | 60 | Meeting |  | Meeting | Derrick
2003-05-06 | 90 | Coding | Triggers | Fixing TN uniqueness check | Derrick
2003-05-06 | 180 | Research / Coding | Resin | Cookie. Why!? Also fixed a bug in LocationBean | Derrick
2003-05-08 | 180 | Coding | Triggers / Resin | Check uniqueness of Locations. Pounded on resin issues =p. | Derrick
2003-05-09 | 180 | Coding | Triggers, Resin, etc. | Discovered problem with TN status when updating location. Encrypting passwords. | Derrick
2003-05-10 | 540 | Debugging/Coding | System | Figuring out problems with resin, the app, the database | Derrick
2003-05-05 | 180 | Testing | MSAG | Ran some MSAG tests. | Jessica
2003-05-06 | 60 | Other | Meeting | Team meeting | Jessica
2003-05-07 | 45 | Other | Website | Added minutes and test cases to the website. | Jessica
2003-05-07 | 240 | Documentation |  | javadoc | Jessica
2003-05-07 | 90 | Coding | Integration | Fixing bugs. | Jessica
2003-05-09 | 20 | Coding | Integration | Tested a fix. | Jessica
2003-05-09 | 360 | Testing |  | test test test! | Jessica
2003-05-10 | 330 | Other | javadoc | javadoc | Jessica
2003-05-10 | 60 | Testing |  | checked to see what is left to test | Jessica
2003-05-04 | 300 | Testing | All |  | Mike
2003-05-05 | 240 | Debugging | Servlet |  | Mike
2003-05-06 | 120 | Debugging | Integration :) |  | Mike
2003-05-08 | 120 | Debugging | Integration :) |  | Mike
2003-05-09 | 220 | Debugging | Integration :) |  | Mike
2003-05-09 | 280 | Testing | Integration :) |  | Mike
2003-05-10 | 300 | Testing | Integration :) |  | Mike
2003-05-10 | 120 | Documentation | ZAAAAA | Working on test docs | Mike

## By Package
Date | Time Spent (minutes) | Phase / Task | Package | Description | Person | Man/Days by Package as of 5/3/2003
2003-05-05 | 60 | Coding | C++ Code Conversion | Minor tweaks and recording open issues. | Derrick |  | Actual Minutes to Date | Actual Man/Days to Date | Original Expected Man/Days | New Expected Man/Days | % of Expected Used to Date | Summary
2003-05-08 | 50 | Coding | EJBs | Fix bugs with rownum ordering | Kevin | Data Model | 740 | 3.0833 | 4 | 3 | 102.8% | Weeks Completed | 9
2003-05-07 | 180 | Coding | Integration | Bug fixes,etc. | Kevin | EJB's | 3390 | 14.125 | 6 | 16 | 88.28% | Average Actual Man-Days/Week | 14.2199
2003-05-09 | 300 | Coding | Integration | Bug fixes,etc. | Kevin | JSP's | 3220 | 13.4167 | 8 | 14 | 95.83%
2003-05-10 | 220 | Coding | Integration | Bug fixes,etc. | Kevin | Servlets | 7705 | 32.1042 | 9 | 33 | 97.29% | Total Weeks Avail. | 10
2003-05-07 | 90 | Coding | Integration | Fixing bugs. | Jessica | UI Testing | 1535 | 6.3958 | 7 | 7 | 91.37% | % Weeks Passed | 90%
2003-05-09 | 20 | Coding | Integration | Tested a fix. | Jessica | C++ Conv. | 1810 | 7.5417 | 6 | 9 | 83.8% | % Estimated Man/Days Spent | 93.42%
2003-05-05 | 10 | Coding | JSPs | Fix bug | Kevin | Unit Testing | 2090 | 8.7083 | 6 | 10 | 87.08%
2003-05-06 | 60 | Coding | JSPs | Add extra links for navigation, remove Logout | Kevin | Norm. & Valid. | 0 | 0 | 1 | 0 | 0% | Projected Completion Week based on Current Work Rate and Est. Time Requirements | 9.6344
2003-05-08 | 100 | Coding | JSPs | Fixing user related stuff, adding client-side scripting to it, cleaning up appearance. | Kevin | Stored Proc. | 250 | 1.0417 | 2 | 2 | 52.08%
2003-05-05 | 60 | Coding | Resin | Encrypted passwords. Simply plug the code into the app! | Derrick | Triggers | 760 | 3.1667 | 2 | 3 | 105.6%
2003-05-05 | 80 | Coding | Servlets | Clean up user stuff error handling | Kevin | Data Creation | 165 | 0.6875 | 2 | 2 | 34.38%
2003-05-06 | 90 | Coding | Triggers | Fixing TN uniqueness check | Derrick | Application Configuration | 1150 | 4.7917 | 0 | 5 | 95.83% | Proj. Slack Man/Days at Current Rate of Work | 5.1991
2003-05-08 | 180 | Coding | Triggers / Resin | Check uniqueness of Locations. Pounded on resin issues =p. | Derrick | Integration | 7900 | 32.9167 | 0 | 33 | 99.75%
2003-05-09 | 180 | Coding | Triggers, Resin, etc. | Discovered problem with TN status when updating location. Encrypting passwords. | Derrick | Total | 30715 | 127.9792 | 53 | 137 | 93.42%
2003-05-06 | 120 | Debugging | Integration :) |  | Mike | % Expended to Date |  |  | 241.5% | 93.42%
2003-05-08 | 120 | Debugging | Integration :) |  | Mike | Other | 13955 | 58.1458
2003-05-09 | 220 | Debugging | Integration :) |  | Mike
2003-05-05 | 240 | Debugging | Servlet |  | Mike
2003-05-10 | 360 | Debugging/Coding | System | Figuring out problems with resin, the app, the database | Derrick
2003-05-07 | 165 | Documentation | Javadoc | Commenting code | Kevin
2003-05-05 | 195 | Documentation | Test Cases | Writing Test Cases | Kevin
2003-05-04 | 60 | Documentation | Test Cases | User Accounts | Jason
2003-05-05 | 60 | Documentation | Test Cases | User Accounts | Jason
2003-05-05 | 270 | Documentation | Test Cases | Location Data Entry, Customer Data Entry, Data Dictionary | Jason
2003-05-04 | 210 | Documentation | Test Cases | Formally typed test cases for 5xx requirements. | Derrick
2003-05-10 | 120 | Documentation | ZAAAAA | Working on test docs | Mike
2003-05-09 | 80 | Documentation |  |  | Kevin
2003-05-10 | 70 | Documentation |  | poster | Kevin
2003-05-04 | 60 | Documentation |  | Time Log Summaries | Jason
2003-05-06 | 30 | Documentation |  | Updating Time Log Summaries | Jason
2003-05-06 | 30 | Documentation |  | Typing up meeting minutes and adding to issue tracking | Jason
2003-05-07 | 120 | Documentation |  | Poster Presentation | Jason
2003-05-08 | 180 | Documentation |  | Poster Presentation | Jason
2003-05-09 | 180 | Documentation |  | Poster Presentation | Jason
2003-05-09 | 120 | Documentation |  | User Documentation | Jason
2003-05-10 | 60 | Documentation |  | User Documentation | Jason
2003-05-10 | 180 | Documentation |  | User Documentation | Jason
2003-05-10 | 30 | Documentation |  | Test Summary | Jason
2003-05-07 | 240 | Documentation |  | javadoc | Jessica
2003-05-06 | 60 | Meeting |  | Team meeting w/ Jon and Judy | Kevin
2003-05-06 | 60 | Meeting |  | Meeting | Derrick
2003-05-10 | 330 | Other | javadoc | javadoc | Jessica
2003-05-06 | 60 | Other | Meeting | Team meeting | Jessica
2003-05-07 | 45 | Other | Website | Added minutes and test cases to the website. | Jessica
2003-05-05 | 30 | Other |  | Meeting preperation. | Jason
2003-05-07 | 30 | Other |  | Setting up my machiene for ant and resin | Jason
2003-05-06 | 180 | Research / Coding | Resin | Cookie. Why!? Also fixed a bug in LocationBean | Derrick
2003-05-06 | 60 | Team Meeting |  |  | Jason
2003-05-10 | 30 | Team Meeting |  | Went over layout of poster | Jason
2003-05-04 | 300 | Testing | All |  | Mike
2003-05-09 | 280 | Testing | Integration :) |  | Mike
2003-05-10 | 300 | Testing | Integration :) |  | Mike
2003-05-05 | 180 | Testing | MSAG | Ran some MSAG tests. | Jessica
2003-05-07 | 90 | Testing | UI Testing | Location Data Entry Find Customer | Jason
2003-05-09 | 210 | Testing | UI Testing |  | Jason
2003-05-09 | 360 | Testing |  | test test test! | Jessica
2003-05-10 | 60 | Testing |  | checked to see what is left to test | Jessica
2003-05-05 | 35 | UI Testing | MSAG | running test cases | Kevin
2003-05-08 | 60 | UI Testing | MSAG | running test cases | Kevin
2003-05-09 | 120 | UI Testing |  | run test cases | Kevin
2003-05-10 | 180 | UI Testing |  | running test cases | Kevin
2003-05-10 | 60 | Team Meeting |  | Poster | Derrick
2003-05-10 | 120 | Testing | System |  | Derrick