## December
Sprint Month |  |  |  | December
Sprint Theme |  |  |  | Elicitation & Planning
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | % Complete | Estimated Hours Remaining | Comments
1 | Project Synopsis Document
|  | Create |  | Joe | 2008-12-05 | 2008-12-31 | 0 | 1 | 100% | 0 | Did not estimate because it was done in the first week of class.
2 | Project Planning |  |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31
2.1 |  | Week 1 |  | Brian | 2007-12-03 | 2007-12-09 | 0 | 0.5 | 100% | 0 | Did not estimate because it was done in the first week of class.
2.2 |  | Week 2 |  | Brian, Joe | 2007-12-10 | 2007-12-16 | 1.75 | 1.5 | 100% | 0 | Joe overestimated a little.
2.3 |  | Week 3 |  | Brian, Rob, Joe, Mark | 2007-12-17 | 2007-12-23 | 8 | 11.25 | 100% | 0 | Everyone pitched in to make sure that this document was well thought out and had enough in it before Xmas break started.
3 | Requirements Elicitation |  |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31
3.1 |  | client phone meetings |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31 | 12 | 12 | 100% | 0 | Estimated at 1.5 per week for 4 weeks
|  | client emails |  | Rob | 2007-12-05 | 2007-12-31 | 6 | 8 | 100% | 0 | About 2 hours per week estimated
4 | Project Website
|  | Create |  | Mark | 2008-12-05 | 2008-12-31 | 3 | 4 | 100% | 0 | Mark overestimated by 1 hour.
5 | Report Time Effort |  |  | Brian, Rob, Joe, Mark | 2007-12-03 | 2007-12-31
5.1 |  | Week 1 |  | Brian, Rob, Joe, Mark | 2007-12-03 | 2007-12-09 | 0 | 1 | 100% | 0 | Did not estimate because it was done in the first week of class.
5.2 |  | Week 2 |  | Brian, Rob, Joe, Mark | 2007-12-10 | 2007-12-16 | 1 | 1 | 100% | 0 | Estimate correct
5.3 |  | Week 3 |  | Brian, Rob, Joe, Mark | 2007-12-17 | 2007-12-23 | 1 | 1 | 100% | 0 | Estimate correct
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
| N/A |  |  | None! | N/A

## January
Sprint Month |  |  |  | January
Sprint Theme |  |  |  | Requirements & Throwaway Prototyping
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | % Complete | Estimated Hours Remaining | Comments
1 | Requirements |  |  | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-02-04
1.1 |  | Elicitation |  | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-02-04
1.11 |  |  | client phone meetings | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-01-31 | 12 | 12 | 100% | 0 | 12
1.2 |  | Baseline SRS Document |  | Brian, Rob, Joe | 2008-01-01 | 2008-02-05
1.21 |  |  | Week 4 | Brian, Rob | 2008-01-07 | 2008-01-13 | 2 | 6.5 | 100% | 0 | Brian estimated only, Rob worked on as well.
1.22 |  |  | Week 5 | Brian, Rob | 2008-01-14 | 2008-01-20 | 6 | 4.5 | 100% | 0 | Brian estimated, but Rob worked on only.
1.23 |  |  | Week 6 | Brian, Rob | 2008-01-21 | 2008-01-27 | 6 | 12 | 100% | 0 | Spent much more time on SRS due to client feedback
1.24 |  |  | Week 7 | Brian, Rob, Joe | 2008-01-28 | 2008-02-03 | 15 | 10 | 90% | 1.5 | Everyone started working on because we needed more, FAST!
1.3 |  | UI Prototypes |  | Joe, Mark | 2008-01-01 | 2008-01-31
1.31 |  |  | Week 4 | Joe, Mark | 2008-01-07 | 2008-01-13 | 0 | 3 | 100% | 0 | Did not plan on working on visualizations, but did due to free time and/or personal interest in the subject
1.32 |  |  | Week 5 | Joe, Mark | 2008-01-14 | 2008-01-20 | 12 | 10.5 | 100% | 0
1.33 |  |  | Week 6 | Joe, Mark | 2008-01-21 | 2008-01-27 | 9.5 | 7.75 | 100% | 0
1.34 |  |  | Week 7 | Joe, Mark | 2008-01-28 | 2008-02-03 | 2 | 3 | 100% | 0 | Joe did not estimate time, but assisted Mark anyways.
2 | Coding |  |  | Joe | 2008-01-01 | 2008-01-31
2.1 |  | XML [Un]Marshalling Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 10 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/28/2008. Get better values from Joe.
2.2 |  | Drag & Drop Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 2.5 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/26/2008. Get better values from Joe.
2.3 |  | GDI+ Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 0 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/26/2008. Get better values from Joe.
3 | Project Planning |  |  | Brian | 2008-01-01 | 2008-01-31
3.1 |  | Project Plan Document |  | Brian | 2008-01-01 | 2008-01-31
3.11 |  |  | Week 4 | Brian | 2008-01-07 | 2008-01-13 | 0 | 0 | 100% | 0 | Was not planned to be worked on and was not worked on. Requirements started and took most of our time.
3.12 |  |  | Week 5 | Brian | 2008-01-14 | 2008-01-20 | 0 | 0 | 100% | 0 | Was not planned to be worked on and was not worked on. Requirements started and took most of our time.
3.13 |  |  | Week 6 | Brian | 2008-01-21 | 2008-01-27 | 2 | 0 | 100% | 0 | Interview out of town interfered with working on project plan.
3.14 |  |  | Week 7 | Brian | 2008-01-28 | 2008-02-03 | 2 | 2 | 100% | 0
3.2 |  | Risk Management Document |  | Brian | 2008-01-01 | 2008-01-31
3.21 |  |  | Week 4 | Brian | 2008-01-07 | 2008-01-13 | 0 | 0 | 100% | 0
3.22 |  |  | Week 5 | Brian | 2008-01-14 | 2008-01-20 | 0 | 0 | 100% | 0
3.23 |  |  | Week 6 | Brian | 2008-01-21 | 2008-01-27 | 0 | 0 | 100% | 0
3.24 |  |  | Week 7 | Brian | 2008-01-28 | 2008-02-03 | 0 | 4 | 100% | 0 | Moved from project planning document to its own document and beautified.
4 | Req's Negotiation - Part 1
4.1 |  | Negotiate |  | Brian, Joe, Mark, Rob | 2008-01-17 | 2008-01-17 | 1 | 1 | 100% | 0 | The client visited Rochester and we negotiated some requirements with first draft of SRS, in person.
5 | Metrics |  |  | Mark | 2008-01-01 | 2008-01-31 |  |  |  |  | We forgot about metrics until we did a couple revisions of the schedule and worked on the project plan again!!
5.1 |  | Take Measurements |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.2 |  | Create Metrics |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.3 |  | Update Website |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.4 |  | Take Measurements |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
5.5 |  | Create Metrics |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
5.6 |  | Update Website |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
| N/A |  |  | None! | N/A

## February
Sprint Month |  |  |  | February
Sprint Theme |  |  |  | Operational Prototyping, Test Planning & Design
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments | Is Level 1? | L1 Est. Hrs. Remain. | L1 Est. Hrs. | L1 Actual Hrs.
1 | Requirements |  |  | Brian, Rob, Joe, Mark |  |  | 31.5 | 28.5 | 100% | 0 |  | X | 0 | 31.5 | 28.5
1.1 |  | Finish Elicitation |  | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-12 | 5.5 | 6.5 | 100% | 0 | Elicitation still seems to need to be done as the client is adding more stuff at the last minute.
1.11 |  |  | client phone meetings | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-29 | 1.5 | 2.5 | 100% | 0 | We will not need to have client phone meetings for requirements anymore. The rest will be taken care of through emails.
1.12 |  |  | client emails | Rob | 2008-02-01 | 2008-02-29 | 4 | 4 | 100% | 0 | Emails should hopefully increase from the normal due to not having phone meetings with the client.
1.2 |  | Complete Baseline SRS Document |  | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-12 | 24 | 20 | 100% | 0 | Estimate extended as more work is needed
1.3 |  | Get Baseline SRS Approved By Client |  | Rob | 2008-02-01 | 2008-02-12 | 2 | 2 | 100% | 0 | We obtained lots of feedback on 2/5/2008, which was our original sign-off date. This pushed back the SRS process.
2 | Interim Project Status Presentation |  |  | Brian, Rob |  |  | 5 | 2 | 100% | 0 |  | X | 0 | 5 | 2
2.1 |  | Create Powerpoint Outline |  | Brian, Rob, Joe, Mark | 2008-02-12 | 2008-02-15 | 1 | 1 | 100% | 0
|  | Fill in slides |  | Brian, Rob, Joe, Mark | 2008-02-15 | 2008-02-18 | 2 | 1 | 100% | 0
2.2 |  | Review Slides |  | Brian, Rob, Joe, Mark | 2008-02-15 | 2008-02-18 | 2 | 0 | 100% | 0
3 | Test Plan Document |  |  | Brian, Rob, Mark |  |  | 12 | 6 | 75% | 3 |  | X | 3 | 12 | 6
3.1 |  | Plan Acceptance Testing |  | Rob, Mark,Brian | 2008-02-01 | 2008-02-19 | 12 | 6 | 75% | 3 | This has been pushed back from 2/15/2008 to 2/19/2008 due to more SRS work needed that was not planned.
4 | Design Document |  |  | Brian, Joe, Mark, Rob |  |  | 50 | 13 | 27.02% | 36.49 |  | X | 36.49 | 50 | 13
4.4 |  | Choose Software Patterns/Tactics |  | Brian, Joe, Mark, Rob | 2008-02-01 | 2008-02-28 | 4 | 1 | 25% | 3
4.5 |  | Create User Interface Design |  | Joe, Mark | 2008-02-07 | 2008-02-28 | 12 | 2 | 16.67% | 10
4.51 |  |  | class diagrams | ? | 2008-02-07 | 2008-02-28 | 2 |  | 0% | 2
4.52 |  |  | sequence diagrams | Joe | 2008-02-07 | 2008-02-28 | 6 |  | 0% | 6
4.53 |  |  | state diagrams | Joe | 2008-02-07 | 2008-02-28 | 4 | 2 | 50% | 2 | Joe worked on a bit
4.6 |  | Create Drawable Object Design |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 11 | 0 | 0% | 11
4.61 |  |  | class diagrams | ? | 2008-02-19 | 2008-02-28 | 2 |  | 0% | 2
|  |  | state diagrams | Joe | 2008-02-07 | 2008-02-28 | 4 |  | 0% | 4 | Joe worked on a bit
4.62 |  |  | sequence diagrams | ? | 2008-02-19 | 2008-02-28 | 5 |  | 0% | 5
4.7 |  | Create Concrete Object Design |  | Brian, Joe, Mark, Rob | 2008-02-26 | 2008-02-28 | 10 | 0.5 | 5.1% | 9.49
4.71 |  |  | class diagrams | ? | 2008-02-26 | 2008-02-28 | 2 |  | 0% | 2
|  |  | state diagrams | Joe | 2008-02-07 | 2008-02-28 | 3 | 0.5 | 17% | 2.49 | Joe worked on a bit
4.72 |  |  | sequence diagrams | ? | 2008-02-26 | 2008-02-28 | 5 |  | 0% | 5
4.8 |  | Create XML Translation Design |  | Joe | 2008-02-07 | 2008-02-28 | 12 | 9.5 | 83.33% | 2
4.81 |  |  | class diagrams | ? | 2008-02-07 | 2008-02-28 | 2 | 1.5 | 75% | 0.5
|  |  | state diagrams | Joe | 2008-02-07 | 2008-02-28 | 5 | 4 | 85% | 0.75 | Joe worked on a bit
4.82 |  |  | sequence diagrams | Joe | 2008-02-07 | 2008-02-28 | 5 | 4 | 85% | 0.75 | Joe worked on a bit
4.9 |  | Create Coding Standards |  | Brian, Joe, Mark, Rob | 2008-02-01 | 2008-02-28 | 1 |  | 0% | 1
5 | Product Release 1 |  |  | Brian, Joe, Mark, Rob |  |  | 8 | 3.75 | 46.88% | 4.25 |  | X | 4.25 | 8 | 3.75
5.1 |  | Code Stubs & Drivers |  | Brian, Joe, Mark | 2008-02-19 | 2008-02-22 | 1 | 0.25 | 25% | 0.75
5.2 |  | XML Reader |  | Joe | 2008-02-19 | 2008-02-25 | 4 | 2 | 50% | 2
5.3 |  | XML Validation |  | Joe | 2008-02-26 | 2008-02-29 | 1 | 1 | 100% | 0
5.4 |  | Add Comments |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 1 | 0.5 | 50% | 0.5
5.5 |  | Code Reviews |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 1 |  | 0% | 1
6 | Metrics |  |  | Mark |  |  | 6 | 0 | 100% | 0 |  | X | 0 | 6 | 0
6.1 |  | Take Measurements |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 100% | 0
6.2 |  | Create Metrics |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 100% | 0
6.3 |  | Update Website |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 100% | 0
6.4 |  | Take Measurements |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 100% | 0
6.5 |  | Create Metrics |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 100% | 0
6.6 |  | Update Website |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 100% | 0
7 | Manage Schedule |  |  | Brian |  |  | 12.8 | 4.9 | 100% | 0 |  | X | 0 | 12.8 | 4.9
7.1 |  | Update Estimated Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 4 | 2 | 100% | 0 | Update estimated hours twice per week
7.2 |  | Update Actual Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 2 | 1 | 100% | 0 | Update actual hours from timesheets once per week.
7.3 |  | Add Any New Activities |  | Brian | 2008-02-01 | 2/31/2008 | 2 | 0.5 | 100% | 0 | Add new activities once per week
7.4 |  | Modify Dates |  | Brian | 2008-02-01 | 2/31/2008 | 2 | 0.5 | 100% | 0 | Modify once a week.
7.5 |  | Move Data To Burndown Chart |  | Brian | 2008-02-01 | 2/31/2008 | 0.8 | 0.4 | 100% | 0 | Move twice a week.
7.6 |  | Work On Other Months |  | Brian | 2008-02-01 | 2/31/2008 | 2 | 0.5 | 100% | 0 | One hour spent on each April and May each.
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [5 empty] | 2008-02-09 | 125.3 | 58.15 | 65.09% | 43.74
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | End of Quarter |  |  | Interim Status Presentation | 2008-02-21

## March
Sprint Month |  |  |  | March
Sprint Theme |  |  |  | Refine Design & Implementation
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
1 | Design Document |  |  | Joe, Brian, Mark, Rob |  |  | 72 | 51 | 95.83% | 3
1.2 |  | User Interface Design (View/Control) |  | Brian, Joe, Mark, Rob | 2008-03-01 | 2008-03-20 | 16 | 9 | 92.5% | 1.2
1.2.1 |  |  | sequence diagrams |  | 2008-03-01 | 2008-03-20 | 8 | 6 | 85% | 1.2
1.2.2 |  |  | state diagrams |  | 2008-03-01 | 2008-03-20 | 8 | 3 | 100% | 0
1.3 |  | Drawable Object Design (View) |  | Brian, Joe, Mark, Rob | 2008-03-01 | 2008-03-20 | 18 | 10 | 90% | 1.8
1.3.1 |  |  | class diagrams |  | 2008-03-01 | 2008-03-20 | 10 | 5 | 90% | 1
1.3.2 |  |  | sequence diagrams |  | 2008-03-01 | 2008-03-20 | 8 | 5 | 90% | 0.8
1.4 |  | Concrete Object Design (Model) |  | Brian, Joe, Mark, Rob | 2008-03-01 | 2008-03-20 | 18 | 12 | 100% | 0
1.4.1 |  |  | class diagrams |  | 2008-03-01 | 2008-03-20 | 10 | 8 | 100% | 0
1.4.2 |  |  | sequence diagrams |  | 2008-03-01 | 2008-03-20 | 8 | 4 | 100% | 0
1.5 |  | Prototyping |  | Mark | 2008-03-01 | 2008-03-24 | 20 | 20 | 100% | 0
1.5.1 |  |  | Initial | Mark | 2008-03-01 | 2008-03-18 | 12 | 12 | 100% | 0
1.5.2 |  |  | Updates from Feedback | Mark | 2008-03-01 | 2008-03-24 | 8 | 8 | 100% | 0
3 | Test Planning |  |  | Brian, Rob |  |  | 35 | 27 | 100% | 0
3.1 |  | Acceptance Test Plan |  | Brian, Rob, Mark | 2008-03-01 | 2008-03-15 | 25 | 20 | 100% | 0
|  | Automated Test Planning |  | Brian, Rob, Mark | 2008-03-15 | 2008-03-31 | 10 | 7 | 100% | 0
4 | Product Release 1&2 |  |  | Joe, Mark, Brian, Rob |  |  | 79.75 | 81.75 | 89.97% | 8
4.1 |  | Read-Only Visualization |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-28 | 50 | 50 | 88% | 6
4.1.1 |  |  | Graphical Representations for test case elements |  | 2008-03-03 | 2008-03-28 | 40 | 38 | 85% | 6
4.1.2 |  |  | GUI components not test case |  | 2008-03-03 | 2008-03-28 | 10 | 12 | 100% | 0
4.2 |  | Initial XML |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-18 | 2.75 | 4 | 100% | 0
4.2.1 |  |  | Code Stubs & Drivers | Joe | 2008-03-03 | 2008-03-18 | 0.75 | 1 | 100% | 0
4.2.2 |  |  | XML Reader | Joe | 2008-03-03 | 2008-03-18 | 2 | 3 | 100% | 0
4.3 |  | Verify Code Comments |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-28 | 2 | 1.25 | 75% | 0.5
4.4 |  | Testing |  | Joe, Brian, Mark, Rob | 2008-03-03 | 2008-03-28 | 10 | 15 | 85% | 1.5
4.5 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-28 | 15 | 11.5 | 100% | 0
5 | Product Release 3 | [5 empty] | 14.5 | 11.3 | 100% | 0
5.1 |  | Property Modification of Test Cases |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 5 | 6 | 100% | 0 | More work was done than originally intended
5.2 |  | Full XML Read/Write Validation |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 2 | 1 | 100% | 0
5.3 |  | Save XML Test Case |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 2 | 1 | 100% | 0
5.4 |  | Verify Code Comments |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 1 | 0.3 | 100% | 0
|  | Testing |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 2.5 | 2 | 100% | 0
5.5 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 2 | 1 | 100% | 0
6 | User Guide |  |  | Joe, Mark, Brian, Rob |  |  | 4 | 0 | 0% | 4
6.1 |  | Start design and creation of user guide |  | Joe, Mark, Brian, Rob | 2008-03-28 | 2008-03-31 | 4 | 0 | 0% | 4
7 | Metrics |  |  | Mark |  |  | 6 | 3 | 50% | 3
7.1 |  | Take Measurements |  | Mark | 2008-03-01 | 2008-03-15 | 1 | 1 | 100% | 0
7.2 |  | Create Metrics |  | Mark | 2008-03-01 | 2008-03-15 | 1 | 1 | 100% | 0
7.3 |  | Update Website |  | Mark | 2008-03-01 | 2008-03-15 | 1 | 1 | 100% | 0
7.4 |  | Take Measurements |  | Mark | 2008-03-16 | 2008-03-31 | 1 |  |  | 1
7.5 |  | Create Metrics |  | Mark | 2008-03-16 | 2008-03-31 | 1 |  |  | 1
7.6 |  | Update Website |  | Mark | 2008-03-16 | 2008-03-31 | 1 |  |  | 1
8 | Manage Schedule |  |  | Brian |  |  | 9.5 | 4 | 95.79% | 0.4
8.1 |  | Update Estimated Work Hours |  | Brian | 2008-03-01 | 2008-03-31 | 1 | 0.2 | 100% | 0 | Update estimated hours twice per week
8.2 |  | Update Actual Work Hours |  | Brian | 2008-03-01 | 2008-03-31 | 1 | 0.25 | 99% | 0.01 | Update actual hours from timesheets once per week.
8.3 |  | Add Any New Activities |  | Brian | 2008-03-01 | 2008-03-31 | 1 | 0.2 | 100% | 0 | Add new activities once per week
8.4 |  | Modify Dates |  | Brian | 2008-03-01 | 2008-03-31 | 1 | 0.2 | 100% | 0 | Modify once a week.
8.5 |  | Move Data To Burndown Chart |  | Brian | 2008-03-01 | 2008-03-31 | 1 | 0.2 | 95% | 0.05 | Move twice a week.
8.6 |  | Create Slippage Chart |  | Brian | 2008-03-01 | 2008-03-16 | 1.5 | 1.5 | 100% | 0 | Sent to Carlyle
8.7 |  | Modify Slippage Chart |  | Brian | 2008-03-28 | 2008-03-31 | 1 | 0.2 | 66% | 0.34 | Add Release 2 by the end of the sprint
8.8 |  | Work On Other Months |  | Brian | 2008-03-01 | 2008-03-31 | 2 | 1.25 | 100% | 0 | One hour spent on each April and May each.
9 | Product Release 4 | [5 empty] | 0 | 2 | 100% | 0
9.1 |  | Drag and Drop UI |  | Joe |  |  | 0 | 2 | 100% | 0 | Work was not originally slated for March
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [6 empty] | 211.25 | 176.05 | 83.34% | 18
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | Release 1 |  |  | Executable | 2008-03-18
2 | Release 2 |  |  | Design Document | 2008-03-20
3 | Release 2 |  |  | Executable | 2008-03-28
4 | Release 3 |  |  | Design Document | 2008-03-31

## April
Sprint Month |  |  |  | April
Sprint Theme |  |  |  | Implementation, Integration, Verification, & Validation
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
1 | Product Release 2 | [5 empty] | 25.2 | 22 | 100% | 0
1.1 |  | Performance Improvements |  | Joe | 2008-04-01 | 2008-04-04 | 4 | 2 | 100% | 0
1.2 |  | Integrate Fancy Drawing |  | Mark, Joe | 2008-04-01 | 2008-04-02 | 5 | 5 | 100% | 0
|  | Test Data View Population |  | Brian | 2008-04-01 | 2008-04-04 | 2 | 1 | 100% | 0
1.3 |  | Property Box View |  | Mark | 2008-04-01 | 2008-04-04 | 3 | 4.75 | 100% | 0
1.4 |  | Remove Collapse from Param & VP |  | Joe | 2008-04-01 | 2008-04-03 | 1 | 0.2 | 100% | 0
1.5 |  | Openning of Invalid Documents |  | Joe | 2008-04-01 | 2008-04-03 | 1 | 1.5 | 100% | 0
|  | Tooltips |  | Rob | 2008-04-03 | 2008-04-06 | 4 | 2.5 | 100% | 0
1.6 |  | Testing |  | Rob | 2008-04-01 | 2008-04-06 | 3 | 3.5 | 100% | 0
1.7 |  | Touchups |  | Joe | 2008-04-04 | 2008-04-06 | 2 | 1.35 | 100% | 0
1.8 |  | Deliver to Pedersen |  | Joe | 2008-04-04 | 2008-04-04 | 0.1 | 0.1 | 100% | 0
1.9 |  | Deliver to Carlyle |  | Rob | 2008-04-04 | 2008-04-06 | 0.1 | 0.1 | 100% | 0
2 | Product Release 3 | [5 empty] | 36.2 | 37.25 | 63.54% | 13.2
2.1 |  | Property Modification of Test Cases |  | Mark, Joe, Rob | 2008-04-04 | 2008-04-10 | 4 | 1.75 | 35% | 2.6
2.2 |  | Undo/Redo Calling |  | Brian | 2008-04-04 | 2008-04-10 | 1 | 2 | 100% | 0
2.3 |  | XML Editor Updates |  | Joe | 2008-04-04 | 2008-04-10 | 2 | 3 | 80% | 0.4
2.4 |  | Debug |  | Joe | 2008-04-04 | 2008-04-10 | 4 | 2 | 100% | 0
2.5 |  | Save Test Case |  | Joe | 2008-04-04 | 2008-04-10 | 0.5 | 0.25 | 100% | 0
2.6 |  | Save Test Case As |  | Brian | 2008-04-04 | 2008-04-10 | 0.5 | 4 | 100% | 0
2.7 |  | Close Modified Test Case |  | Brian | 2008-04-04 | 2008-04-10 | 2 | 7 | 100% | 0
2.8 |  | Verify Code Comments |  | Joe, Mark, Brian, Rob | 2008-04-04 | 2008-04-12 | 2 | 1 | 50% | 1
2.9 |  | Testing |  | Rob | 2008-04-04 | 2008-04-12 | 10 | 10.25 | 80% | 2
2.10 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-04-04 | 2008-04-12 | 8 | 4 | 25% | 6
2.11 |  | Touchups |  | Joe, Mark, Brian, Rob | 2008-04-08 | 2008-04-12 | 2 | 2 | 50% | 1
2.12 |  | Deliver to Pedersen |  | Rob | 2008-04-08 | 2008-04-10 | 0.1 |  | 0% | 0.1
2.13 |  | Deliver to Carlyle |  | Rob | 2008-04-10 | 2008-04-12 | 0.1 |  | 0% | 0.1
3 | Product Release 4 | [5 empty] | 80.7 | 0 | 0% | 80.7
3.1 |  | Drag-N-Drop UI |  | Mark, Joe | 2008-04-10 | 2008-04-20 | 33 | 0 | 0% | 33
3.1.1 |  |  | Add Artifacts | Mark, Joe | 2008-04-10 | 2008-04-20 | 15 |  | 0% | 15
3.1.2 |  |  | Copy/Move Artifacts | Mark | 2008-04-10 | 2008-04-20 | 4 |  | 0% | 4
3.1.3 |  |  | Adjust Sequencing | Joe | 2008-04-10 | 2008-04-20 | 4 |  | 0% | 4
3.1.4 |  |  | Delete Artifacts | Mark | 2008-04-10 | 2008-04-20 | 2 |  | 0% | 2
3.1.5 |  |  | Add/Remove Comments | Mark, Joe | 2008-04-10 | 2008-04-20 | 8 |  | 0% | 8
3.2 |  | Read-only file opening |  | Joe | 2008-04-10 | 2008-04-20 | 0.5 |  | 0% | 0.5
3.3 |  | Auto XML Editor Updates |  | Brian | 2008-04-10 | 2008-04-20 | 1 |  | 0% | 1
3.4 |  | Autosaving |  | Brian | 2008-04-10 | 2008-04-20 | 12 | 0 | 0% | 12
3.4.1 |  |  | Create Auto-save files | Brian | 2008-04-10 | 2008-04-20 | 3 |  | 0% | 3
3.4.2 |  |  | Recover upon detection of files | Brian | 2008-04-10 | 2008-04-20 | 9 |  | 0% | 9
3.5 |  | Undo/Redo Settings |  | Brian | 2008-04-10 | 2008-04-20 | 1 |  | 0% | 1
3.6 |  | Color/Font Settings |  | Brian | 2008-04-10 | 2008-04-20 | 1 |  | 0% | 1
3.7 |  | Verify Code Comments |  | Joe, Mark, Brian, Rob | 2008-04-10 | 2008-04-22 | 2 |  | 0% | 2
3.8 |  | Testing |  | Rob | 2008-04-10 | 2008-04-22 | 20 |  | 0% | 20
3.9 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-04-10 | 2008-04-22 | 8 |  | 0% | 8
3.10 |  | Touchups |  | Joe, Mark, Brian, Rob | 2008-04-18 | 2008-04-22 | 2 |  | 0% | 2
3.11 |  | Deliver to Pedersen |  | Rob | 2008-04-18 | 2008-04-20 | 0.1 |  | 0% | 0.1
3.12 |  | Deliver to Carlyle |  | Rob | 2008-04-20 | 2008-04-22 | 0.1 |  | 0% | 0.1
4 | User Guide | [5 empty] | 4 | 0 | 0% | 4
4.1 |  | Design and creation |  | Joe, Mark, Brian, Rob | 2008-04-04 | 2008-04-30 | 4 |  | 0% | 4
5 | Final Poster | [5 empty] | 20 | 0 | 0% | 20
5.1 |  | Make award winning poster |  | Joe, Mark, Brian, Rob | 2008-04-04 | 2008-04-22 | 20 |  | 0% | 20 | Due at noon on 4/24!
6 | Metrics | [5 empty] | 6 | 0 | 0% | 6
6.1 |  | Take Measurements |  | Mark | 2008-04-06 | 2008-04-06 | 1 |  | 0% | 1
6.2 |  | Create Metrics |  | Mark | 2008-04-06 | 2008-04-06 | 1 |  | 0% | 1
6.3 |  | Update Website |  | Mark | 2008-04-06 | 2008-04-06 | 1 |  | 0% | 1
6.4 |  | Take Measurements |  | Mark | 2008-04-20 | 2008-04-20 | 1 |  | 0% | 1
6.5 |  | Create Metrics |  | Mark | 2008-04-20 | 2008-04-20 | 1 |  | 0% | 1
6.6 |  | Update Website |  | Mark | 2008-04-20 | 2008-04-20 | 1 |  | 0% | 1
7 | Manage Schedule | [5 empty] | 11.5 | 4.4 | 40.43% | 6.85
7.1 |  | Update Estimated Work Hours |  | Brian | 2008-04-01 | 2008-04-30 | 5 | 4.1 | 90% | 0.5 | Update estimated hours twice per week
7.2 |  | Update Actual Work Hours |  | Brian | 2008-04-01 | 2008-04-30 | 2 | 0.2 | 5% | 1.9 | Update actual hours from timesheets once per week.
7.3 |  | Add Any New Activities |  | Brian | 2008-04-01 | 2008-04-30 | 0.5 | 0.1 | 10% | 0.45 | Add new activities once per week
7.4 |  | Modify Dates |  | Brian | 2008-04-01 | 2008-04-30 | 0.5 |  | 0% | 0.5 | Modify once a week.
7.5 |  | Move Data To Burndown Chart |  | Brian | 2008-04-01 | 2008-04-30 | 1 |  | 0% | 1 | Move twice a week.
7.7 |  | Update Slippage Chart |  | Brian | 2008-04-01 | 2008-04-30 | 0.5 |  | 0% | 0.5 | Modify it by the end of the month.
7.8 |  | Work On Other Month |  | Brian | 2008-04-01 | 2008-04-30 | 2 |  | 0% | 2
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [6 empty] | 183.6 | 63.65 | 34.67% | 130.75
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | Release 2 |  |  | Executable | 2008-04-06
2 | Release 3 |  |  | Executable | 2008-04-12
3 | Release 4 |  |  | Executable | 2008-04-22

## May
Sprint Month |  |  |  | May
Sprint Theme |  |  |  | Wrap Up
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
1 | User Guide | [5 empty] | 0 | 0 | #DIV/0! | 0
1.2 |  | Finish
2 | Code | [5 empty] | 0 | 0 | #DIV/0! | 0
2.1 |  | Final Code Reviews | [7 empty] | 0
2.2 |  | Refactor, if necessary | [7 empty] | 0
2.3 |  | Comment all code | [7 empty] | 0
3 | Testing | [5 empty] | 0 | 0 | #DIV/0! | 0
3.1 |  | Complete final tests | [7 empty] | 0
3.2 |  | Update testing documents | [7 empty] | 0
4 | Bugs | [5 empty] | 0 | 0 | #DIV/0! | 0
4.1 |  | Record and document all existing bugs | [7 empty] | 0
5 | Product Release 5 - Final | [5 empty] | 0 | 0 | #DIV/0! | 0
5.1 |  | Finishing UI touches | [7 empty] | 0
5.2 |  | Fix bugs
5.3 |  | Final Project CD | [7 empty] | 0
6 | User Guide | [5 empty] | 0 | 0 | #DIV/0! | 0
6.1 |  | Finish | [7 empty] | 0
6.2 | Documentation | [5 empty] | 0 | 0 | #DIV/0! | 0
6.3 |  | Project technical report | [7 empty] | 0
6.4 |  | Project reflection report | [7 empty] | 0
7 | Metrics |  |  | Mark |  |  | 6 | 0 | 0% | 6
7.1 |  | Take Measurements |  | Mark |  |  | 1 |  |  | 1
7.2 |  | Create Metrics |  | Mark |  |  | 1 |  |  | 1
7.3 |  | Update Website |  | Mark |  |  | 1 |  |  | 1
7.4 |  | Take Measurements |  | Mark |  |  | 1 |  |  | 1
7.5 |  | Create Metrics |  | Mark |  |  | 1 |  |  | 1
7.6 |  | Update Website |  | Mark |  |  | 1 |  |  | 1
8 | Manage Schedule |  |  | Brian |  |  | 15.8 | 0 | 0% | 15.8
8.1 |  | Update Estimated Work Hours |  | Brian |  |  | 4 |  |  | 4 | Update estimated hours twice per week
8.2 |  | Update Actual Work Hours |  | Brian |  |  | 2 |  |  | 2 | Update actual hours from timesheets once per week.
8.3 |  | Add Any New Activities |  | Brian |  |  | 2 |  |  | 2 | Add new activities once per week
8.4 |  | Modify Dates |  | Brian |  |  | 2 |  |  | 2 | Modify once a week.
8.5 |  | Move Data To Burndown Chart |  | Brian |  |  | 0.8 |  |  | 0.8 | Move twice a week.
8.6 |  | Create Slippage Chart |  | Brian |  |  | 1.5 |  |  | 1.5 | For Carlyle soon!
8.7 |  | Modify Slippage Chart |  | Brian |  |  | 1.5 |  |  | 1.5 | Modify it by the end of the month.
8.8 |  | Work On Other Months |  | Brian |  |  | 2 |  |  | 2 | One hour spent on each April and May each.
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [6 empty] | 21.8 | 0 | 0% | 21.8
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | Release 5 |  |  | Executable | 2008-03-18
2 | Release 5 |  |  | Design Document | 2008-03-20
3 | Final |  |  | Poster | 2008-03-20
4 | Final |  |  | Presentation | 2008-03-20
5 | Release 5 |  |  | Final Project CD | 2008-03-20

## Burn Down Charts
February
Date | Estimated Hours Remaining | Comments
2008-02-05 | 143
2008-02-06 | 135 | Moved some stuff to March
2008-02-08 | 114.1
2008-02-09 | 126.9 | Added schedule management activities
2008-02-15 | 116.4 | Week 9 and SRS other work getting done as planned
2008-02-16 | 116.4 | spring break
2008-02-17 | 116.4 | spring break
2008-02-19 | 116.4 | spring break
2008-02-21 | 116.4 | spring break
2008-02-23 | 116.4 | spring break
2008-02-25 | 116.4 | spring break
2008-02-27 | 116.4 | spring break
2008-02-29 | 116.4 | spring break
March
Date | Estimated Hours Remaining | Comments
2008-03-01 | 251
2008-03-03 | 251 | did not update
2008-03-05 | 251 | did not update
2008-03-07 | 251 | did not update
2008-03-09 | 251 | did not update
2008-03-11 | 251 | did not update
2008-03-13 | 213
2008-03-15 | 213 | did not update
2008-03-17 | 213 | did not update
2008-03-19 | 199
2008-03-21 | 199 | did not update
2008-03-23 | 199 | did not update
2008-03-25 | 88.05 | design almost complete and coding started!!
2008-03-27 | 88.05 | did not update
2008-03-29 | 59.34 | Lots of coding for Release 2 to finish, not all will get done.
April
Date | Estimated Hours Remaining | Comments
2008-04-01 | 183.6
2008-04-03 | 177.6
2008-04-05
2008-04-07
2008-04-09
2008-04-11
2008-04-13
2008-04-15
2008-04-17
2008-04-19
2008-04-21
2008-04-23
2008-04-25
2008-04-27
2008-04-29
May
Date | Estimated Hours Remaining | Comments
2008-05-01
2008-05-03
2008-05-05
2008-05-07
2008-05-09
2008-05-11
2008-05-13
2008-05-15
2008-05-17
2008-05-19
2008-05-21
2008-05-23
2008-05-25
2008-05-27
2008-05-29
2008-05-31