## December
Sprint Month |  |  |  | December
Sprint Theme |  |  |  | Elicitation & Planning
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | % Complete | Estimated Hours Remaining | Comments
1 | Project Synopsis Document
|  | Create |  | Joe | 2008-12-05 | 2008-12-31 | 0 | 1 | 100% | 0 | Did not estimate because it was done in the first week of class.
2 | Project Planning |  |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31
2.1 |  | Week 1 |  | Brian | 2007-12-03 | 2007-12-09 | 0 | 0.5 | 100% | 0 | Did not estimate because it was done in the first week of class.
2.2 |  | Week 2 |  | Brian, Joe | 2007-12-10 | 2007-12-16 | 1.75 | 1.5 | 100% | 0 | Joe overestimated a little.
2.3 |  | Week 3 |  | Brian, Rob, Joe, Mark | 2007-12-17 | 2007-12-23 | 8 | 11.25 | 100% | 0 | Everyone pitched in to make sure that this document was well thought out and had enough in it before Xmas break started.
3 | Requirements Elicitation |  |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31
3.1 |  | client phone meetings |  | Brian, Rob, Joe, Mark | 2007-12-05 | 2007-12-31 | 12 | 12 | 100% | 0 | Estimated at 1.5 per week for 4 weeks
|  | client emails |  | Rob | 2007-12-05 | 2007-12-31 | 6 | 8 | 100% | 0 | About 2 hours per week estimated
4 | Project Website
|  | Create |  | Mark | 2008-12-05 | 2008-12-31 | 3 | 4 | 100% | 0 | Mark overestimated by 1 hour.
5 | Report Time Effort |  |  | Brian, Rob, Joe, Mark | 2007-12-03 | 2007-12-31
5.1 |  | Week 1 |  | Brian, Rob, Joe, Mark | 2007-12-03 | 2007-12-09 | 0 | 1 | 100% | 0 | Did not estimate because it was done in the first week of class.
5.2 |  | Week 2 |  | Brian, Rob, Joe, Mark | 2007-12-10 | 2007-12-16 | 1 | 1 | 100% | 0 | Estimate correct
5.3 |  | Week 3 |  | Brian, Rob, Joe, Mark | 2007-12-17 | 2007-12-23 | 1 | 1 | 100% | 0 | Estimate correct
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
| N/A |  |  | None! | N/A

## January
Sprint Month |  |  |  | January
Sprint Theme |  |  |  | Requirements & Throwaway Prototyping
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | % Complete | Estimated Hours Remaining | Comments
1 | Requirements |  |  | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-02-04
1.1 |  | Elicitation |  | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-02-04
1.11 |  |  | client phone meetings | Brian, Rob, Joe, Mark | 2008-01-01 | 2008-01-31 | 12 | 12 | 100% | 0 | 12
1.2 |  | Baseline SRS Document |  | Brian, Rob, Joe | 2008-01-01 | 2008-02-05
1.21 |  |  | Week 4 | Brian, Rob | 2008-01-07 | 2008-01-13 | 2 | 6.5 | 100% | 0 | Brian estimated only, Rob worked on as well.
1.22 |  |  | Week 5 | Brian, Rob | 2008-01-14 | 2008-01-20 | 6 | 4.5 | 100% | 0 | Brian estimated, but Rob worked on only.
1.23 |  |  | Week 6 | Brian, Rob | 2008-01-21 | 2008-01-27 | 6 | 12 | 100% | 0 | Spent much more time on SRS due to client feedback
1.24 |  |  | Week 7 | Brian, Rob, Joe | 2008-01-28 | 2008-02-03 | 15 | 10 | 90% | 1.5 | Everyone started working on because we needed more, FAST!
1.3 |  | UI Prototypes |  | Joe, Mark | 2008-01-01 | 2008-01-31
1.31 |  |  | Week 4 | Joe, Mark | 2008-01-07 | 2008-01-13 | 0 | 3 | 100% | 0 | Did not plan on working on visualizations, but did due to free time and/or personal interest in the subject
1.32 |  |  | Week 5 | Joe, Mark | 2008-01-14 | 2008-01-20 | 12 | 10.5 | 100% | 0
1.33 |  |  | Week 6 | Joe, Mark | 2008-01-21 | 2008-01-27 | 9.5 | 7.75 | 100% | 0
1.34 |  |  | Week 7 | Joe, Mark | 2008-01-28 | 2008-02-03 | 2 | 3 | 100% | 0 | Joe did not estimate time, but assisted Mark anyways.
2 | Coding |  |  | Joe | 2008-01-01 | 2008-01-31
2.1 |  | XML [Un]Marshalling Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 10 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/28/2008. Get better values from Joe.
2.2 |  | Drag & Drop Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 2.5 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/26/2008. Get better values from Joe.
2.3 |  | GDI+ Prototypes |  | Joe | 2008-01-01 | 2008-01-31 | 0 | 0 | 100% | 0 | Estimate was not in timesheet, but actual hours worked on were in an email sent on 1/26/2008. Get better values from Joe.
3 | Project Planning |  |  | Brian | 2008-01-01 | 2008-01-31
3.1 |  | Project Plan Document |  | Brian | 2008-01-01 | 2008-01-31
3.11 |  |  | Week 4 | Brian | 2008-01-07 | 2008-01-13 | 0 | 0 | 100% | 0 | Was not planned to be worked on and was not worked on. Requirements started and took most of our time.
3.12 |  |  | Week 5 | Brian | 2008-01-14 | 2008-01-20 | 0 | 0 | 100% | 0 | Was not planned to be worked on and was not worked on. Requirements started and took most of our time.
3.13 |  |  | Week 6 | Brian | 2008-01-21 | 2008-01-27 | 2 | 0 | 100% | 0 | Interview out of town interfered with working on project plan.
3.14 |  |  | Week 7 | Brian | 2008-01-28 | 2008-02-03 | 2 | 2 | 100% | 0
3.2 |  | Risk Management Document |  | Brian | 2008-01-01 | 2008-01-31
3.21 |  |  | Week 4 | Brian | 2008-01-07 | 2008-01-13 | 0 | 0 | 100% | 0
3.22 |  |  | Week 5 | Brian | 2008-01-14 | 2008-01-20 | 0 | 0 | 100% | 0
3.23 |  |  | Week 6 | Brian | 2008-01-21 | 2008-01-27 | 0 | 0 | 100% | 0
3.24 |  |  | Week 7 | Brian | 2008-01-28 | 2008-02-03 | 0 | 4 | 100% | 0 | Moved from project planning document to its own document and beautified.
4 | Req's Negotiation - Part 1
4.1 |  | Negotiate |  | Brian, Joe, Mark, Rob | 2008-01-17 | 2008-01-17 | 1 | 1 | 100% | 0 | The client visited Rochester and we negotiated some requirements with first draft of SRS, in person.
5 | Metrics |  |  | Mark | 2008-01-01 | 2008-01-31 |  |  |  |  | We forgot about metrics until we did a couple revisions of the schedule and worked on the project plan again!!
5.1 |  | Take Measurements |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.2 |  | Create Metrics |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.3 |  | Update Website |  | Mark | 2008-01-01 | 2008-01-15 | 0 | 0 | 100% | 0
5.4 |  | Take Measurements |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
5.5 |  | Create Metrics |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
5.6 |  | Update Website |  | Mark | 2008-01-16 | 2008-01-31 | 0 | 0 | 100% | 0
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
| N/A |  |  | None! | N/A

## February
Sprint Month |  |  |  | February
Sprint Theme |  |  |  | Operational Prototyping, Test Planning & Design
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments | Is Level 1? | L1 Est. Hrs. Remain. | L1 Est. Hrs. | L1 Actual Hrs.
1 | Requirements |  |  | Brian, Rob, Joe, Mark |  |  | 19 | 8.5 | 69.47% | 5.8 |  | X | 5.8 | 19 | 8.5
1.1 |  | Finish Elicitation |  | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-12 | 5.5 | 2.5 | 60% | 2.2 | Elicitation still seems to need to be done as the client is adding more stuff at the last minute.
1.11 |  |  | client phone meetings | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-29 | 1.5 | 1.5 | 100% | 0 | We will not need to have client phone meetings for requirements anymore. The rest will be taken care of through emails.
1.12 |  |  | client emails | Rob | 2008-02-01 | 2008-02-29 | 4 | 1 | 45% | 2.2 | Emails should hopefully increase from the normal due to not having phone meetings with the client.
1.2 |  | Complete Baseline SRS Document |  | Brian, Rob, Joe, Mark | 2008-02-01 | 2008-02-12 | 6 | 5 | 65% | 2.1 | Estimate extended as more work is needed
1.3 |  | Get Baseline SRS Approved By Client |  | Rob | 2008-02-01 | 2008-02-12 | 2 | 1 | 25% | 1.5 | We obtained lots of feedback on 2/5/2008, which was our original sign-off date. This pushed back the SRS process.
2 | Interim Project Status Presentation |  |  | Brian, Rob | 2008-02-12 |  | 3 | 0 | 0% | 3 |  | X | 3 | 3 | 0
2.1 |  | Create Powerpoint Outline |  | ? | 2008-02-12 | 2008-02-15 | 1 |  | 0% | 1
2.2 |  | Fill in slides |  | ? | 2008-02-15 | 2008-02-21 | 2 |  | 0% | 2
3 | Test Plan Document |  |  | Brian, Rob, Mark |  |  | 16 | 0 | 9.375% | 14.5 |  | X | 14.5 | 16 | 0
3.1 |  | Plan Acceptance Testing |  | Rob, Mark | 2008-02-01 | 2008-02-19 | 6 |  | 25% | 4.5 | This has been pushed back from 2/15/2008 to 2/19/2008 due to more SRS work needed that was not planned.
3.2 |  | Plan System Testing |  | ? | 2008-02-01 | 2/31/2008 | 4 |  | 0% | 4
3.3 |  | Plan Unit Testing |  | ? | 2008-02-01 | 2/31/2008 | 4 |  | 0% | 4
3.4 |  | Plan Automated Testing |  | ? | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2
4 | Design Document |  |  | Brian, Joe, Mark, Rob |  |  | 74 | 5 | 1.351% | 73 |  | X | 73 | 74 | 5
4.4 |  | Choose Software Patterns/Tactics |  | Brian, Joe, Mark, Rob | 2008-02-01 | 2008-02-28 | 5 | 5 | 0% | 5
4.5 |  | Create User Interface Design |  | Joe, Mark | 2008-02-07 | 2008-02-28 | 20 | 0 | 5% | 19
4.51 |  |  | class diagrams | ? | 2008-02-07 | 2008-02-28 | 8 |  | 0% | 8
4.52 |  |  | sequence diagrams | ? | 2008-02-07 | 2008-02-28 | 8 |  | 0% | 8
4.53 |  |  | state diagrams | ? | 2008-02-07 | 2008-02-28 | 4 |  | 25% | 3
4.6 |  | Create Drawable Object Design |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 16 | 0 | 0% | 16
4.61 |  |  | class diagrams | ? | 2008-02-19 | 2008-02-28 | 8 |  | 0% | 8
4.62 |  |  | sequence diagrams | ? | 2008-02-19 | 2008-02-28 | 8 |  | 0% | 8
4.7 |  | Create Concrete Object Design |  | Brian, Joe, Mark, Rob | 2008-02-26 | 2008-02-28 | 16 | 0 | 0% | 16
4.71 |  |  | class diagrams | ? | 2008-02-26 | 2008-02-28 | 8 |  | 0% | 8
4.72 |  |  | sequence diagrams | ? | 2008-02-26 | 2008-02-28 | 8 |  | 0% | 8
4.8 |  | Create XML Translation Design |  | Joe | 2008-02-07 | 2008-02-28 | 16 | 0 | 0% | 16
4.81 |  |  | class diagrams | ? | 2008-02-07 | 2008-02-28 | 8 |  | 0% | 8
4.82 |  |  | sequence diagrams | ? | 2008-02-07 | 2008-02-28 | 8 |  | 0% | 8
4.9 |  | Create Coding Standards |  | Brian, Joe, Mark, Rob | 2008-02-01 | 2008-02-28 | 1 |  | 0% | 1
5 | Product Release 1 |  |  | Brian, Joe, Mark, Rob |  |  | 22 | 6 | 46.36% | 11.8 |  | X | 11.8 | 22 | 6
5.1 |  | Code Stubs & Drivers |  | Brian, Joe, Mark | 2008-02-19 | 2008-02-22 | 8 |  | 0% | 8
5.2 |  | XML Reader |  | Joe | 2008-02-19 | 2008-02-25 | 6 | 3 | 85% | 0.9
5.3 |  | XML Validation |  | Joe | 2008-02-26 | 2008-02-29 | 6 | 3 | 85% | 0.9
5.4 |  | Add Comments |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 1 |  | 0% | 1
5.5 |  | Code Reviews |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-28 | 1 |  | 0% | 1
6 | Metrics |  |  | Mark |  |  | 6 | 0 | 0% | 6 |  | X | 6 | 6 | 0
6.1 |  | Take Measurements |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 0% | 1
6.2 |  | Create Metrics |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 0% | 1
6.3 |  | Update Website |  | Mark | 2008-02-01 | 2008-02-15 | 1 |  | 0% | 1
6.4 |  | Take Measurements |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 0% | 1
6.5 |  | Create Metrics |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 0% | 1
6.6 |  | Update Website |  | Mark | 2008-02-16 | 2008-02-29 | 1 |  | 0% | 1
7 | Manage Schedule |  |  | Brian |  |  | 12.8 | 0 | 0% | 12.8 |  | X | 12.8 | 12.8 | 0
7.1 |  | Update Estimated Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 4 |  | 0% | 4 | Update estimated hours twice per week
7.2 |  | Update Actual Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Update actual hours from timesheets once per week.
7.3 |  | Add Any New Activities |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Add new activities once per week
7.4 |  | Modify Dates |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Modify once a week.
7.5 |  | Move Data To Burndown Chart |  | Brian | 2008-02-01 | 2/31/2008 | 0.8 |  | 0% | 0.8 | Move twice a week.
7.6 |  | Work On Other Months |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | One hour spent on each April and May each.
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [5 empty] | 2008-02-09 | 152.8 | 19.5 | 16.95% | 126.9
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | End of Quarter |  |  | Interim Status Presentation | 2008-02-21

## March
Sprint Month |  |  |  | March
Sprint Theme |  |  |  | Refine Design & Implementation
# | Activity Level 1 | Activity Level 2 | Activity Level 3 | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
1 | Design Document |  |  | Joe, Brian, Mark, Rob |  |  | 14 | 0 | 0% | 14
1.2 |  | User Interface Design |  | Joe, Mark | 2008-02-07 | 2008-02-18 | 6 | 0 | 0% | 6
1.2.1 |  |  | class diagrams | ? | 2008-02-07 | 2008-02-18 | 2 |  |  | 2
1.2.2 |  |  | sequence diagrams | ? | 2008-02-07 | 2008-02-18 | 2 |  |  | 2
1.2.3 |  |  | state diagrams | ? | 2008-02-07 | 2008-02-18 | 2 |  |  | 2
1.3 |  | Drawable Object Design |  | Brian, Joe, Mark, Rob | 2008-02-19 | 2008-02-25 | 4 | 0 | 0% | 4
1.3.1 |  |  | class diagrams | ? | 2008-02-19 | 2008-02-25 | 2 |  |  | 2
1.3.2 |  |  | sequence diagrams | ? | 2008-02-19 | 2008-02-25 | 2 |  |  | 2
1.4 |  | Concrete Object Design |  | Brian, Joe, Mark, Rob | 2008-02-26 | 2008-03-03 | 4 | 0 | 0% | 4
1.4.1 |  |  | class diagrams | ? | 2008-02-26 | 2008-03-03 | 2 |  |  | 2
1.4.2 |  |  | sequence diagrams | ? | 2008-02-26 | 2008-03-03 | 2 |  |  | 2
2 | Requirements Negotiation Part II |  |  | Joe, Brian, Mark, Rob |  |  | 10 | 0 | 0% | 10
2.1 |  | Negotiate |  | Joe, Brian, Mark, Rob | 2008-03-01 | 2008-03-31 | 2 |  |  | 2
2.2 |  | Update SRS Document |  | Brian, Rob | 2008-03-01 | 2008-03-31 | 4 |  |  | 4
2.3 |  | Update SDD |  | Joe, Mark | 2008-03-01 | 2008-03-31 | 4 |  |  | 4
3 | Update Test Plan Document |  |  | Brian, Rob |  |  | 14 | 0 | 0% | 14
3.1 |  | Add Unit Test Planning |  | Brian, Rob | 2008-03-01 | 2008-03-15 | 8 |  |  | 8
3.2 |  | Update Test Plan Document |  | Brian, Rob | 2008-03-01 | 2008-03-15 | 4 |  |  | 4
3.3 |  | Finish Baseline Test Plan Document |  | Brian, Rob | 2008-03-01 | 2008-03-15 | 2 |  |  | 2
4 | Product Release 2 |  |  | Joe, Mark, Brian, Rob |  |  | 26 | 0 | 0% | 26
4.1 |  | Read-Only Visualization |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-18 | 20 |  |  | 20
4.2 |  | Add Comments |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-31 | 2 |  |  | 2
4.3 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-31 | 4 |  |  | 4
5 | Product Release 3 | [5 empty] | 46 | 0 | 0% | 46
5.1 |  | Property Modification of Test Cases |  | Joe, Mark, Brian, Rob | 2008-03-19 | 2008-03-31 | 10 |  |  | 10
5.2 |  | Full XML Read/Write Validation |  | Joe, Mark, Brian, Rob | 2008-03-19 | 2008-03-24 | 15 |  |  | 15
5.3 |  | Save XML Test Case |  | Joe, Mark, Brian, Rob | 2008-03-25 | 2008-03-26 | 15 |  |  | 15
5.4 |  | Add Comments |  | Joe, Mark, Brian, Rob | 2008-03-19 | 2008-03-31 | 2 |  |  | 2
5.5 |  | Perform Code Reviews |  | Joe, Mark, Brian, Rob | 2008-03-19 | 2008-03-31 | 4 |  |  | 4
6 | User Guide |  |  | Joe, Mark, Brian, Rob |  |  | 4 | 0 | 0% | 4
6.1 |  | Start design and creation of user guide |  | Joe, Mark, Brian, Rob | 2008-03-03 | 2008-03-31 | 4 |  |  | 4
7 | Metrics |  |  | Mark |  |  | 6 | 0 | 0% | 6
7.1 |  | Take Measurements |  | Mark | 2008-01-01 | 2008-01-15 | 1 |  |  | 1
7.2 |  | Create Metrics |  | Mark | 2008-01-01 | 2008-01-15 | 1 |  |  | 1
7.3 |  | Update Website |  | Mark | 2008-01-01 | 2008-01-15 | 1 |  |  | 1
7.4 |  | Take Measurements |  | Mark | 2008-01-16 | 2008-01-31 | 1 |  |  | 1
7.5 |  | Create Metrics |  | Mark | 2008-01-16 | 2008-01-31 | 1 |  |  | 1
7.6 |  | Update Website |  | Mark | 2008-01-16 | 2008-01-31 | 1 |  |  | 1
8 | Manage Schedule |  |  | Brian |  |  | 12.8 | 0 | 0% | 12.8
8.1 |  | Update Estimated Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 4 |  | 0% | 4 | Update estimated hours twice per week
8.2 |  | Update Actual Work Hours |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Update actual hours from timesheets once per week.
8.3 |  | Add Any New Activities |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Add new activities once per week
8.4 |  | Modify Dates |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | Modify once a week.
8.5 |  | Move Data To Burndown Chart |  | Brian | 2008-02-01 | 2/31/2008 | 0.8 |  | 0% | 0.8 | Move twice a week.
8.6 |  | Work On Other Months |  | Brian | 2008-02-01 | 2/31/2008 | 2 |  | 0% | 2 | One hour spent on each April and May each.
[6 empty] | Last Updated | Estimated Work Hours | Actual Work Hours | Estimated % Complete | Estimated Hours Remaining | Comments
Total | [6 empty] | 120 | 0 | 0 | 120
| Milestone Description |  |  | Milestone Deliverables | Milestone Date
1 | N/A |  |  | None! | N/A

## April
Sprint Month | April
Sprint Theme | Implementation, Integration, Verification, & Validation
Activity | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours
Product Release 4
Drag & Drop UI | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-12
Add Comments | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-12
Integrate Subsystems | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-12
Fix Bugs | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-12
Perform Code Reviews | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-12
Testing
Verify Unit Tests | Brian, Rob | 2008-04-02 | 2008-04-18
Verify System Tests | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-18
Verify Integration Tests | Joe, Mark | 2008-04-02 | 2008-04-18
Perform Usability Tests | Brian, Rob | 2008-04-02 | 2008-04-18
Document Bugs | Joe, Brian, Mark, Rob | 2008-04-02 | 2008-04-18
Metrics
Take Measurements | Joe, Brian, Mark, Rob | 2008-04-01 | 2008-04-15
Create Metrics | Joe, Brian, Mark, Rob | 2008-04-01 | 2008-04-15
Update Website | Joe, Brian, Mark, Rob | 2008-04-01 | 2008-04-15
Take Measurements | Joe, Brian, Mark, Rob | 2008-04-16 | 2008-04-30
Create Metrics | Joe, Brian, Mark, Rob | 2008-04-16 | 2008-04-30
Update Website | Joe, Brian, Mark, Rob | 2008-04-16 | 2008-04-30
Continue Creating User Guide | Joe, Brian, Mark, Rob | 2008-04-01 | 2008-04-30
Beging Working on Final Poster | Joe, Brian, Mark, Rob | 2008-04-03 | 2008-04-30
Milestone Description | Milestone Deliverables | Milestone Date
N/A | None! | N/A

## May
Sprint Month | April
Sprint Theme | Wrap Up
Activity | Assigned To | Activity Start Date | Activity End Date | Estimated Work Hours | Actual Work Hours
Finish Creating User Guide | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Comment All Code | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-06
Finish Final Project Poster | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Final Product Release
Complete Finishing Touches on UI | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-06
Fix Bugs | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-06
Finalize Comments | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-06
Document All Bugs | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Complete All Final Documentation
Project Technical Report | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Project Reflection Report | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Final Project CD | Joe, Brian, Mark, Rob | 2008-05-01 | 2008-05-15
Milestone Description | Milestone Deliverables | Milestone Date
End of Senior Project | Final Project Poster | TBA
End of Implementation | Completed Application | 2008-05-06

## Burn Down Charts
February
Date | Estimated Hours Remaining | Comments
2008-02-05 | 143
2008-02-06 | 135 | Moved some stuff to March
2008-02-08 | 114.1
2008-02-09 | 126.9 | Added schedule management activities
2008-02-11
2008-02-13
2008-02-15
2008-02-17
2008-02-19
2008-02-21
2008-02-23
2008-02-25
2008-02-27
2008-02-29
March
Date | Estimated Hours Remaining | Comments
2008-03-01
2008-03-03
2008-03-05
2008-03-07
2008-03-09
2008-03-11
2008-03-13
2008-03-15
2008-03-17
2008-03-19
2008-03-21
2008-03-23
2008-03-25
2008-03-27
2008-03-29
April
Date | Estimated Hours Remaining | Comments
2008-04-01
2008-04-03
2008-04-05
2008-04-07
2008-04-09
2008-04-11
2008-04-13
2008-04-15
2008-04-17
2008-04-19
2008-04-21
2008-04-23
2008-04-25
2008-04-27
2008-04-29
May
Date | Estimated Hours Remaining | Comments
2008-05-01
2008-05-03
2008-05-05
2008-05-07
2008-05-09
2008-05-11
2008-05-13
2008-05-15
2008-05-17
2008-05-19
2008-05-21
2008-05-23
2008-05-25
2008-05-27
2008-05-29
2008-05-31