## Instructions
Your Name: | Joe Andrusyszyn
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 0.5 |  | General Meeting
Y | 1.5 |  | Customer Meeting
Y | 2 |  | Team Meeting
Y | 1 |  | Write Project Synopsis
| 5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Customer Meeting
|  | 2 | Team Meeting
|  | 1 | Examine Customer XSDs
|  | 0.75 | Start thinking about project plan
|  | 5.75 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 2 | 1 | Examine Customer XSDs
Y | 0.5 | 0.75 | Start thinking about project plan
Y | 0.25 |  | Saturday Scrum
| 6.75 | 5.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 2 | Write Initial Project Plan
|  | 0.25 | Examine .Net tool 'XSD' to ensure it is appropriate
|  | 0.25 | Saturday Scrum
|  | 6.75 | TOTAL TIME
Issues
XSD wasn't as clear as expected, brought up many questions that need to be discussed with the customer

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 0.35 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
Y | 1.75 | 2 | Write Initial Project Plan
Y | 0.25 | 0.25 | Examine .Net tool 'XSD' to ensure it is appropriate
Y | 0.25 | 0.25 | Saturday Scrum
Y | 0.25 |  | Examine alternatives to .Net tool 'XSD'
| 6.85 | 6.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Scrums
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 2 | Teem Meeting
|  | 2 | Examine Customer XML files
|  | 7 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Scrums
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 2 | 2 | Teem Meeting
Y | 2 | 2 | Examine Customer XML files
N | 2 |  | Draw Potential Visual Representations
| 9 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Meeting With Pedersen
|  | 2 | Customer Meeting
|  | 2 | Team Meeting
|  | 4 | Draw Potential Visual Representations
|  | 9.25 | TOTAL TIME
Issues
Computer's Operating System got corrupted, had to get computer setup again

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Meeting With Pedersen
Y | 2 | 2 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 4 | 4 | Draw Potential Visual Representations
| 9.25 | 9.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 2 | Team Meeting
|  | 5 | Technical Risk Analysis & Prototyping
|  | 9.75 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1 | 1.5 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 5.5 | 5 | Technical Risk Analysis & Prototyping
Y | 1.75 |  | Second Team Meeting
| 11.5 | 9.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 2 | Team Meeting
|  | 4 | Assist with SRS
|  | 2 | Start more solid design
|  | 10.75 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.75 | 0.5 | Meeting with Pedersen
Y | 1.25 | 1.5 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 4 | 4 | Assist with SRS
N | 0 | 2 | Start more solid design
Y | 1 |  | Assist with prototypes
| 9.75 | 10.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 2 | Team Meeting
|  | 6 | Design
|  | 10.75 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.75 | Scrums
Y | 0.75 | 0.5 | Meeting with Pedersen
Y | 0.75 | 1.5 | Customer Meeting
Y | 3 | 2 | Team Meeting
N | 3.5 | 6 | Design
Y | 1 |  | SRS
| 9.5 | 10.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 2 | Customer Meeting and/or Team Meeting
|  | 2 | Team Meeting
|  | 6 | Overall System State Diagram
|  | 2 | Sequence Diagrams
|  | 12.75 | TOTAL TIME
Issues
Unexpected schedule changes made computer access limited, so more time was focused elsewhere

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 0..75 | 0.75 | Scrums
Y | 2 | 2 | Customer Meeting and/or Team Meeting
Y | 1.5 | 2 | Team Meeting
N | 6 | 6 | Overall System State Diagram
N | 3.5 | 2 | Sequence Diagrams
N | 1.5 |  | Class Diagrams
| 14.5 | 12.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 4 | Project Presentations
|  | 3 | Presentation Preparations
|  | 5 | Overall System State Diagram
|  | 2 | Sequence Diagrams
|  | 1 | Class Diagrams
|  | 15.75 | TOTAL TIME
Issues

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 4 | 4 | Project Presentations
Y | 4 | 3 | Presentation Preparations
N | 3 | 5 | Overall System State Diagram
N | 0.5 | 2 | Sequence Diagrams
N | 0.25 | 1 | Class Diagrams
Y | 1.5 |  | Team Evaluation
| 14 | 15.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Scrums
|  | 5 | Overall System State Diagrams
|  | 2 | Sequence Diagrams
|  | 1 | Class Diagrams
|  | 1 | Team Evaluation
|  | 9.5 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Scrums
N | 3 | 5 | Overall System State Diagrams
N | 0 | 2 | Sequence Diagrams
N | 0 | 1 | Class Diagrams
Y | 1 | 1 | Team Evaluation
| 4.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Meeting with Pedersen
|  | 4 | Finish State Diagrams
|  | 4 | Sequence and/or Class diagrams
|  | 3 | Team Meeting
|  | 0.5 | Customer Meeting
|  | 12.75 | TOTAL TIME
Issues
Lots of unexpected things came up during break that took away the time I was supposed to have

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Meeting with Pedersen
N | 2 | 4 | Finish State Diagrams
Y | 4 | 4 | Sequence and/or Class diagrams
Y | 3 | 3 | Team Meeting
Y | 1 | 0.5 | Customer Meeting
N | 1.5 |  | Release 1 coding
| 12.75 | 12.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 2 | Finish Release 1 coding
|  | 3 | Design Diagrams
|  | 5 | Release 2 coding/code reviews
|  | 2 | Release 1 testing
|  | 1.5 | Customer Meeting
|  | 2.5 | Team Meeting
|  | 16.75 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 3 | 2 | Finish Release 1 coding
Y | 3 | 3 | Design Diagrams
| 0.5 | 5 | Release 2 coding/code reviews
Y | 0.5 | 2 | Release 1 testing
Y | 0.5 | 1.5 | Customer Meeting
Y | 5 | 2.5 | Team Meeting
| 2 |  | Release 3 coding
| 15.25 | 16.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 0.5 | Project Poster Meeting
|  | 8 | Release 2 coding/code reviews
|  | 2 | XML Editor Control research
|  | 1 | Meeting with Pedersen
|  | 16.75 | TOTAL TIME
Issues
Why oh why does .Net not have a built in way to force proper ordering for XML objects when it is possible for schemas to require specific ordering?

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4.5 | 4 | Team Meeting
N | 0 | 0.5 | Project Poster Meeting
N | 6 | 8 | Release 2 coding/code reviews
Y | 2 | 2 | XML Editor Control research
Y | 1 | 1 | Meeting with Pedersen
Y | 5 |  | Release 3 & 4 work
| 19.75 | 16.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 0.5 | Project Poster Meeting
|  | 4 | Release 3 work
|  | 2 | Release 4 work
|  | 7 | Release 2 work
|  | 19.75 | TOTAL TIME
Issues
XML Editor control research resulted in no useable controls
Mixed up the week for the project poster meeting…
Mark was on a roll with Release 2 work, decided it was more efficient in the long run to put in more work for release 3 early and allow for release 2 to be a little later
Forgot that Release 3 was so limited, accidentally went ahead to Release 4 work

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 3 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 0.5 | 0.5 | Project Poster Meeting
Y | 4 | 4 | Release 3 work
N | 0 | 2 | Release 4 work
Y | 11.5 | 7 | Release 2 work
| 21.25 | 19.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 3 | Release 3 work
|  | 5 | Release 4 work
|  | 5 | General Code Cleanup
|  | 19.25 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 1 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
N | 11 | 3 | Release 3 work
N | 0 | 5 | Release 4 work
Y | 5 | 5 | General Code Cleanup
| 22.75 | 19.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 7 | Release 4 work
|  | 3 | Poster
|  | 3 | Release 3 work
|  | 19.25 | TOTAL TIME
Issues
Many unexpected hassles with Release 3 work

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 3.5 | 4 | Team Meeting
Y | 0.5 | 1 | Meeting with Pedersen
Y | 8 | 7 | Release 4 work
N | 2.5 | 3 | Poster
Y | 3 | 3 | Release 3 work
| 18.75 | 19.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 0.5 | Meeting with Pedersen
|  | 3 | Poster
|  | 10 | Release 4 work
|  | 18.75 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 3 | 4 | Team Meeting
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 3 | 3 | Poster
Y | 11 | 10 | Release 4 work
| 18.75 | 18.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 2 | Team Meeting
|  | 0.5 | Meeting with Pedersen
|  | 10 | Release 4 work
|  | 2 | User Guide
|  | 4.5 | Poster Presentations
|  | 20.25 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 10 | 10 | Release 4 work
Y | 2 | 2 | User Guide
Y | 4.5 | 4.5 | Poster Presentations
| 20.25 | 20.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 3 | Team Meeting
|  | 7 | Bug Fixes
|  | 5 | User Guide
|  | 3 | Final Presentation Prep
|  | 19.25 | TOTAL TIME
Issues
Very confused as to how I managed to hit all my estimates…

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 1 | 0.5 | Customer Meeting
Y | 1 | 3 | Team Meeting
Y | 6 | 7 | Bug Fixes
Y | 5 | 5 | User Guide
Y | 3.5 | 3 | Final Presentation Prep
| 17.25 | 19.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 4 | Presentations
|  | 0.5 | Customer Meeting
|  | 8 | Bug Fixes
|  | 3 | User Guide
|  | 16.25 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 4 | 4 | Presentations
Y | 0.5 | 0.5 | Customer Meeting
Y | 3 | 8 | Bug Fixes
Y | 1 | 3 | User Guide
| 9.25 | 16.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Post-mortem
|  | 2 | Self assessment
|  | 1 | User Guide
|  | 2 | Code cleanup
|  | 1 | Last bug
|  | 8 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Post-mortem
Y | 2 | 2 | Self assessment
Y | 1 | 1 | User Guide
Y | 1.5 | 2 | Code cleanup
Y | 1 | 1 | Last bug
| 7.5 | 8 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem