## Instructions
Your Name: | Mark Bryant
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
x | 0.5 |  | Kickoff meeting
x | 1 |  | Client meeting
x | 2 |  | Team meeting
x | 6 |  | Set up project server
x | 0.5 |  | MS Project Server (examine)
| 10 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Set up project website
|  | 0.5 | Set up CVS repository
|  | 0.5 | Set up internal project wiki
|  | 1 | Client meeting
|  | 2 | Team meeting
|  | 6 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
x | 3.5 | 2 | Set up project website
x | 0.5 | 0.5 | Set up CVS repository
x | 0.25 | 0.5 | Set up internal project wiki
x | 1 | 1 | Client meeting
x | 2 | 2 | Team meeting
| 0 | 0.25 | Saturday Scrum
| 7.25 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client meeting
|  | 2 | Team meeting
|  | 2 | First draft of project plan
|  | 0.25 | Website updates (meeting minutes and effort tracking)
|  | 0.25 | Project server backups
|  | 0.1 | Wiki updates (meeting notes)
|  | 5.6 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Client meeting
x | 2 | 2 | Team meeting
x | 1.5 | 2 | First draft of project plan
x | 0.5 | 0.25 | Website updates (meeting minutes and effort tracking)
x | 0.25 | 0.25 | Project server backups
x | 0.1 | 0.1 | Wiki updates (meeting notes)
x | 0.3 |  | Saturday Scrum
| 5.65 | 5.6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
x | 1 |  | Client Meeting
x | 2 |  | Team Meeting
x | 0.25 |  | Saturday Scrum
x | 1 |  | Installation of CVS client and Office software on server
x | 0.5 |  | Website updates
x | 0.25 |  | Project server backups
x | 0.25 |  | Wiki updates (meeting notes)
x | 1 |  | Visualization brainstorming
| 6.25 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Client Meeting
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 0.5 | Website and wiki updates
|  | 0.25 | Project server backups
|  | 8 | Freeform throwaway prototype
|  | 13 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
x | 2.25 | 2 | Client Meeting
x | 2 | 2 | Team Meeting
x | 0.25 | 0.25 | Saturday Scrum
x | 0.5 | 0.5 | Website and wiki updates
x | 0.25 | 0.25 | Project server backups
x | 6.5 | 8 | Freeform throwaway prototype
| 11.75 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 7 | Extended freeform throwaway prototype
|  | 0.25 | Project server backups
|  | 0.25 | Website and wiki updates
|  | 10.75 | TOTAL TIME
Issues

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Client Meeting
x | 2 | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
x | 5 | 7 | Extended freeform throwaway prototype
x | 0.25 | 0.25 | Project server backups
x | 0.25 | 0.25 | Website and wiki updates
x | 4 |  | New Project Schedule
| 12.5 | 10.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 2 | Finish last freeform prototype
|  | 0.25 | Project server backups
|  | 0.5 | Website and wiki updates
|  | 3 | Requirements Document
|  | 9 | TOTAL TIME
Issues
Had an emergency over the weekend, so I was unable to attend Saturday's meeting. I will make up the effort on Monday night.

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Client Meeting
| 2 | 2 | Team Meeting
| 0.25 | 0.25 | Saturday Scrum
| 5 | 2 | Finish last freeform prototype
| 0.25 | 0.25 | Project server backups
| 0.75 | 0.5 | Website and wiki updates
| 1 | 3 | Requirements Document
| 2 | 0 | Project schedule (MS Project)
| 12.25 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 0.25 | Project server backups
|  | 0.5 | Website and wiki updates
|  | 1.5 | Installation of software on project server
|  | 2 | Scrum project artifacts
|  | 7.5 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Client Meeting
x | 2.5 | 2 | Team Meeting
x | 0.25 | 0.25 | Saturday Scrum
x | 0.25 | 0.25 | Project server backups
x | 0.5 | 0.5 | Website and wiki updates
x | 2.5 | 1.5 | Installation of software on project server
| 1 | 2 | Scrum project artifacts
| 8 | 7.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 0.25 | Project server backups
|  | 0.5 | Website and wiki updates
|  | 1 | Scrum project artifacts
|  | 3 | Prototype development
|  | 8 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Client Meeting
x | 2 | 2 | Team Meeting
x | 0.25 | 0.25 | Saturday Scrum
x | 0.25 | 0.25 | Project server backups
| 0.5 | 0.5 | Website and wiki updates
| 0 | 1 | Scrum project artifacts
| 1 | 3 | Prototype development
| 5 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Presentation prep
|  | 4 | Presentations
|  | 0.25 | Saturday Scrum
|  | 0.25 | Project server backups
|  | 0.5 | Website and wiki updates
|  | 3 | Prototype development
|  | 10 | TOTAL TIME
Issues
Other class projects are starting to press into my effort for the project. I expect these conflicts to end by Thursday of week 10.

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Presentation prep
| 4 | 4 | Presentations
| 0.25 | 0.25 | Saturday Scrum
| 0.25 | 0.25 | Project server backups
| 0.5 | 0.5 | Website and wiki updates
| 0.5 | 3 | Prototype development
| 3 |  | Team Self-Evaluation
| 10.5 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Prototype Development
|  | 4 | Test Plan
|  | 0.25 | Project server backups
|  | 1 | Website and wiki updates
|  | 1 | Team eval meeting
|  | 9.25 | TOTAL TIME
Issues
Prototype and test plan work pushed back, since all exams are at the start of exam week

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 2 | 3 | Prototype Development
X | 10 | 4 | Test Plan
X | 0.25 | 0.25 | Project server backups
| 0 | 1 | Website and wiki updates
X | 1 | 1 | Team eval meeting
| 13.25 | 9.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 1 | Client Meeting
|  | 3 | Team Meetings
|  | 0.25 | Saturday Scrum
|  | 1 | Prototypes
|  | 2 | Design Activities
|  | 1.5 | Project server manual backups and automated backup mechanism
|  | 9.75 | TOTAL TIME
Issues
(Ongoing) Spring quarter schedule is very packed and will leave little room for schedule fluctuations

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 1 | Website and wiki updates
| 1 | 1 | Client Meeting
| 4.5 | 3 | Team Meetings
| 0.25 | 0.25 | Saturday Scrum
| 1 | 1 | Prototypes
| 1 | 2 | Design Activities
| 1.5 | 1.5 | Project server manual backups and automated backup mechanism
| 9.75 | 9.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 1 | Client meeting
|  | 4 | Team Meetings
|  | 1.5 | Prototype updates
|  | 2 | Design Activities
|  | 4 | UI Development
|  | 13.5 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
y | 1 | 1 | Website and wiki updates
y | 1 | 1 | Client meeting
y | 4 | 4 | Team Meetings
y | 1 | 1.5 | Prototype updates
n | 1 | 2 | Design Activities
n | 3 | 4 | UI Development
| 11 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 1 | Client meeting
|  | 4 | Team meetings
|  | 15 | UI Development
|  | 21 | TOTAL TIME
Issues

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
y | 1 | 1 | Website and wiki updates
y | 0.5 | 1 | Client meeting
y | 4 | 4 | Team meetings
n | 18 | 15 | UI Development
| 23.5 | 21 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 1 | Client meeting
|  | 4 | Team meetings
|  | 15 | UI Development
|  | 21 | TOTAL TIME
Issues
Lost some work on UI development earlier in the week. Had to start over, but caught up quick.

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
y | 0.5 | 1 | Website and wiki updates
y | 1 | 1 | Client meeting
y | 4 | 4 | Team meetings
y | 15 | 15 | UI Development
| 20.5 | 21 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 4 | Metrics/Measurements
|  | 10 | R3 Coding
|  | 4 | Team meetings
|  | 1 | Client meeting
|  | 20 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
n | 0.5 | 1 | Website and wiki updates
y | 3 | 4 | Metrics/Measurements
n | 9 | 10 | R3 Coding
y | 3 | 4 | Team meetings
y | 1 | 1 | Client meeting
| 16.5 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 3 | R3 Touchups
|  | 4 | R4 Coding
|  | 3 | Project Poster
|  | 4 | Team Meetings
|  | 1 | Client Meeting
|  | 16 | TOTAL TIME
Issues

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
y | 1 | 1 | Website and wiki updates
y | 2 | 3 | R3 Touchups
n | 3 | 4 | R4 Coding
y | 2 | 3 | Project Poster
y | 4 | 4 | Team Meetings
y | 1 | 1 | Client Meeting
| 13 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Website and wiki updates
|  | 0.5 | Server backups
|  | 6 | R4 Coding
|  | 5 | Team Meetings
|  | 1 | Client Meeting
|  | 13.5 | TOTAL TIME
Issues

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
y | 1 | 1 | Website and wiki updates
y | 0.5 | 0.5 | Server backups
n | 3 | 6 | R4 Coding
y | 3 | 5 | Team Meetings
y | 1 | 1 | Client Meeting
| 8.5 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Finish R4
|  | 0.5 | Client Meeting
|  | 7 | Team Meetings
|  | 1 | Website and Wiki Updates
|  | 0.5 | Server Backups
|  | 19 | TOTAL TIME
Issues
Senioritis
Had to leave town for most of weekend to help with family issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
y | 17 | 10 | Finish R4
y | 0.5 | 0.5 | Client Meeting
y | 5 | 7 | Team Meetings
n | 0 | 1 | Website and Wiki Updates
y | 0.5 | 0.5 | Server Backups
| 23 | 19 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 5 | Team Meetings
|  | 1 | Website/wiki updates
|  | 3 | Metrics/measurements updates
|  | 1.5 | User Manual
|  | 2 | Presentation work
|  | 13.5 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
y | 1 | 1 | Client Meeting
y | 6 | 5 | Team Meetings
y | 0.25 | 1 | Website/wiki updates
n | 0 | 3 | Metrics/measurements updates
y | 1 | 1.5 | User Manual
y | 3 | 2 | Presentation work
| 11.25 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Final Presentations
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 5 | Application Installer
|  | 3 | Fixing Defects
|  | 15 | TOTAL TIME
Issues
Need to make time for projects in other classes during week 10

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
y | 4 | 4 | Final Presentations
y | 1 | 1 | Client Meeting
n | 0 | 2 | Team Meeting
n | 1 | 5 | Application Installer
n | 1 | 3 | Fixing Defects
| 7 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Application Installer
|  | 3 | Metrics/Measurements
|  | 3 | Final Website Updates
|  | 2 | Fixing Defects
|  | 1 | Final Team Meeting
|  | 3 | Burn DVDs for team, client, Vallino, and Pedersen
|  | 16 | TOTAL TIME
Issues

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
y | 3 | 4 | Application Installer
y | 2 | 3 | Metrics/Measurements
y | 2 | 3 | Final Website Updates
y | 0.5 | 2 | Fixing Defects
y | 1.25 | 1 | Final Team Meeting
y | 3 | 3 | Burn DVDs for team, client, Vallino, and Pedersen
| 11.75 | 16 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem