## Instructions
Your Name: | Brian Hannan
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W_Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 0.5 |  | Kickoff meeting
Y | 1 |  | Client meeting
Y | 2 |  | Team meeting
Y | 0.5 |  | Emails – team communication
Y | 1 |  | Emails – database options
N | 3.5 |  | Setup Windows XP on home machine
Y | 0.5 |  | Project plan sections research
| 9 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Customer Meeting
|  | 2 | Team Meeting
|  | 1 | Project plan brainstorming
|  | 2 | Try to install Oracle on Scrumware server
|  | 3 | Finish setting up Windows XP on home machine
|  | 10 | TOTAL TIME
Issues
Having troubles installing Windows XP on new SATA RAID hard drive

## W_Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Customer Meeting
Y | 2 | 2 | Team Meeting
Y | 1 | 1 | Project plan brainstorming
N | 0 | 2 | Try to install Oracle on Scrumware server
Y | 4 | 3 | Finish setting up Windows XP on home machine
| 9 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 2 | Write Initial Project Plan
|  | 0.25 | Saturday Scrum
|  | 2 | Try to install Oracle on Scrumware server
|  | 8.5 | TOTAL TIME
Issues
Windows XP troubles lead to not being able to try Oracle this week

## W_Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 0.25 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
Y | 6 | 2 | Write Initial Project Plan
Y | 0.25 | 0.25 | Saturday Scrum
N | 0 | 2 | Try to install Oracle on Scrumware server
| 10.5 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 2 | Try to install Oracle on Scrumware server (over break if able)
|  | 2 | Start working on SRS document
|  | 8.5 | TOTAL TIME
Issues

## W_Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 0.25 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
Y | 0.25 | 0.25 | Saturday Scrum
N | 0 | 2 | Try to install Oracle on Scrumware server (over break if able)
Y | 4.5 | 2 | Start working on SRS document
| 9 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 2 | Begin C# tutorials and writing simple code
|  | 2 | Continue working on SRS document
|  | 8.5 | TOTAL TIME
Issues
|  |  | Do not have licensed version of Windows on my machine so I do not want to install .NET if I just have to reinstall in 12 days. I would need to find time to make it to the SE labs to work on C# for now. | Low
|  |  | Our focus is more on requirements right now and not interfacing with an Oracle database as we might not even really need to do this in our project if we don't have time. Installation of the Oracle database is being delayed until there is more time or we see that it is absolutely necessary. | Medium

## W_Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 0.25 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
N | 0 | 0.25 | Saturday Scrum
N | 0 | 2 | Continue working on SRS document
| 4.25 | 6.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 2 | Continue working on SRS especially use case diagram, use cases, state transition diagrams for UI, which will all lead to more in depth feature descriptions
|  | 2 | Continue working on Project Plan with Sprint Schedule Updated
|  | 8.5 | TOTAL TIME
Issues
Other classes and commitments are starting to build as the quarter goes on and I have less and less time to work on Senior Project than I did at the beginning.

## W_Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 0 | 0.5 | Meeting with Pedersen
N | 0 | 1.5 | Customer Meeting
N | 0 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
Y | 0.25 | 0.25 | Saturday Scrum
Y | 4 | 2 | Continue working on SRS especially use case diagram, use cases, state transition diagrams for UI, which will all lead to more in depth feature descriptions
N | 0 | 2 | Continue working on Project Plan with Sprint Schedule Updated
| 6.25 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 4 | Continue working on SRS especially use case diagram, use cases, state transition diagrams for UI, which will all lead to more in depth feature descriptions
|  | 2 | Continue working on Project Plan with Sprint Schedule Updated
|  | 10.5 | TOTAL TIME
Issues
I'm waiting for Mark to finish the project schedule in project as we have pushed it away from me to him as he has more experience.

## W_Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
X | 0.5 | 0.5 | Meeting with Pedersen
X | 1.5 | 1.5 | Customer Meeting
X | 0.25 | 0.25 | Post-Customer Meeting Scrum
X | 2 | 2 | Team Meeting
X | 0.25 | 0.25 | Saturday Scrum
X | 2 | 4 | Continue working on SRS especially use case diagram, use cases, state transition diagrams for UI, which will all lead to more in depth feature descriptions
X | 2 | 2 | Continue working on Project Plan with Sprint Schedule Updated
| 8.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 1 | Add state transition diagrams to Visio
|  | 0.5 | Create burn down chart
|  | 1.5 | Start working on adding estimates and actual times for sprint activities
|  | 7.5 | TOTAL TIME
Issues
None

## W_Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 | 0.5 | Meeting with Pedersen
Y | 1.5 | 1.5 | Customer Meeting
Y | 0.25 | 0.25 | Post-Customer Meeting Scrum
Y | 2 | 2 | Team Meeting
Y | 0.25 | 0.25 | Saturday Scrum
N | 0 | 1 | Add state transition diagrams to Visio
Y | 3 | 0 | Start thinking about design.
Y | 4 | 1.5 | Start working on adding estimates and actual times for sprint activities
| 11.5 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meeting with Pedersen
|  | 1.5 | Customer Meeting
|  | 0.25 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting
|  | 0.25 | Saturday Scrum
|  | 1 | Add state transition diagrams to Visio
|  | 1 | Update sprint schedule to reflect any new changes
|  | 4 | Start working on design
|  | 10.5 | TOTAL TIME
Issues
None.

## W_Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 1.5 | 1.5 | Customer Meeting
| 0.25 | 0.25 | Post-Customer Meeting Scrum
| 2 | 2 | Team Meeting
| 0.25 | 0.25 | Saturday Scrum
| 0 | 1 | Add state transition diagrams to Visio
| 1 | 1 | Update sprint schedule to reflect any new changes
| 1.5 | 2 | Start presentation
| 6.5 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | Customer Meeting
|  | 0 | Post-Customer Meeting Scrum
|  | 2 | Team Meeting - presentation
|  | 3.5 | Attend presentations
|  | 0.5 | Do presentation
|  | 0.25 | Saturday Scrum
|  | 1 | Update sprint schedule to reflect any new changes
|  | 7.25 | TOTAL TIME
Issues

## W_Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | Customer Meeting
| 0 | 0 | Post-Customer Meeting Scrum
| 2.5 | 2 | Team Meeting - presentation
| 3.5 | 3.5 | Attend presentations
| 0.5 | 0.5 | Do presentation
|  | 0.25 | Saturday Scrum
|  | 1 | Update sprint schedule to reflect any new changes
| 6.5 | 7.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Quarter Review
|  | 0.25 | Scrum Meeting
|  | 3 | Test Plan
|  | 3 | Design
|  | 7.25 | TOTAL TIME
Issues

## W_Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 1 | Quarter Review
|  | 0.25 | Scrum Meeting
|  | 3 | Test Plan
|  | 3 | Design
| 0 | 7.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Faculty Meeting
|  | 0.5 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum
|  | 1 | Test Plan
|  | 6 | Design Activities
|  | 11 | TOTAL TIME
Issues

## S_Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Faculty Meeting
| 0.5 | 0.5 | Client Meeting
| 2 | 2 | Team Meeting
| 0.5 | 0.5 | Scrum
| 0 | 1 | Test Plan
| 10 | 6 | Design Activities
| 14 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 2 | Updating Schedule for April and May
|  | 3 | Release 2 design diagrams
|  | 4 | Drag and Drop functionality research, design, experimenting
|  | 1 | Create slippage chart
|  | 1.5 | Customer Meeting
|  | 2.5 | Team Meeting
|  | 14.75 | TOTAL TIME
Issues
None

## S_Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 2 | Updating Schedule for April and May
Y | 0 | 3 | Release 2 design diagrams
Y | 0.5 | 4 | Drag and Drop functionality research, design, experimenting
Y | 1 | 1 | Create slippage chart
Y | 1.5 | 1.5 | Customer Meeting
Y | 2.5 | 2.5 | Team Meeting
| 6.75 | 14.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 0.5 | Project Poster Meeting
|  | 8 | Release 2 coding/code reviews
|  | 1 | Meeting with Pedersen
|  | 14.75 | TOTAL TIME
Issues

## S_Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 0.5 | 0.5 | Project Poster Meeting
Y | 6 | 8 | Release 2 coding/code reviews
Y | 1 | 1 | Meeting with Pedersen
| 12.75 | 14.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 0.5 | Project Poster Meeting
|  | 2 | Release 3 work
|  | 8 | Release 2 work
|  | 16.75 | TOTAL TIME
Issues

## S_Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 1 | 1 | Meeting with Pedersen
Y | 0.5 | 0.5 | Project Poster Meeting
Y | 0.5 | 2 | Release 3 work
Y | 6 | 8 | Release 2 work
| 8.75 | 12.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 6 | Release 3 work
|  | 2 | Release 4 work
|  | 1 | General Code Cleanup
|  | 15.25 | TOTAL TIME
Issues

## S_Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 2 | 6 | Release 3 work
Y | 4 | 2 | Release 4 work
N | 0 | 1 | General Code Cleanup
| 12.25 | 15.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 7 | Release 3 work
|  | 2 | Bug Fixes
|  | 15.25 | TOTAL TIME
Issues

## S_Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 6 | 7 | Release 3 work
Y | 3 | 2 | Bug Fixes
| 15.25 | 15.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 6 | Release 3 work
|  | 4 | Bug Fixes
|  | 16.25 | TOTAL TIME
Issues

## S_Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 4 | 6 | Release 3 work
Y | 5 | 4 | Bug Fixes
| 15.25 | 16.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 8 | Bug Fixes
|  | 14.25 | TOTAL TIME
Issues

## S_Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 12 | 8 | Bug Fixes
| 18.25 | 14.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 8 | Final Release Work
|  | 14.25 | TOTAL TIME
Issues

## S_Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 6 | 8 | Final Release Work
| 12.25 | 14.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 5 | Final Release Cleanup Work
|  | 2 | Final Presentation Work
|  | 13.25 | TOTAL TIME
Issues

## S_Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 4 | 5 | Final Release Cleanup Work
Y | 3 | 2 | Final Presentation Work
| 13.25 | 13.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.75 | Scrums
|  | 0.5 | Customer Meeting
|  | 4 | Team Meeting
|  | 1 | Meeting with Pedersen
|  | 5 | Final Release Cleanup Work
|  | 2 | Technical Report
|  | 13.25 | TOTAL TIME
Issues

## S_Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 0.75 | 0.75 | Scrums
Y | 0.5 | 0.5 | Customer Meeting
Y | 4 | 4 | Team Meeting
Y | 1 | 1 | Meeting with Pedersen
Y | 4 | 4 | Final Release Cleanup Work
Y | 2 | 2 | Technical Report
| 12.25 | 12.25 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem