## Instructions
Your Name: | Robert Songer
Instructions
Fill in your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done
Add any other tasks you worked on this week
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate how many minutes you will spend on each task
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## W-Wk1
Winter - Week 1
Accomplished this week
Done? | ACT |  | Task
x | 0.5 |  | Kick-Off Meeting
x | 1 |  | Client Meeting
x | 2 |  | Team Meeting (roles and responsibilities, team name, process)
x | 1 |  | Week 2 Client Meeting Agenda
x | 0.5 |  | E-mail Communication
| 5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 2 | Team Meeting (process, methodology, risks, scope)
|  | 0.5 | Week 3 Client Meeting Agenda
|  | 2 | Test Suite Tools Research
|  | 5.5 | TOTAL TIME
Issues

## W-Wk2
Winter - Week 2
Accomplished this week
Done? | ACT | EST | Task
x |  | 1 | Client Meeting
x |  | 2 | Team Meeting (process, methodology, risks, scope)
|  | 0.5 | Week 3 Client Meeting Agenda
|  | 2 | Test Suite Tools Research
x |  | 0.25 | Saturday Scrum
x |  | 1 | Coach Meeting
| 0 | 6.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Client Meeting
|  | 1 | Coach Meeting
|  | 2 | Team Meeting (Project Planning document)
|  | 0.5 | Week 4 Client Meeting Agenda
|  | 2 | Project Planning document draft
|  | 6.5 | TOTAL TIME
Issues

## W-Wk3
Winter - Week 3
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Client Meeting
x | 1 | 2 | Team Meeting (Project Planning document)
| 0 | 0.5 | Week 4 Client Meeting Agenda
x | 2 | 2 | Project Planning document draft
| 1 |  | Testing Tools Prep
x | 0.5 |  | Scrum Meetings
| 5.5 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 4 Client Meeting Agenda
|  | 1 | Client Meeting
|  | 2 | Team Meeting (Requirements)
|  | 0.5 | Week 5 Client Meeting Agenda
|  | 0.5 | Scrum Meetings
|  | 4.5 | TOTAL TIME
Issues
Due to the holiday break, the Week 4 Agenda will be written at the start of Week 4 to account for any issues arisen during the break.

## W-Wk4
Winter - Week 4
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 0.5 | Week 4 Client Meeting Agenda
x | 1 | 1 | Client Meeting
x | 2 | 2 | Team Meeting (Requirements)
|  | 0.5 | Week 5 Client Meeting Agenda
x | 0.5 | 0.5 | Scrum Meetings
| 2 |  | Requirements Document
x | 1.5 |  | System Features Outline
| 8 | 4.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 5 Client Meeting Agenda
|  | 0.5 | Faculty Meeting
|  | 1.5 | Team Meeting
|  | 2 | Client Meeting
|  | 0.5 | Scrum Meetings
|  | 4 | Requirements Document
|  | 9 | TOTAL TIME
Issues

## W-Wk5
Winter - Week 5
Accomplished this week
Done? | ACT | EST | Task
x | 0.25 | 0.5 | Week 5 Client Meeting Agenda
x | 1 | 0.5 | Faculty Meeting
x | 1 | 1.5 | Team Meeting
x | 2 | 2 | Client Meeting
x | 0.5 | 0.5 | Scrum Meetings
| 4.5 | 4 | Requirements Document
| 9.25 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Week 6 Client Meeting Agenda
|  | 1 | Faculty Meeting
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum Meetings
|  | 4 | Requirements Document
|  | 8.75 | TOTAL TIME
Issues
Project in another class due on Wednesday--may occupy my time

## W-Wk6
Winter - Week 6
Accomplished this week
Done? | ACT | EST | Task
x | 0.25 | 0.25 | Week 6 Client Meeting Agenda
x | 0.5 |  | Rough Deliverables Schedule
x | 1 | 1 | Faculty Meeting
x | 0.75 | 1 | Client Meeting
x | 0.75 | 2 | Team Meeting
x | 0.5 | 0.5 | Scrum Meetings
| 8 | 4 | Requirements Document
| 2 |  | SRS Review
| 13.75 | 8.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 7 Client Meeting Agenda
|  | 1 | Faculty Meeting
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum Meetings
|  | 4 | Requirements Document
|  | 4 | Test Plan
|  | 13 | TOTAL TIME
Issues

## W-Wk7
Winter - Week 7
Accomplished this week
Done? | ACT | EST | Task
s | 0.5 | 0.5 | Week 7 Client Meeting Agenda
x | 1 | 1 | Faculty Meeting
x | 1 | 1 | Client Meeting
x | 2 | 2 | Team Meeting
x | 0.5 | 0.5 | Scrum Meetings
| 6.5 | 4 | Requirements Document
| 1.5 | 4 | Test Plan
| 13 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 8 Client Meeting Agenda
|  | 1 | Faculty Meeting
|  | 1 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum Meetings
|  | 8 | Test Plan
|  | 1 | Requirements Document
|  | 14 | TOTAL TIME
Issues

## W-Wk8
Winter - Week 8
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 8 Client Meeting Agenda
x | 1 | 1 | Faculty Meeting
x | 0.5 | 1 | Client Meeting
x | 3 | 2 | Team Meeting
x | 0.5 | 0.5 | Scrum Meetings
| 5 | 8 | Test Plan
| 1 | 1 | Requirements Document
| 11.5 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum Meetings
|  | 6 | Test Plan
|  | 1 | Requirements Document
|  | 11.5 | TOTAL TIME
Issues

## W-Wk9
Winter - Week 9
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 2 | Client Meeting
x | 4.5 | 2 | Team Meeting
x | 0.5 | 0.5 | Scrum Meetings
| 3.5 | 6 | Test Plan
x | 1.5 | 1 | Requirements Document
| 11 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3.5 | Team Presentations
|  | 0.5 | Interim Presentation
|  | 2 | Team Meeting
|  | 1 | Evaluations
|  | 6 | Test Plan
|  | 13 | TOTAL TIME
Issues
Last week of classes → lots of work :(

## W-Wk10
Winter - Week 10
Accomplished this week
Done? | ACT | EST | Task
x | 3.5 | 3.5 | Team Presentations
x | 0.5 | 0.5 | Interim Presentation
x | 3 | 2 | Team Meeting
x | 0.5 | 1 | Evaluations
|  | 6 | Test Plan
x | 3 |  | Presentation Slideshow
| 10.5 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Quarter Review
|  | 0.25 | Scrum Meeting
|  | 6 | Test Plan
|  | 2 | Testing Framework
|  | 9.25 | TOTAL TIME
Issues

## W-Finals
Winter - Finals Week
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Quarter Review
| 0 | 0.25 | Scrum Meeting
| 6 | 6 | Test Plan
| 0 | 2 | Testing Framework
| 7 | 9.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Faculty Meeting
|  | 0.5 | Client Meeting
|  | 2 | Team Meeting
|  | 0.5 | Scrum
|  | 6 | Test Plan
|  | 2 | Design Activities
|  | 12 | TOTAL TIME
Issues

## S-Wk1
Spring - Week 1
Accomplished this week
Done? | ACT | EST | Task
x | 1 | 1 | Faculty Meeting
x | 0.5 | 0.5 | Client Meeting
x | 2 | 2 | Team Meeting
x | 0.5 | 0.5 | Scrum
x | 7.5 | 6 | Test Plan
| 1 | 2 | Design Activities
x | 0.5 |  | Week 1 Agenda
x | 0.75 |  | Sprint Planning
| 13.75 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 2 Agenda
|  | 1 | Client Meeting
|  | 4 | Team Meeting
|  | 0.5 | Scrum
|  | 6 | Testing Framework
|  | 1 | Slippage Chart
|  | 13 | TOTAL TIME
Issues

## S-Wk2
Spring - Week 2
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 2 Agenda
x | 0.5 | 1 | Client Meeting
x | 1.5 | 4 | Team Meeting
x | 0.5 | 0.5 | Scrum
| 10.5 | 6 | Testing Framework
| 1.5 | 1 | Slippage Chart
| 15 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 3 Agenda
|  | 0.5 | Client Meeting
|  | 1 | Coach Meeting
|  | 0.5 | Scrum
|  | 1 | Team Meeting
|  | 10 | Testing for R2
|  | 13.5 | TOTAL TIME
Issues
Time is always an issue.
Also, hyper-activity of the extracurricular kind.

## S-Wk3
Spring - Week 3
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 3 Agenda
x | 0.25 | 0.5 | Client Meeting
x | 1 | 1 | Coach Meeting
x | 0.5 | 0.5 | Scrum
x | 2 | 1 | Team Meeting
| 2.5 | 10 | Testing for R2
x | 0.5 |  | Requirements Coverage Chart
| 4 |  | Release 3 Implementation
| 11.25 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 4 Agenda
|  | 0.5 | Client Meeting
|  | 1 | Coach Meeting
|  | 0.5 | Scrum
|  | 1 | Technical Report and Poster Presentation
|  | 8 | Testing / Debugging
|  | 11.5 | TOTAL TIME
Issues

## S-Wk4
Spring - Week 4
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 4 Agenda
x | 0.25 | 0.5 | Client Meeting
x | 0.75 | 1 | Coach Meeting
x | 0.5 | 0.5 | Scrum
x | 0.5 | 1 | Technical Report and Poster Presentation
| 8 | 8 | Testing / Debugging
x | 2.5 |  | R2 Tooltips Implementation
| 0.5 |  | R3 Implementation
x | 1.5 |  | Sprint Wrap-Up / Planning
| 15 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 5 Agenda
|  | 0.75 | Client Meeting
|  | 0.75 | Coach Meeting
|  | 0.5 | Scrum
|  | 3 | R3 Implementation
|  | 8 | Testing / Debugging
|  | 13.5 | TOTAL TIME
Issues

## S-Wk5
Spring - Week 5
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 5 Agenda
x | 0.5 | 0.75 | Client Meeting
x | 0.75 | 0.75 | Coach Meeting
x | 0.15 | 0.5 | Scrum
| 5.5 | 3 | R3 Implementation
| 8.25 | 8 | Testing / Debugging
| 15.65 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Week 6 Agenda
|  | 0.25 | Client Meeting
|  | 0.75 | Coach Meeting
|  | 0.5 | Scrum
|  | 3 | R3 Implementation
|  | 5 | R4 Implementation
|  | 8 | Testing / Debugging
|  | 2 | Project Poster Creation
|  | 20 | TOTAL TIME
Issues
Project slippage hurts!

## S-Wk6
Spring - Week 6
Accomplished this week
Done? | ACT | EST | Task
x | 0.5 | 0.5 | Week 6 Agenda
x | 0.5 | 0.25 | Client Meeting
x | 0.5 | 0.75 | Coach Meeting
| 0.5 | 0.5 | Scrum
| 6.5 | 3 | R3 Implementation
|  | 5 | R4 Implementation
| 7 | 8 | Testing / Debugging
| 2.75 | 2 | Project Poster Creation
| 2.75 |  | Team Meeting
| 21 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Week 7 Agenda
|  | 0.25 | Client Meeting
|  | 0.75 | Coach Meeting
|  | 0.5 | Scrum
|  | 5 | R4 Implementation
|  | 8 | Testing / Debugging
|  | 2 | Project Poster Design
|  | 16.75 | TOTAL TIME
Issues
Vallino waited a week to give us less time for the poster.

## S-Wk7
Spring - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0.25 | 0.25 | Week 7 Agenda
| 0.3 | 0.25 | Client Meeting
| 0.7 | 0.75 | Coach Meeting
| 0.25 | 0.5 | Scrum
| 1.5 | 5 | R4 Implementation
| 9.5 | 8 | Testing / Debugging
| 3 | 2 | Project Poster Design
| 15.5 | 16.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Week 8 Agenda
|  | 0.25 | Client Meeting
|  | 0.75 | Coach Meeting
|  | 0.5 | Scrum
|  | 4 | R4 Bug Bash
|  | 8 | Testing /Debugging
|  | 5 | Project Poster Presentation
|  | 18.75 | TOTAL TIME
Issues

## S-Wk8
Spring - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0.25 | 0.25 | Week 8 Agenda
| 0.3 | 0.25 | Client Meeting
| 0.6 | 0.75 | Coach Meeting
| 0.1 | 0.5 | Scrum
|  | 4 | R4 Bug Bash
| 13.75 | 8 | Testing /Debugging
| 4.25 | 5 | Project Poster Presentation
| 19.25 | 18.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Week 9 Agenda
|  | 0.5 | Client Meeting
|  | 0.75 | Coach Meeting
|  | 0.5 | Scrum
|  | 12 | R4 Bug Bash
|  | 2 | User Manual
|  | 16 | TOTAL TIME
Issues

## S-Wk9
Spring - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 0.25 | Week 9 Agenda
| 1 | 0.5 | Client Meeting
| 0 | 0.75 | Coach Meeting
| 0 | 0.5 | Scrum
| 1 | 12 | R4 Bug Bash
|  | 2 | User Manual
| 3 |  | Final Presentation
| 1.5 |  | Team Meeting
| 7 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Final Presentation
|  | 3.5 | Final Presentation Viewing
|  | 2 | Automation Testing
|  | 2 | Final Assessment
|  | 2 | Technical Report
|  | 2 | Post Mortem
|  | 0.5 | Peer Evaluations
|  | 12.5 | TOTAL TIME
Issues

## S-Wk10
Spring - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 0.5 | Final Presentation
| 3.5 | 3.5 | Final Presentation Viewing
| 2.5 | 2 | Automation Testing
|  | 2 | Final Assessment
|  | 2 | Technical Report
|  | 2 | Post Mortem
|  | 0.5 | Peer Evaluations
| 0.65 |  | Client Meeting
| 0.5 |  | Debugging
| 7.15 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Post-Mortem
|  | 2 | Final Self-Assessment
|  | 2 | Wrap-up
|  | 6 | TOTAL TIME
Issues
Finals!

## S-Finals
Spring - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Post-Mortem
| 3 | 2 | Final Self-Assessment
| 1 | 2 | Wrap-up
| 6 | 6 | TOTAL TIME
Issues

## Example
Winter - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 20 | 30 | Read textbook about version control
Y | 45 | 30 | Set up subversion on my computer
N | 30 | 60 | Design error-handling subsystem
Y | 15 |  | Read good introduction to subversion on web
| 110 | 120 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 30 | Design error-handling subsystem
|  | 120 | Code error-handling subsystem
|  | 150 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem