## Feature List
Project Feature List
| Feature | Sub-Features | Who | Completed

## Example
Project Feature List
| Features | Sub-Features | Who | Completed
Record position of widget
|  | Initialize encoder | akc | week 1
|  | Read data from encoder | akc | week 1
|  | Compute widget position from encoder data | dgh | week 1
|  | Write widget position data to file | dgh | week 1
|  | Write Excel macro to process data into chart | jrr | week 2
Control valve opening
|  | Show selected control algorithm | akc | week 2
|  | Task executes periodically | dgh | week 2
|  | Show time difference equations for controller | akc | week 3
|  | Controller can be configured and outputs values | akc | week 3
|  | Controller drives valve motor | dgh | week 3
System controllable from user interface
Monitor system power demand
---
At the beginning of the project, identify the desired Project Features that the team would like to have. The team may want to list them in priority order.
Breakdown each Project Feature into smaller Sub-Features that are achievements the team will present as a demonstration of making progress completing the Project Feature. Phrase the Features and Sub-Features in terms of things that the team will demonstrate or show, rather than activities team members will do. Define Sub-Features which are small enough for a team member to easily accomplish in a few days. At that scale, each Project Feature will usually have three or more Sub-Features.
As you learn more about each Project Feature, you may add and delete Sub-Features. Each week, review the feature list, and update it as necessary. Each team member will select Sub-Features to work on as the project progresses.