## Instructions
Your Name: | #NoName!
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Regular team meeting
Y | 2 |  | Meeting with project sponsor
Y | 0.5 |  | Meeting with Bob
Y | 3 |  | Initial Project Research
Y | 0.5 |  | Establishment of team name
Y | 0.5 |  | Identifying initial questions for sponsor
| 8.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Start Team website
|  | 2 | Publish team documents on website
|  | 2 | Complete project information survey form
|  | 10 | TOTAL TIME
Issues
N/A

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
y | 2.5 | 2 | Regular team meeting
y | 2 | 2 | Meeting with project sponsor
y | 2 | 2 | Start Team website
y | 2 | 2 | Publish team documents on website
y | 1 | 2 | Complete project information survey form
y | 0.5 | 0.5 | Prepare Next meeting Power Point
y | 1 | 1 | Set up NetBeans
y | 0.5 | 0.5 | Update Synopsis
| 11.5 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Project Plan
|  | 1.5 | Review previous team deliverables
|  | 2 | Increment 1 Architecture
|  | 1 | Website tweaks
|  | 11 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 3 | 2.5 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Project Plan
Y | 1 | 1.5 | Review previous team deliverables
Y | 2.5 | 2 | Increment 1 Architecture
Y | 1 | 1 | Website tweaks
| 11.5 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | During break: Work on assigned deliverables
|  | 2 | Regular Team Meeting
|  | 2 | Meeting With Sponcer
|  | 4 | Integration of Individual work
|  | 1 | Assessment of Break work
|  | 14 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 5 | During break: Work on assigned deliverables
Y | 2 | 2 | Regular Team Meeting
Y | 2 | 2 | Meeting With Sponcer
Y | 4 | 4 | Integration of Individual work
Y | 1 | 1 | Assessment of Break work
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponcer Meeting
|  | 2 | Thursday Meeting: Discussing testing/documentation/Phase 2
|  | 5 | Finish Work on Assigned Phase 1 deliverables: Mailer/User Components
|  | 4 | Test Individual Components
|  | 2 | Phase 1 Documentation Deliverables: Client-Server View, Use Cases
|  | 15 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sponcer Meeting
Y | 2 | 2 | Thursday Meeting: Discussing testing/documentation/Phase 2
Y | 5 | 5 | Finish Work on Assigned Phase 1 deliverables: Mailer/User Components
Y | 4 | 4 | Test Individual Components
Y | 2 | 2 | Phase 1 Documentation Deliverables: Client-Server View, Use Cases
| 15 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Phase 2 Design
|  | 8 | Testing Phase 1
|  | 2 | Sponcer Meeting
|  | 2 | Phase 2 Documentation Updates
|  | 14 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Phase 2 Design
Y | 8 | 8 | Testing Phase 1
Y | 2 | 2 | Sponcer Meeting
Y | 2 | 2 | Phase 2 Documentation Updates
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Team Meeting
|  | 6 | Phase 2 Design Continued
|  | 6 | Phase 1 Testing Continued
|  | 16 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponcer
Y | 2.5 | 2 | Team Meeting
Y | 5 | 6 | Phase 2 Design Continued
Y | 7 | 6 | Phase 1 Testing Continued
| 16.5 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting With Sponcer
|  | 2 | Phase 2 Estimation Review
|  | 2 | Team Meeting
|  | 2 | First Quarter Presentation Creation
|  | 2 | Presentation Practice
|  | 6 | Phase 1 Testing Finish
|  | 16 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting With Sponcer
Y | 2 | 2 | Phase 2 Estimation Review
Y | 2 | 2 | Team Meeting
Y | 2 | 2 | First Quarter Presentation Creation
Y | 2 | 2 | Presentation Practice
Y | 5.5 | 6 | Phase 1 Testing Finish
| 15.5 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Presentation Practice
|  | 2 | Presentations: Day 1
|  | 2 | Presentations: Day 2
|  | 1 | Week 10 Discussions
|  | 2 | User/UserManager/Mailer Limit/Improper Usage Testing
|  | 8 | TOTAL TIME
Issues
This is kind of an off week for us. We gave our presentation which went well after a few minor technical difficulties.
Work on a team level will resume next week.

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Presentation Practice
Y | 2 | 2 | Presentations: Day 1
Y | 2 | 2 | Presentations: Day 2
Y | 1 | 1 | Week 10 Discussions
Y | 2 | 2 | User/UserManager/Mailer Limit/Improper Usage Testing
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Team Meeting - Thursday
|  | 5 | Phase 2 Implementation Begins - Extractors (me)
|  | 2 | Phase 2 Documentation Cleanup
|  | 2 | Schedule Assessment/Break Discussions
|  | 13 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponcer
Y | 2 | 2 | Team Meeting - Thursday
Y | 3 | 5 | Phase 2 Implementation Begins - Extractors (me)
Y | 2 | 2 | Phase 2 Documentation Cleanup
Y | 2 | 2 | Schedule Assessment/Break Discussions
| 11 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Unit Test Contruction
|  | 5 | Phase 2 Implementation Continuation (Extractors)
|  | 5 | Other coding/review/testing work for over break
|  | 15 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
N | 5 | 5 | Unit Test Contruction
N | 5 | 5 | Phase 2 Implementation Continuation (Extractors)
N | 5 | 5 | Other coding/review/testing work for over break
| 15 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Second Team Meeting
|  | 3 | Sunday Integration Meeting
|  | 3 | Unit Test Construction for Phase 1
|  | 2 | File I/O Class Construction
|  | 12 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponcer
Y | 2 | 2 | Second Team Meeting
Y | 3 | 3 | Sunday Integration Meeting
Y | 3 | 3 | Unit Test Construction for Phase 1
Y | 3 | 2 | File I/O Class Construction
| 13 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting With Sponcer
|  | 2 | Second Team Meeting
|  | 8 | Phase 2 Testing: General System testing/ File I/O / Regression Testing
|  | 2 | Sunday Meeting
|  | 14 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Meeting With Sponcer
y | 2 | 2 | Second Team Meeting
n | 8 | 8 | Phase 2 Testing: General System testing/ File I/O / Regression Testing
n | 0 | 2 | Sunday Meeting
| 12 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting With Sponcer
|  | 2 | Second Team Meeting
|  | 4 | Sunday Meeting (for sure)
|  | 3 | File IO finish up
|  | 6 | Leo Pair Programming
|  | 5 | Tests
|  | 22 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting With Sponcer
Y | 2 | 2 | Second Team Meeting
Y | 4 | 4 | Sunday Meeting (for sure)
Y | 3 | 3 | File IO finish up
N | 5 | 6 | Leo Pair Programming
N | 4 | 5 | Tests
| 20 | 22 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Metting with Sponcer
|  | 2 | Second Team meeting
|  | 4 | Sunday Meeting (possible)
|  | 5 | Continue work on Table Generation with Leo
|  | 5 | Continue Unit Test Writing
|  | 2 | Begin Looking at Scheduled Notifications
|  | 20 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Metting with Sponcer
Y | 2 | 2 | Second Team meeting
Y | 4 | 4 | Sunday Meeting (possible)
Y | 3 | 5 | Continue work on Table Generation with Leo
Y | 6 | 5 | Continue Unit Test Writing
Y | 2 | 2 | Begin Looking at Scheduled Notifications
| 19 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Second Team Meeting
|  | 5 | Continue Working on Scheduled Notifications
|  | 3 | Test Scheduled Notifications
|  | 2 | Begin Planning Poster
|  | 14 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponcer
Y | 2 | 2 | Second Team Meeting
Y | 5 | 5 | Continue Working on Scheduled Notifications
Y | 3 | 3 | Test Scheduled Notifications
Y | 2 | 2 | Begin Planning Poster
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Second Team Meeting
|  | 4 | Begin Linking Scheduled Notifications Backend to Frontend
|  | 2 | Test Through Website
|  | 5 | Work on Team Poster
|  | 15 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
N | 2 | 2 | Meeting with Sponcer
Y | 2 | 2 | Second Team Meeting
N | 3 | 4 | Begin Linking Scheduled Notifications Backend to Frontend
N | 1 | 2 | Test Through Website
Y | 6 | 5 | Work on Team Poster
| 14 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting With Sponcer
|  | 2 | Second Team Meeting
|  | 6 | Finish Scheduled Notifications
|  | 2 | Update Unit Tests
|  | 2 | Update Poster based on Feedback
|  | 14 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
y | 2 | 2 | Meeting With Sponcer
y | 2 | 2 | Second Team Meeting
n | 6 | 6 | Finish Scheduled Notifications
y | 2 | 2 | Update Unit Tests
y | 2 | 2 | Update Poster based on Feedback
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Second Team Meeting
|  | 4 | Continue Scheduled Notification testing
|  | 4 | Update Unit Tests
|  | 4 | Poster Demonstration
|  | 16 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
n | 2 | 2 | Meeting with Sponcer
n | 0 | 2 | Second Team Meeting
y | 4 | 4 | Continue Scheduled Notification testing
y | 4 | 4 | Update Unit Tests
y | 4 | 4 | Poster Demonstration
| 14 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponcer
|  | 2 | Second Team Meeting
|  | 5 | Finish Scheduled Notifications Front End Tie Up
|  | 4 | Documentation Updates
|  | 13 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponcer
Y | 2 | 2 | Second Team Meeting
Y | 4 | 5 | Finish Scheduled Notifications Front End Tie Up
Y | 3 | 4 | Documentation Updates
Y | 3 | 2 | Final Presentation Preparation
| 14 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Presentation Practice
|  | 0.5 | Final Presentation
|  | 1.5 | Senior Presentations Day 1
|  | 2 | Senior Presentations Day 2
|  | 2 | Scheduler testing
|  | 2 | Group Review
|  | 10 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Presentation Practice
Y | 0.5 | 0.5 | Final Presentation
Y | 1.5 | 1.5 | Senior Presentations Day 1
Y | 2 | 2 | Senior Presentations Day 2
Y | 2 | 2 | Scheduler testing
Y | 2 | 2 | Group Review
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Sponcer and Faculty Coach Final Meeting
|  | 5 | system Testing
|  | 4 | Documentation Review
|  | 11 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Sponcer and Faculty Coach Final Meeting
Y | 5 | 5 | system Testing
Y | 4 | 4 | Documentation Review
| 11 | 11 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8.5 | 12 | 11.5 | 11 | 11.5 | 14 | 14 | 15 | 15 | 14 | 14 | 16 | 16.5 | 16 | 15.5 | 8 | 8 | 13 | 11 | 15 | 15
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
12 | 13 | 14 | 12 | 22 | 20 | 20 | 19 | 14 | 14 | 15 | 14 | 14 | 14 | 16 | 14 | 15 | 14 | 10 | 10 | 11 | 11