## Instructions
Your Name: | #NoName!
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Regular team meeting
Y | 2 |  | Meeting with project sponsor
Y | 0.5 |  | Meeting with Bob
Y | 3 |  | Initial Project Research
Y | 0.5 |  | Establishment of team name
Y | 0.5 |  | Identifying initial questions for sponsor
| 8.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Start Team website
|  | 2 | Publish team documents on website
|  | 2 | Complete project information survey form
|  | 10 | TOTAL TIME
Issues
N/A

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2.5 | 2 | Start Team website
Y | 1 | 2 | Publish team documents on website
Y | 1 | 1 | Online meeting to prepare for week 3
Y | 1 | 1 | Set up tools required for project
Y | 1 |  | Create Team Logo
| 11 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 5 | Work on Project Plan
|  | 2 | Work on Team website
|  | 9 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Meeting with Project Sponsor
| 4 | 5 | Work on Project Plan
| 3.5 | 2 | Work on Team Website
| 1.5 |  | Read Over Previous Team Deliverables
| 11 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team (Includes Work on User Scenarios)
|  | 1.5 | Work on Team Website
|  | 3 | Work on UpdateUserServlet
|  | 1 | Work on Architecture Document
|  | 1 | Work on Project Webpages (Reorganization/Style)
|  | 1.3 | Work on Project Webpages (Menu/Status)
|  | 1 | Assist Leo and Nick with Project Setup
|  | 12.8 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team (Includes Work on User Scenarios)
Y | 1 | 1.5 | Work on Team Website
Y | 2 | 3 | Work on UpdateUserServlet
Y | 2.5 | 1 | Work on Architecture Document
Y | 1.5 | 1 | Work on Project Webpages (Reorganization/Style)
Y | 1.5 | 1.5 | Work on Project Webpages (Menu/Status)
Y | 2.3 | 1 | Assist Leo and Nick with Project Setup
| 14.8 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Team (Tuesday)
|  | 2 | Meeting with Team (Thursday)
|  | 1.5 | Work on Team Website
|  | 0.5 | Work on Submission Page
|  | 2.5 | Complete Script Checking (Alerts user if Javascript off) for all Pages
|  | 1 | Fixes/Additions to Architecture Document based on Bob/Dom's Feedback
|  | 3 | Work on Internet Explorer 7 and FireFox Compatibility/Style Issues
|  | 12.5 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Team (Tuesday)
Y | 2 | 2 | Meeting with Team (Thursday)
Y | 1.5 | 1.5 | Work on Team Website
Y | 0.5 | 0.5 | Work on Submission Page
Y | 2.5 | 2.5 | Complete Script Checking (Alerts user if Javascript off) for all Pages
Y | 1.25 | 1 | Fixes/Additions to Architecture Document based on Bob/Dom's Feedback
Y | 2 | 3 | Work on Internet Explorer 7 and FireFox Compatibility/Style Issues
| 11.75 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Internet Explorer 7 and FireFox Compatibility/Style Issues Cont
|  | 1.5 | Work on Team Website
|  | 1.5 | Style & JS for the top-right Menu to keep in theme with rest of pages
|  | 8.5 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
N | 0 | 2 | Meeting with Team
Y | 2.5 | 1.5 | Work on Internet Explorer 7 and FireFox Compatibility/Style Issues Cont
Y | 1.5 | 1.5 | Work on Team Website
Y | 2 | 1.5 | Style & JS for the top-right Menu to keep in theme with rest of pages
| 8 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 3 | Work on User List Page & Notifications Servlet
|  | 2 | Several minor fixes and/or additions for all Pages
|  | 2.5 | Research Jquery and AJAX to assist Dom
|  | 1 | Study BOE techniques in preparation for making a BOE presentation next week
|  | 1 | Work on Team Website
|  | 13.5 | TOTAL TIME
Issues
Team Meeting for Week 6 Cancelled

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 4 | 3 | Work on User List Page & Notifications Servlet
Y | 1.5 | 2 | Several minor fixes and/or additions for all Pages
Y | 2 | 2.5 | Research Jquery and AJAX to assist Dom
Y | 1 | 1 | Study BOE techniques in preparation for making a BOE presentation next week
Y | 1 | 1 | Work on Team Website
| 13.5 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1 | Create Basis of Estimate (BOE) Presentation for Will
|  | 1 | Work on Team Website
|  | 2 | Work on Mailer & Notifications
|  | 2 | Work on Validation Issues & White Pages
|  | 1 | Work on Presentation
|  | 11 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1 | 1 | Create Basis of Estimate (BOE) Presentation for Will
Y | 1 | 1 | Work on Team Website
Y | 3 | 2 | Work on Mailer & Notifications
Y | 2 | 2 | Work on Validation Issues & White Pages
Y | 1 | 1 | Work on Presentation
| 12 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Deliver Presentation & Watch Others (Tuesday)
|  | 2 | Watch Presentations (Thursday)
|  | 2 | Work on Presentation
|  | 1.5 | Add Logging/Error Handling to all Pages
|  | 3.5 | Validation Fixes for UserList & Validation additions to many other pages
|  | 2.5 | Implement TinyMCE for Textareas
|  | 1.5 | Moving Project to Team Server for Testing & Some testing
|  | 2 | Update Team Website & Fillout Presentation Evaluations
|  | 17 | TOTAL TIME
Issues
Computer Issues (Lost everything), had to set up the computer from scratch & reinstall all programs/drivers, took about 20 hours

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Deliver Presentation & Watch Others (Tuesday)
Y | 2 | 2 | Watch Presentations (Thursday)
Y | 1.5 | 2 | Work on Presentation
Y | 1.5 | 1.5 | Add Logging/Error Handling to all Pages
Y | 3.5 | 3.5 | Validation Fixes for UserList & Validation additions to many other pages
Y | 2.5 | 2.5 | Implement TinyMCE for Textareas
Y | 1.5 | 1.5 | Moving Project to Team Server for Testing & Some testing
Y | 2 | 2 | Update Team Website & Fillout Presentation Evaluations
| 16.5 | 17 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 2 | Work on Team Website (Includes Putting Files/Info up for Bob's Grading)
|  | 2 | Several bug fixes for Servlets and UserManager
|  | 2.5 | Add UserManager functionality (update user w/o password & delete user)
|  | 5 | Add Administrator Functionality (page & servlet)
|  | 15.5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 2 | 2 | Work on Team Website (Includes Putting Files/Info up for Bob's Grading)
Y | 2.5 | 2 | Several bug fixes for Servlets and UserManager
Y | 2.5 | 2.5 | Add UserManager functionality (update user w/o password & delete user)
Y | 6 | 5 | Add Administrator Functionality (page & servlet)
| 17 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Create Issue Page for Editors
|  | 1.5 | Work on Team Website
|  | 2.5 | Work on Interim Team Self-Assessment
|  | 1.5 | Work on Administration Page
|  | 8 | TOTAL TIME
Issues
No Meetings This Week

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 2.5 | 2.5 | Create Issue Page for Editors
Y | 1.5 | 1.5 | Work on Team Website
Y | 2.5 | 2.5 | Work on Interim Team Self-Assessment
Y | 1.5 | 1.5 | Work on Administration Page
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team (Thursday)
|  | 3 | Meeting with Team (Sunday), Work on NullPointer bug, Work on Issues
|  | 1 | Hunting down NullPointer bug (continued)
|  | 1.5 | Work on Team Website
|  | 1.5 | Various small bug fixes for servlets
|  | 11 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team (Thursday)
Y | 3 | 3 | Meeting with Team (Sunday), Work on NullPointer bug, Work on Issues
Y | 1 | 1 | Hunting down NullPointer bug (continued)
Y | 1.5 | 1.5 | Work on Team Website
Y | 1.5 | 1.5 | Various small bug fixes for servlets
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 1 | Bug Fix: Hints do not work pages with pre-validation.
|  | 3 | Bug Fix: Null Pointer bug
|  | 5 | Mailer Settings for Admins, so any mail account can be used for notifications
|  | 1 | Option for Admins to be CCed on all Notifications and Roles added to User List
|  | 1.5 | Update Submit Document Page to include Keywords and Abstracts & Validation for Numbers
|  | 17 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
Y | 1 | 1 | Bug Fix: Hints do not work pages with pre-validation.
Y | 3 | 3 | Bug Fix: Null Pointer bug
Y | 5 | 5 | Mailer Settings for Admins, so any mail account can be used for notifications
Y | 1 | 1 | Option for Admins to be CCed on all Notifications and Roles added to User List
Y | 1.5 | 1.5 | Update Submit Document Page to include Keywords and Abstracts & Validation for Numbers
| 17 | 17 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 1.5 | Select all functionality for User List
|  | 2 | Meeting with Team (Sunday)
|  | 2 | Bug Fixes for Admin Page and Mailer
|  | 11 | TOTAL TIME
Issues
Server up-time is now 6 days and counting due to Null Pointer bug fix.
I need to focus on GMAT preparation the next couple weeks, so I front-loaded my work.

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
Y | 5 | 1.5 | Select all functionality for User List
Y | 3 | 2 | Meeting with Team (Sunday)
Y | 2 | 2 | Bug Fixes for Admin Page and Mailer
| 15.5 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Wesite
|  | 3.5 | Added Phone Number, Address in all appropriate locations
|  | 2 | Meeting with Team (Sunday)
|  | 1 | Minor bug fixes to servlets, validation, and the like.
|  | 2.5 | Updates (From field) and Usability Stuff for Settings Page
|  | 14.5 | TOTAL TIME
Issues
GMAT Week Pushed Back One Week
Select all functionality was much more time consuming than expected.

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Wesite
Y | 3.5 | 3.5 | Added Phone Number, Address in all appropriate locations
Y | 3.5 | 2 | Meeting with Team (Sunday)
Y | 1 | 1 | Minor bug fixes to servlets, validation, and the like.
Y | 2.5 | 2.5 | Updates (From field) and Usability Stuff for Settings Page
| 16 | 14.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 5.5 | TOTAL TIME
Issues
New GMAT Week

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
N | N | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
| 3.5 | 5.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 4 | Transaction Logs
|  | 2 | Process Diagram
|  | 3 | Poster (Includes making process diagram pretty)
|  | 1 | General Commenting
|  | 15.5 | TOTAL TIME
Issues
Studied For/Took GMAT this week, no time for anything else.
Thursday meeting was cancelled for the entire team.

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
Y | 4 | 4 | Transaction Logs
Y | 2.5 | 2 | Process Diagram
Y | 2.5 | 3 | Poster (Includes making process diagram pretty)
Y | 1 | 1 | General Commenting
| 15.5 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 2 | Poster
|  | 2 | Transaction Log UI (added to admin page)
|  | 2 | Configure Tomcat To Allow Access To Resources Outside Deployment Folder
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
Y | 5 | 2 | Poster
Y | 2 | 2 | Transaction Log UI (added to admin page)
Y | 1 | 2 | Configure Tomcat To Allow Access To Resources Outside Deployment Folder
| 13.5 | 11.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 3 | Poster Day
|  | 1.5 | Work on Team Website
|  | 1 | Assist Dom with Document Submission
|  | 3 | Server / Content Configuration
|  | 10.5 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 3 | 3 | Poster Day
Y | 1.5 | 1.5 | Work on Team Website
Y | 1 | 1 | Assist Dom with Document Submission
Y | 3 | 3 | Server / Content Configuration
| 10.5 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Project Sponsor
|  | 2 | Meeting with Team
|  | 1.5 | Work on Team Website
|  | 3 | Server / Content Configuration, Validation Changes
|  | 8.5 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Project Sponsor
Y | 2 | 2 | Meeting with Team
Y | 1.5 | 1.5 | Work on Team Website
Y | 3 | 3 | Server / Content Configuration, Validation Changes
| 8.5 | 8.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Team (Monday)
|  | 2 | Presentations (Tuesday)
|  | 2 | Presentations (Thursday)
|  | 3 | Server / Content Configuration
|  | 1.5 | Work on Team Website
|  | 2 | Technical Report
|  | 12.5 | TOTAL TIME
Issues
Under severe time strain due to 3D Games

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Team (Monday)
Y | 2 | 2 | Presentations (Tuesday)
Y | 2 | 2 | Presentations (Thursday)
Y | 5 | 3 | Server / Content Configuration
Y | 1.5 | 1.5 | Work on Team Website
Y | 2 | 2 | Technical Report
| 14.5 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Reflection Meeting (Monday)
|  | 5 | Remaining Documentation
|  | 7 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| Y | 2 | Reflection Meeting (Monday)
| Y | 5 | Remaining Documentation
| 0 | 7 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8.5 | 14 | 11 | 9 | 11 | 13 | 14.8 | 12.5 | 11.75 | 8.5 | 8 | 13.5 | 13.5 | 11 | 12 | 17 | 16.5 | 15.5 | 17 | 8 | 8
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
11 | 11 | 17 | 17 | 11 | 15.5 | 14.5 | 16 | 5.5 | 3.5 | 15.5 | 15.5 | 11.5 | 13.5 | 10.5 | 10.5 | 8.5 | 8.5 | 12.5 | 14.5 | 7 | 0