## Instructions
Your Name: | #NoName!
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Regular team meeting
Y | 2 |  | Meeting with project sponsor
Y | 0.5 |  | Meeting with Bob
Y | 3 |  | Initial Project Research
Y | 0.5 |  | Establishment of team name
Y | 0.5 |  | Identifying initial questions for sponsor
| 8.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Start Team website
|  | 2 | Publish team documents on website
|  | 2 | Complete project information survey form
|  | 10 | TOTAL TIME
Issues
N/A

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 1 | 2 | Start Team website
Y | 1 | 2 | Publish team documents on website
Y | 1 | 2 | Complete project information survey form
| 7 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 5 | Research
|  | 9 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 5 | 5 | Research
| 9 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 6 | Research
|  | 2 | Documentation
|  | 2 | Planning
|  | 14 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 6 | 6 | Research
Y | 2 | 2 | Documentation
Y | 2 | 2 | Planning
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Documentation
|  | 1 | Additional Team meeting
|  | 4 | Initial development
|  | 11 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Documentation
Y | 1 | 1 | Additional Team meeting
Y | 4 | 4 | Initial development
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Documentation
|  | 3 | Development
|  | 3 | Testing
|  | 12 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Documentation
Y | 3 | 3 | Development
Y | 3 | 3 | Testing
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Documentation
|  | 2 | Development
|  | 4 | Testing
|  | 12 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Documentation
Y | 2 | 2 | Development
Y | 4 | 4 | Testing
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Documentation
|  | 2 | Development
|  | 6 | Testing
|  | 14 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Documentation
Y | 2 | 2 | Development
Y | 6 | 6 | Testing
| 14 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Team Presentation
|  | 2 | Regular team meeting
|  | 3 | Documentation
|  | 6 | Testing
|  | 13 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Team Presentation
Y | 2 | 2 | Regular team meeting
Y | 3 | 3 | Documentation
Y | 6 | 6 | Testing
| 13 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with sponsor
|  | 2 | Regular Team Meeting
|  | 3 | Documentation
|  | 5 | Testing
|  | 12 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with sponsor
Y | 2 | 2 | Regular Team Meeting
Y | 3 | 3 | Documentation
Y | 5 | 5 | Testing
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Testing
|  | 3 | Documentation
|  | 8 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Testing
|  | 3 | Documentation
|  | 8 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 8 | 8 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Regular Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Meeting with Sponsor
Y | 2 | 2 | Regular Meeting
Y | 5 | 5 | Testing
Y | 3 | 3 | Documentation
| 12 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Team Meeting
|  | 5 | Testing
|  | 3 | Documentation
|  | 12 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
|  | 2 | Meeting with Sponsor
|  | 2 | Team Meeting
|  | 5 | Testing
|  | 3 | Documentation
| 0 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8.5 | 10 | 7 | 9 | 9 | 14 | 14 | 11 | 11 | 12 | 12 | 12 | 12 | 14 | 14 | 13 | 13 | 12 | 12 | 8 | 8
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0