## Instructions
Your Name: | #NoName!
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 2 |  | Regular team meeting
Y | 2 |  | Meeting with project sponsor
Y | 0.5 |  | Meeting with Bob
Y | 3 |  | Initial Project Research
Y | 0.5 |  | Establishment of team name
Y | 0.5 |  | Identifying initial questions for sponsor
| 8.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 2 | Start Team website
|  | 2 | Publish team documents on website
|  | 2 | Complete project information survey form
|  | 10 | TOTAL TIME
Issues
N/A

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 2 | 2 | Regular team meeting
Y | 2 | 2 | Meeting with project sponsor
Y | 2 | 2 | Start Team website
Y | 2 | 2 | Publish team documents on website
Y | 2 | 2 | Complete project information survey form
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Phase plan development
|  | 6 | Phase 1 architecture
|  | 3 | Project plan work
|  | 2 | Note publishing
|  | 14 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Y | 3.5 | 3 | Phase plan development
Y | 6 | 6 | Phase 1 architecture
Y | 3 | 3 | Project plan work
Y | 2 | 2 | Note publishing
| 14.5 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | note publishing
|  | 15 | Document system implementation
|  | 5 | more detailed architecture for document system
|  | 22 | TOTAL TIME
Issues
working on some implementation will be done over break

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 1.5 | 2 | note publishing
| 12 | 15 | Document system implementation
| 3 | 5 | more detailed architecture for document system
| 16.5 | 22 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Use case diagrams
|  | 5 | Functional Requirements
|  | 4 | Further develop submission/document system JSP
|  | 2 | Further develop backend for document submission
|  | 2 | Moderate team meeting, take notes
|  | 1 | Publish notes
|  | 16 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Use case diagrams
| 5 | 5 | Functional Requirements
| 4 | 4 | Further develop submission/document system JSP
| 2 | 2 | Further develop backend for document submission
| 2 | 2 | Moderate team meeting, take notes
| 0 | 1 | Publish notes
| 4 |  | Archtectural Document work, package view
| 19 | 16 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Test/Finish document module for Phase 1
|  | 2 | Moderate team meeting, take notes
|  | 1 | Publish notes
|  | 2 | Begin test plan
|  | 3 | Begin table generation coding
|  | 12 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 7 | 4 | Test/Finish document module for Phase 1
| 2 | 2 | Moderate team meeting, take notes
| 1 | 1 | Publish notes
| 0 | 2 | Begin test plan
| 0 | 3 | Begin table generation coding
| 10 | 12 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Continue testing of Phase1
|  | 2 | Moderate team meeting, take notes
|  | 1 | Publish notes
|  | 1 | Test plan discussion
|  | 2 | Initial work on test plan
|  | 3 | Updates to architectural doc/SRS
|  | 11 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Continue testing of Phase1
| 4 | 2 | Moderate team meeting, take notes
| 1 | 1 | Publish notes
| 1 | 1 | Test plan discussion
| 0.5 | 2 | Initial work on test plan
| 2 | 2 | Estimates work
| 4 | 4 | Transaction Log implementation
| 2 |  | User manual
| 16.5 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Release Phase 1
|  | 2 | Update srs/architectural doc
|  | 2 | Estimates document
|  | 4 | Start work on phase 2 implementation: Table generation
|  | 4 | Moderate team meeting, take notes
|  | 1 | Publish notes
|  | 15 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 7 | 2 | Release Phase 1
| 0 | 2 | Update srs/architectural doc
| 2 | 2 | Estimates document
| 0 | 4 | Start work on phase 2 implementation: Table generation
| 4 | 4 | Moderate team meeting, take notes
| 1 | 1 | Publish notes
| 2 |  | Help Nick with netbeans and mysql setup
| 16 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Finish presentation
|  | 0.5 | Give interim presentation
|  | 3.5 | Observe other teams present
|  | 4 | Start work on phase 2 implementation: Table generation
|  | 4 | Develop more fine grained schedule, MS Project Gantt chart
|  | 14 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Finish presentation
| 0.5 | 0.5 | Give interim presentation
| 3.5 | 3.5 | Observe other teams present
| 0 | 4 | Start work on phase 2 implementation: Table generation
| 5 | 4 | Develop more fine grained schedule, MS Project Gantt chart
| 1 |  | Fill out interim presentation evaluations
| 1 |  | Discuss TinyMCE feasibility/benefits/tradeoffs for notification
| 13 | 14 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Moderate team meeting, take notes
|  | 3 | Find xml in word that creates one ROW
|  | 2 | Download and experiment with Apache POI API for word document manipulation
|  | 9 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 2.75 | 4 | Moderate team meeting, take notes
| 3 | 3 | Find xml in word that creates one ROW
| 2 | 2 | Download and experiment with Apache POI API for word document manipulation
| 1 |  | Publish notes
| 8.75 | 9 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 7 | Phase 2 Make xml generate tables with row
|  | 4 | Find out APIs that can create tables in docx, POI only works for DOC well
|  | 11 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 1 | 7 | Phase 2 Make xml generate tables with row
| 2 | 4 | Find out APIs that can create tables in docx, POI only works for DOC well
| 2 |  | Team self assessment
| 5 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Phase 2 xml row generation in tables
|  | 2 | Add duplicate document submission support
|  | 5 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Phase 2 xml row generation in tables
| 0 | 2 | Add duplicate document submission support
| 4 |  | Moderate team meeting, take notes
| 3 |  | Additional team meeting on Sunday
| 5 |  | Break apart word2003 xml into easier sections
| 4 |  | Investigate null pointer issue, looking at loginservlet/UserManager
| 1 |  | Publish notes
| 20 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Phase 3 architecture
|  | 4 | Moderate Team meeting, take notes
|  | 1 | Publish notes
|  | 4 | Phase 2 polishing
|  | 3 | Phase 3 requirements
|  | 15 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0.5 | 3 | Phase 3 architecture
| 4 | 4 | Moderate Team meeting, take notes
| 1 | 1 | Publish notes
| 0 | 4 | Phase 2 polishing
| 0 | 3 | Phase 3 requirements
| 3 |  | XML generation, investagation into format problems
| 4 |  | XML combining documents
| 12.5 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Re-write xml, transfer to java String
|  | 2 | Backup plan for xml transfer, look at OpenOffice UNO for java
|  | 4 | Moderate team meeting, take notes
|  | 3 | Additional Team meeting on Sunday
|  | 3 | Add functionality to download the saved PDF or DOC
|  | 17 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 3 | 5 | Re-write xml, transfer to java String
| 4 | 2 | Backup plan for xml transfer, look at OpenOffice UNO for java
| 4 | 4 | Moderate team meeting, take notes
| 3 | 3 | Additional Team meeting on Sunday
| 0 | 3 | Add functionality to download the saved PDF or DOC
| 0.5 |  | publish notes
| 1 |  | Encryption
| 15.5 | 17 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Moderate team meeting, take notes
|  | 0.5 | publish notes
|  | 3 | team meeting Sunday
|  | 5 | finalize openoffice UNO
|  | 3 | test document generation
|  | 15.5 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 4 | 4 | Moderate team meeting, take notes
| 0.2 | 0.5 | publish notes
| 4 | 3 | team meeting Sunday
| 9 | 5 | finalize openoffice UNO
| 0 | 3 | test document generation
| 17.2 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Moderate team meeting, take notes
|  | 0.5 | publish notes
|  | 3 | team meeting Sunday
|  | 11 | continue work on openoffice UNO, generate backmatter
|  | 4 | Test openoffice UNO generation
|  | 22.5 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 2 | 4 | Moderate team meeting, take notes
| 0.5 | 0.5 | publish notes
| 0 | 3 | team meeting Sunday
| 7 | 11 | continue work on openoffice UNO, generate backmatter
| 0 | 4 | Test openoffice UNO generation
| 9.5 | 22.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Continue work on backmatter generation
|  | 6 | Test openoffice UNO generation and compare to regular issue
|  | 4 | Moderate team meeting, take notes
|  | 3 | Sunday team meeting
|  | 0.5 | Publish notes
|  | 17.5 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 12 | 4 | Continue work on backmatter generation
| 6 | 6 | Test openoffice UNO generation and compare to regular issue
| 3 | 4 | Moderate team meeting, take notes
| 0 | 3 | Sunday team meeting
| 0 | 0.5 | Publish notes
| 21 | 17.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Moderate team meeting, take notes
|  | 10 | Backmatter Generation
|  | 5 | Backmatter testing
|  | 0.5 | Publish notes
|  | 19.5 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 2 | 4 | Moderate team meeting, take notes
| 7 | 10 | Backmatter Generation
| 0 | 5 | Backmatter testing
| 0 | 0.5 | Publish notes
| 4 |  | attempts at converting .odt to DOC
| 13 | 19.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 7 | Convert .odt to DOC
|  | 5 | Backmatter generation
|  | 4 | Moderate team meeting, take notes
|  | 0.5 | Publish notes
|  | 16.5 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 7 | Convert .odt to DOC
| 9 | 5 | Backmatter generation
| 2 | 4 | Moderate team meeting, take notes
|  | 0.5 | Publish notes
| 3 |  | Poster presentation
| 14 | 16.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 7 | convert ODT to doc
|  | 4 | Moderate team meeting, notes
|  | 0.5 | publish notes
|  | 3 | Work on presentation
|  | 6 | Finish backmatter generation
|  | 20.5 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
y | 7 | 7 | convert ODT to doc
| 2 | 4 | Moderate team meeting, notes
| 0 | 0.5 | publish notes
| 2 | 3 | Work on presentation
| 5 | 6 | Finish backmatter generation
| 16 | 20.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 6 | Finish backmatter, format correctly
|  | 3.5 | Team presentations
|  | 0.5 | Our presentation
|  | 4 | Host on GODADDY
|  | 0.5 | Surveys for presentations
|  | 2 | Work on technical report
|  | 16.5 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 3 | 6 | Finish backmatter, format correctly
| 3.5 | 3.5 | Team presentations
| 0.5 | 0.5 | Our presentation
| 7 | 4 | Host on GODADDY
| 0.5 | 0.5 | Surveys for presentations
| 0 | 2 | Work on technical report
| 3 |  | Fix contrib authors
| 2 |  | Update sharp server
| 19.5 | 16.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | technical report
|  | 2 | reflection meeting
|  | 4 | update docs
|  | 3 | Work on team self assessment
|  | 11 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 2 | technical report
| 1 | 2 | reflection meeting
| 1 | 4 | update docs
| 3 | 3 | Work on team self assessment
| 7 |  | Finish doc generation backmatter
| 5 |  | GoDaddy Config
| 17 | 11 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
8.5 | 10 | 10 | 14 | 14.5 | 22 | 16.5 | 16 | 19 | 12 | 10 | 14 | 16.5 | 15 | 16 | 14 | 13 | 9 | 8.75 | 11 | 5
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
5 | 20 | 15 | 12.5 | 17 | 15.5 | 15.5 | 17.2 | 22.5 | 9.5 | 17.5 | 21 | 19.5 | 13 | 16.5 | 14 | 20.5 | 16 | 16.5 | 19.5 | 11 | 17