## Sprint 1 Jan-2-13
| 88 | 18
Story # | Points | Date Added | Description | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  | 2007-01-02 | 2007-01-03 | 2007-01-04 | 2007-01-05 | 2007-01-06 | 2007-01-09 | 2007-01-10 | 2007-01-11 | 2007-01-12 | 2007-01-13
Total Estimated Hours: |  |  |  | planning | 158 | 145 | 149 | 144 | 132 | 92 | 87 | 93 | 80 | 4 of 11
S1 | 8 | 2007-01-02 | <storydescription text> | 2007-01-02: Split 9-Jan
S1-A | 8 | 2007-01-10 | <storydescription text> | 2007-01-02: Split 9-Jan | DONE Accepted
| 1A-1 | 2007-01-02 | running … for ... data |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1A-2 | 2007-01-02 | running … for ... data |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1A-3 | 2007-01-02 | refactor for ... Table | Split 9-Jan | 16 | 16 | 16 | 16 | 14 | Moved to S1-B
| 1A-4 | 2007-01-02 | redirect … |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| 1A-5 | 2007-01-05 | validate ... files data |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 1A-6 | 2007-01-05 | update … | 2007-01-02: Split 9-Jan; 2007-01-05: 1; 2007-01-06: 2; 2007-01-09: 2; 2007-01-10: Moved to S1-B
S1-B | 3 | 2007-01-10 | <storydescription text> | 2007-01-02: Split 9-Jan | Returned to PB
| 1B-1 | 2007-01-02 | refactor for ... table | Split 9-Jan | 16 | 16 | 16 | 16 | 14 | 20 | 14 | 12 | 12
| 1B-2 | 2007-01-05 | update … | Split 9-Jan |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2
S2 |  | 2007-01-02 | <storydescription text> | 2007-01-02: Merged 2-Jan
S3 | 20 | 2007-01-02 | <storydescription text> | [10 empty] | Returned to PB
| 3-1 | 2007-01-02 | Investigate … |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 3-2 | 2007-01-02 | ... Switchover |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| 3-3 | 2007-01-06 | Chg. ... to … |  |  |  |  | 1 | 1 | 3 | 1 | 1 | 1
| 3-4 | 2007-01-06 | Change ... names … |  |  |  |  | 8 | 8 | 4 | 8 | 8 | 8
S4 |  | 2007-01-02 | <storydescription text> | 2007-01-02: Split
S4-A | 3 | 2007-01-06 | <storydescription text> | [10 empty] | Returned to PB
| 4A-1 | 2007-01-02 | data validation (QA) |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1
| 4A-2 | 2007-01-02 | create unit tests for … | Split 9-Jan | 16 | 16 | 16 | 16 | 16 | Moved to S4-B
| 4A-3 | 2007-01-02 | push to production | Split 9-Jan | 4 | 4 | 4 | 4 | 4
| 4A-4 | 2007-01-02 | add to SVN | Split 9-Jan | 1 | 1 | 1 | 1 | 1
| 4A-5 | 2007-01-02 | meet production rqmtrs. | Split 9-Jan | 2 | 2 | 2 | 2 | 2
| 4A-6 | 2007-01-05 | investigate data load failure … |  |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0
| 4A-7 | 2007-01-10 | investigate data load failure … | 2007-01-10: 1; 2007-01-11: 1; 2007-01-12: 0
S4-B | 13 | 2007-01-06 | <storydescription text> | 2007-01-02: Split | Returned to PB
| 4B-1 | 2007-01-02 | create unit tests for … | Split 9-Jan | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8
| 4B-2 | 2007-01-02 | push to production | Split 9-Jan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 4B-3 | 2007-01-02 | add to SVN | Split 9-Jan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 4B-4 | 2007-01-02 | meet production rqmtrs. | Split 9-Jan | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S5 | 20 | 2007-01-02 | <storydescription text> | [10 empty] | Returned to PB
| 5-1 | 2007-01-02 | reload remaining data |  | 8 | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0
| 5-2 | 2007-01-02 | data validation (QA) |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| 5-3 | 2007-01-06 | task text |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
| 5-4 | 2007-01-12 | task text | 2007-01-12: 3; 2007-01-13: 3
| 5-5 | 2007-01-12 | task text | 2007-01-12: 16; 2007-01-13: 16
| 5-6 | 2007-01-12 | task text | 2007-01-12: 3; 2007-01-13: 3
S6 | 5 | 2007-01-02 | <storydescription text> | [10 empty] | DONE Accepted
| 6-1 | 2007-01-02 | new … report |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 6-2 | 2007-01-02 | run sched … job - verify script runs |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
S7 | 8 | 2007-01-02 | <storydescription text> | [10 empty] | Returned to PB
| 7-1 | 2007-01-02 | table access from … |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 7-2 | 2007-01-02 | coding |  | 24 | 24 | 24 | 14 | 8 | 12 | 12 | 8 | 8
| 7-3 | 2007-01-02 | data validation (QA) |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
S8 | 3 | 2007-01-02 | <storydescription text> | 2007-01-10: Returned to Product Backlog
| 8-1 | 2007-01-02 | verify ... availability | 2007-01-03: 1; 2007-01-04: 0; 2007-01-05: 0; 2007-01-06: 0; 2007-01-09: 0
| 8-2 | 2007-01-02 | gen.samples; send to ... for OK | bar: 2007-01-03 to 2007-01-13
| 8-3 | 2007-01-02 | meet production rqmtrs. | 2007-01-03: 4; 2007-01-04: 4; 2007-01-05: 4; 2007-01-06: 4; 2007-01-09: 4
S9 | 3 | 2007-01-02 | <storydescription text> | [10 empty] | DONE Accepted
| 9-1 | 2007-01-02 | investigate code |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9-2 | 2007-01-02 | coding |  | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 9-3 | 2007-01-02 | unit testing |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 9-4 | 2007-01-02 | meet Ops. production rqmtrs. |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
S10 | 2 | 2007-01-02 | ... Training | [10 empty] | DONE Accepted
| 10-1 | 2007-01-02 | ... Training |  | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 9 | 0
| 10-2 | 2007-01-10 | Sched. Training | 2007-01-10: 1; 2007-01-11: 1; 2007-01-12: 1; 2007-01-13: 0
Below Not in Burndown |  |  |  |  | 20 | 20 | 24 | 14 | 38 | 33 | 31 | 20 | ???
S-Research |  |  | RESEARCH |  | 1 | 1 | 1 | 1 | 23 | 21 | 18 | 14 | 2
| R-1 | 2007-01-02 | general DB research for … |  | ? | ? | ? | ? | 20 | 10 | 10 | 10 | 0
| R-2 | 2007-01-02 | … res. & task creation |  | ? | ? | ? | ? | 2 | 2 | 2 | 2 | 2
| R-3 | 2007-01-02 | investigate ... upload |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| R-4 | 2007-01-10 | determine how to test ... | 2007-01-10: 8; 2007-01-11: 5; 2007-01-12: 2; 2007-01-13: 0
S-Maintenance |  |  | MAINTENANCE |  | 19 | 19 | 23 | 13 | 15 | 12 | 13 | 6 | ???
| M-1 | 2007-01-02 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| M-2 | 2007-01-02 | bar: 2007-01-03 to 2007-01-13
| M-3 | 2007-01-02 |  |  | 6 | 6 | 6 | 2 | 2 | 0 | 0 | 0 | 0
| M-4 | 2007-01-02 |  |  | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| M-5 | 2007-01-02 |  |  | 0 | ? | ? | ? | ? | ? | ? | 0 | 0
| M-6 | 2007-01-02 |  |  | 3 | 3 | 3 | 3 | 4 | 0 | 0 | 0 | 0
| M-7 | 2007-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| M-8 | 2007-01-02 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| M-9 | 2007-01-02 |  |  | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| M-10 | 2007-01-05 |  |  |  |  | 2 | 2 | 1 | 1 | 1 | 1 | ?
| M-11 | 2007-01-05 |  |  |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0
| M-12 | 2007-01-09 | bar: 2007-01-03 to 2007-01-13
| M-13 | 2007-01-09 |  | 2007-01-09: 2; 2007-01-10: 2; 2007-01-11: 2; 2007-01-12: 0; 2007-01-13: 0
| M-14 | 2007-01-10 |  | 2007-01-10: 2; 2007-01-11: 2; 2007-01-12: 2; 2007-01-13: ?
| M-15 | 2007-01-10 | bar: 2007-01-03 to 2007-01-13
| M-16 | 2007-01-11 |  | 2007-01-11: 3; 2007-01-12: 0; 2007-01-13: 0
Team Capacity Estimates
|  |  | Who | 2007-01-02: Tot.Hrs.; 2007-01-03: Maint.; 2007-01-04: Proj.; 2007-01-05: Tasks; 2007-01-11: 32
|  |  | E1 | 2007-01-02: 54
|  |  | E2 | 2007-01-02: 54
|  |  | E3 | 2007-01-02: 54
|  |  | E4 | 2007-01-02: 54
|  |  | E5 | 2007-01-02: 27
QA
|  |  | Totals | 2007-01-02: 243; 2007-01-03: 43; 2007-01-04: 200; 2007-01-05: 0
|  |  | PO | 2007-01-02: 0; 2007-01-03: 0; 2007-01-04: 0
|  |  | SM | 2007-01-02: 0; 2007-01-03: 0; 2007-01-04: 0; 2007-01-05: 0
|  |  | EM | 2007-01-02: 0; 2007-01-03: 0; 2007-01-04: 0; 2007-01-05: 0
|  |  | SP | 2007-01-02: 0; 2007-01-03: 0; 2007-01-04: 0; 2007-01-05: 0

## Sprint 2 Jan-16-27
| 125 | 63 |  | Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  |  | 2007-01-16 | 2007-01-17 | 2007-01-18 | 2007-01-19 | 2007-01-20 | 2007-01-23 | 2007-01-24 | 2007-01-25 | 2007-01-26 | 2007-01-27
Total Estimated Hours: |  |  |  |  | 121 | 116 | 102 | 73 | 64 | 79 | 52 | 36 | 22 | 19 | 5 of 11
S1 | 20 | 2007-01-16 | <storydescription text> | [11 empty] | DONE ACCEPTED
| T1 | 2007-01-16 | data validation (QA) | PO | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0
| T2 | 2006-07-27 | Release (switchover) ROI Cube | E5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| T3 | 2006-07-27 | Push most recent data | E5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S2 | 20 | 2007-01-16 | <storydescription text> |  | 2007-01-23: Blocked | DONE ACCEPTED
| T1 | 2006-07-27 | notify users | PO | bar: 2007-01-16 to 2007-01-27
| T2 | 2006-07-27 | change scripts for switchover + test | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T3 | 2006-07-27 | QA and data validation (test rules) | E2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| T4 | 2006-07-27 | move to production | E2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0
| T5 | 2006-07-27 | test | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| T6 | 2006-07-27 | finish restructure | E2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T7 | 2006-07-27 | review rules and test | E1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T8 | 2006-07-27 | data validation (QA) | PO | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| T9 | 2006-07-27 | load missing data | E2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 13 | 2007-01-16 | <storydescription text> |  | 2007-01-20: Blocked; 2007-01-23: Blocked; 2007-01-25: Blocked; 2007-01-26: Returned to Product Backlog
| T1 | 2006-07-27 | update atom from CID for last 60 days in Redirect_Fact | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T2 | 2006-07-27 | update atom from CID for last 60 days in Apollo_Redirect_Fact | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T3 | 2006-07-27 | update atom from CID for last 60 days in 1-day redirect files | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T4 | 2006-07-27 | update atom from CID for last 60 days in DSSOL.archive.redirect_log. | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S4 | 20 | 2007-01-16 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2006-07-27 | populate NEW CR data into table | E3 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2006-07-27 | generate spreadsheet version of upload data | E3 | 5 | 2 | 5 | 3 | 4 | 2 | 2 | 2 | 0 | 0
| T3 | 2006-07-27 | generate CVS version of upload data | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| T4 | 2006-07-27 | exception report | E3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T5 | 2006-07-27 | Define teat plan & teat case for monthly invoice uploading & execute test cases Partially replaced by T2 & T3 | QA | 6 | 6 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0
S5 | 8 | 2007-01-16 | <storydescription text> | [11 empty] | Returned to PB
| T1 | 2006-07-27 | QA & approve data for use | E1 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S6 | 8 | 2007-01-16 | <storydescription text> | [11 empty] | DONE ACCEPTED
| T1 | 2006-07-27 | Finish development | E5 | 12 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2006-07-27 | User acceptance (QA) | PO | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T3 | 2006-08-02 | Discuss QA concerns | ? |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
| T4 | 2006-08-03 | Implement new changes | E5 | 2007-01-23: 24; 2007-01-24: 3; 2007-01-25: 3; 2007-01-26: 1; 2007-01-27: 0
S7 | 13 | 2007-01-16 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2006-07-27 | table access from DW | E1 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 0 | 0 | 0
| T2 | 2006-07-27 | coding | E1 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0
| T3 | 2006-07-27 | data validation (QA) | E1 | bar: 2007-01-16 to 2007-01-27
| T4 | 2006-07-27 | QA ROI Cube | E1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T5 | 2006-07-27 | user acceptance testing | PO | bar: 2007-01-16 to 2007-01-27
S8 | 3 | 2007-01-16 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2006-07-27 | validate data | E2 | 2 |  | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2
| T2 | 2006-07-27 | documentation | E2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| T3 | 2006-07-27 | Productionize | E2 | bar: 2007-01-16 to 2007-01-27
| T4 | 2006-07-27 | user acceptance testing | PO | bar: 2007-01-16 to 2007-01-27
S9 | 13 | 2007-01-16 | <storydescription text> | [11 empty] | DONE ACCEPTED
| T1 | 2006-07-27 | add user/pw to DSP for DW: codep_user & codep_load Essbase: admin | SP | ??? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2006-07-27 | add DSP usage to EssbaseShopzilla for codep_user, codep_load & admin | E1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| T3 | 2006-07-27 | refactor redirect cube build process to use EssbaseSHopzilla module | E1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
S10 | 2 | 2007-01-16 | <storydescription text> | [11 empty] | DONE ACCEPTED
| T1 | 2007-01-16 | modify data on dev to make sure changes are made (BRUS) | PO | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
| T2 | 2007-01-16 | write new data to pkdss01..bizops after change | PO | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
| T3 | 2007-01-16 | validate new daya (QA?) | E2 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0
| T4 | 2007-01-16 | change conf file to incorporate new channels | PO | 1 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0
S11 | 5 | 2007-01-16 | <storydescription text> | [11 empty] | Returned to PB
| T1 | 2007-01-16 | Investigate ECPC script to understand task | E2 | 3 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0
Below Not in Burndown |  |  |  |  | 24 | 24 | 6 | 8 | 6 | 15 | 73 | 78 | 92 | 96
S-Research |  |  | RESEARCH |  | 24 | 24 | 6 | 8 | 6 | 15 | 15 | 15 | 15 | 14
| T1 |  | Training ... on ... Processes | QA/PO | 4 | 4 |  |  |  | 1 | 1 | 1 | 1 | 0
| T2 |  | Investigating scripts using ... logs | E3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T3 |  | ... investigation | E3 E4 | 10 | 10 |  |  |  | 8 | 8 | 8 | 8 | 8
| T4 |  | Calc … | ?? | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
| T5 |  | Train ... on ... data validity - QA | PO/QA | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| T6 | BLOCKED | Investigate unit test creation |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
S-Maintenance |  |  | MAINTENANCE actual hours totals |  | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 63 | 77 | 82
| T1 |  | Category 1 | E1 E2 E3 | 2007-01-24: 16; 2007-01-25: 18; 2007-01-26: 21; 2007-01-27: 22
| T2 |  | Category 2 | E5 | 2007-01-24: 2; 2007-01-25: 2; 2007-01-26: 2; 2007-01-27: 3
| T3 |  | Category 3 | E2 | 2007-01-24: 20; 2007-01-25: 20; 2007-01-26: 20; 2007-01-27: 23
| T4 |  | Category 4 | E5 | bar: 2007-01-24 to 2007-01-27
| T5 |  | Category 5 | EF | 2007-01-24: 9; 2007-01-25: 9; 2007-01-26: 19; 2007-01-27: 19
| T6 |  | Category 6 | E1 E2 | 2007-01-24: 3; 2007-01-25: 4; 2007-01-26: 4; 2007-01-27: 4
| T7 |  | Category 7 | E1 E2 | 2007-01-24: 3; 2007-01-25: 3; 2007-01-26: 3; 2007-01-27: 3
| T8 |  | Failed Jobs | E4 | 2007-01-24: 4; 2007-01-25: 6; 2007-01-26: 7; 2007-01-27: 7
TeAB Capacity Estimates
|  |  | Who | Tot.Hrs. | 2007-01-16: Maint.; 2007-01-17: Proj.; 2007-01-18: Tasks
|  |  | E1 | 63 | 2007-01-16: 20; 2007-01-17: 43; 2007-01-18: 34
|  |  | E2 | 70 | 2007-01-16: 20; 2007-01-17: 50; 2007-01-18: 24
|  |  | E3 | 45 | 2007-01-16: 35; 2007-01-17: 10; 2007-01-18: 29
|  |  | E4 | 40 | 2007-01-16: 20; 2007-01-17: 20; 2007-01-18: 7
|  |  | E5 | 63 | 2007-01-16: 20; 2007-01-17: 43; 2007-01-18: 38
|  |  | QA | 50 | 2007-01-16: 0; 2007-01-17: 50; 2007-01-18: 12
|  |  | Core TeAB Totals | 331 | 2007-01-16: 115; 2007-01-17: 216; 2007-01-18: 144
|  |  | PO | 15 | 2007-01-16: 0; 2007-01-17: 15; 2007-01-18: 24
|  |  | SM | 60 | 2007-01-16: 0; 2007-01-17: 60; 2007-01-18: 0
|  |  | EM | 0 | 2007-01-16: 0; 2007-01-17: 0; 2007-01-18: 0
|  |  | SP | 5 | 2007-01-16: 0; 2007-01-17: 5; 2007-01-18: 0

## Sprint 3 Jan-30-Feb-10
| 101 | 41 |  | Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  |  | 2007-01-30 | 2007-01-31 | 2007-02-01 | 2007-02-02 | 2007-02-03 | 2007-02-06 | 2007-02-07 | 2007-02-08 | 2007-02-09 | 2007-02-10
Total Estimated Hours: |  |  |  |  | 211 | 195 | 195 | 186 | 174 | 147 | 124 | 122 | 95 | 91 | 5 of 13
S1 | 20 | 2007-01-30 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-01-30 | test/fix ... files | E3 | 4 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 2 | 0
| T2 | 2007-01-30 | test/fix … | E3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| T3 | 2007-01-30 | exception report | E3 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 1 | 0 | 0
S2 | 3 | 2007-01-30 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-01-30 | validate data | E1 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6
| T2 | 2007-01-30 | code review | E2 | bar: 2007-01-30 to 2007-02-10
| T3 | 2007-01-30 | productionalize | E2 | bar: 2007-01-30 to 2007-02-10
| T4 | 2007-01-30 | user acceptance testing | E2 PO | bar: 2007-01-30 to 2007-02-10
S3 | 5 | 2007-01-30 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-01-30 | design/architect | E2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-01-30 | code reporting script | E2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T3 | 2007-01-30 | code ... script | E2 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| T4 | 2007-01-30 | unit testing for report and ... scripts | E2 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| T5 | 2007-01-30 | ... functional testing | E2 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 4 | POSTPONED
| T6 | 2007-01-30 | committing to CVS and productionalize | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
S4 | 8 | 2007-01-30 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-01-30 | remediate scripts impacted by … | E2 | 20 | 20 | 20 | 20 | 20 | 8 | 8 | 8 | 8 | 24
| T2 | 2007-01-30 | refresh data used by … | E2 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0
| T3 | 2007-01-30 | notify users about changes to reports | E4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 0 | 0
| T4 | 2007-02-02 | code script to update … | E2 |  |  |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
| T5 | 2007-02-06 | run remaining … | E2 | 2007-02-06: 1; 2007-02-07: 1; 2007-02-08: 8; 2007-02-09: 0; 2007-02-10: 0
| T6 | 2007-02-03 |  | E4 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0
S5 | 13 | 2007-01-30 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-01-30 | Change … table for … |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| T2 | 2007-01-30 | complete audit |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| T3 | 2007-01-30 | update ... table |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T4 | 2007-01-30 | update ... table |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T5 | 2007-01-30 | Change ... dimension build view and rule |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
S6 | 13 | 2007-01-30 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-01-30 | identify scripts that need modification and which group will do it |  | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-01-30 | document ... data flow |  | 4 | 3 | 3 | 3 | 3 | 3 | 3 | POSTPONED
S7 | 8 | 2007-01-30 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-01-30 | audit code which uses … | E4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 3 | 0
| T2 | 2007-01-30 | Reworded mm/dd: document impact of ... | E4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
S8 | 5 | 2007-01-30 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-01-30 | create a roadmap for SOX compliance |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2
| T2 | 2007-01-30 | SOX Cubes planning |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
S9 | 13 | 2007-01-30 | <storydescription text> |  | 2007-02-07: Blocked; 2007-02-08: Blocked; 2007-02-09: Blocked; 2007-02-10: Blocked | Returned to Product Backlog
| T1 | 2007-01-30 | rewrite resync script | E3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-01-30 | construce new job streams | E3 | 4 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| T3 | 2007-01-30 | setup environment to test Houston | E3 | 12 | 10 | 10 | 10 | 10 | 9 | 6 | 4 | 2 | 1
| T4 | 2007-01-30 | id problems (maint.) | E3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| T5 | 2007-01-30 | convert RPM for Houston | E3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1
| T6 | 2007-01-30 | create job to daily views (serves Houston) | E3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3
S10 | 1 | 2007-01-30 | <storydescription text> |  | 2007-02-07: Blocked; 2007-02-08: Blocked | Returned to Product Backlog
| T1 | 2007-01-30 | remove ... dependency from … | E3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
S11 | 8 | 2007-01-30 | <storydescription text> |  | 2007-02-08: Blocked; 2007-02-09: Blocked; 2007-02-10: Blocked | Returned to Product Backlog
| T1 | 2007-01-30 | update stored proc |  | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| T2 | 2007-01-30 | restore dashboard monitor |  | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
| T3 | 2007-01-30 | dashboard code in SVN |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T4 | 2007-01-30 | implement freshness checker doc. And Email to developers |  | 4 | 4 | 4 | 4 | 4 | 11 | 11 | 11 | 11 | 11
| T5 | 2007-01-30 | identify dashboard data sources |  | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| T6 | 2007-01-30 | clean up the dashboard directory |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| T7 | 2007-01-30 | implement email notification systems for hourly dashboard |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
S12 | 3 | 2007-01-30 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-01-30 | create skill matrix template | QA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-01-30 | collect skill information from team | QA | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
| T3 | 2007-01-30 | finalize skill matrix | QA | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| T4 | 2007-01-30 | publish team skill matrix | QA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S13 | 1 | 2007-01-30 | <storydescription text> |  | 2007-02-03: CANCELED
| T1 | 2007-01-30 | add redirect and ROI cubes to BIM |  | 2007-01-30: 2; 2007-01-31: 2; 2007-02-01: 2; 2007-02-02: 0
Below Not in Burndown |  |  |  |  | 8 | 8 | 8 | 5 | 5 | 25 | 28 | 30 | 32 | 34
S-Research |  |  | RESEARCH |  | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Returned to Product Backlog
| T1 |  | establish runbook framework | E4 SP | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| T2 | BLOCKED | Investigate unit test creation | E2 QA E1 E4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
S-Maintenance |  |  | MAINTENANCE actual hours totals |  | 0 | 0 | 0 | 0 | 0 | 20 | 23 | 25 | 27 | 29
| T1 |  | Category 1 | E1 E2 E5 | ? | ? | ? | ? | ? | 3 | 4 | 6 | 7 | 8
| T2 |  | Category 2 | E5 | ? | ? | ? | ? | ? | 4 | 5 | 5 | 5 | 5
| T3 |  | Category 3 | E2 | ? | ? | ? | ? | ? | 0 | 0 | 0 | 0 | 0
| T4 |  | Category 4 | E5 | ? | ? | ? | ? | ? | 0 | 0 | 0 | 0 | 0
| T5 |  | Category 5 | E1 E4 | ? | ? | ? | ? | ? | 7 | 7 | 7 | 8 | 8
| T6 |  | Category 6 | E4 | ? | ? | ? | ? | ? | 0 | 0 | 0 | 0 | 0
| T7 |  | Category 7 | E2 E4 | bar: 2007-01-30 to 2007-02-10
| T8 |  | Failed Jobs | E4 SP | ? | ? | ? | ? | ? | 5 | 5 | 5 | 5 | 5
| T9 |  | Other
| T9 | 2006-02-06 | Investigate impact of pending releases of other groups. | E4 SP | 2007-02-07: 1; 2007-02-08: 1; 2007-02-09: 1; 2007-02-10: 2
Team Capacity Estimates
|  |  | Who | Tot.Hrs. | 2007-01-30: Maint.; 2007-01-31: Proj.; 2007-02-01: Tasks
|  |  | E1 | 44 | 2007-01-30: 6; 2007-01-31: 38; 2007-02-01: 24
|  |  | E2 | 56 | 2007-01-30: 11; 2007-01-31: 45; 2007-02-01: 44
|  |  | E3 | 45 | 2007-01-30: 8; 2007-01-31: 37; 2007-02-01: 42
|  |  | E4 | 45 | 2007-01-30: 15; 2007-01-31: 30; 2007-02-01: 48
|  |  | E5 | 56 | 2007-01-30: 20; 2007-01-31: 36; 2007-02-01: 20
|  |  | QA | 40 | 2007-01-30: 0; 2007-01-31: 40; 2007-02-01: 30
|  |  | Core Team Totals | 286 | 2007-01-30: 60; 2007-01-31: 226; 2007-02-01: 208
|  |  | PO | 5 | 2007-01-30: 0; 2007-01-31: 5
|  |  | SM |  | 2007-01-31: 0; 2007-02-01: 0
|  |  | EM |  | 2007-01-31: 0; 2007-02-01: 0
|  |  | SP |  | 2007-01-31: 0; 2007-02-01: 0

## Sprint 4 Feb-13-24
| 87 | 11 |  | Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  |  | 2007-02-13 | 2007-02-14 | 2007-02-15 | 2007-02-16 | 2007-02-17 | 2007-02-20 | 2007-02-21 | 2007-02-22 | 2007-02-23 | 2007-02-24
Total Estimated Hours: |  |  |  |  | 267 | 250 | 238 | 245 | 235 | 189 | 178 | 178 | 154 | 124 | 4 of 18
S1 | 3 | 2007-02-13 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-02-13 | Optimize the query by DBA & review/push | E2 | 4 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-02-13 | Code Review | E2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| T3 | 2007-02-13 | Push to Production | E2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Rmv'd.
| T4 | 2007-02-13 | Create runbook | E2 | bar: 2007-02-13 to 2007-02-24
S2 | 5 | 2007-02-13 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Prepare for ... data review | E1 | 8 | 8 | 8 | 4 | 4 | 2 | 1 | 1 | 1 | 1
| T2 | 2007-02-13 | Meet to review ... data | PO | 3 | 5 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
| T3 | 2007-02-13 | Consolidate ... review notes from … | PO | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T4 | 2007-02-13 | Ops training for … w/doc. | E1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S3 | 2 | 2007-02-13 | <storydescription text> | [11 empty] | DONE Accepted
| T1 | 2007-02-13 | QA | QA | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1
S4 | 8 | 2007-02-13 | <storydescription text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Fix ... to use Java ... client | E2 | 28 | 28 | 28 | 19 | 18 | 18 | 18 | 18 | 18 | 18
| T2 | 2007-02-13 | environment | E2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T3 | 2007-02-13 | Code Review | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T4 | 2007-02-13 | QA of … | E2 QA | 16 | 16 | 16 | 15 | 14 | 14 | 14 | 14 | 14 | 14
| T5 | 2007-02-13 | Stored proc reviews and push | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T6 | 2007-02-13 | ... acceptance testing | E2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T7 | 2007-02-13 | Productionalize … and ... | E2 | bar: 2007-02-13 to 2007-02-24
| T8 | 2006-08-29 | investigate ... log architecture | E2 E1 |  |  |  | 24 | 24 | 20 | 16 | 16 | 16 | 12
S5 | 5 | 2007-02-13 | <story description text> | [11 empty] | DONE Accepted
| T1 | 2007-02-13 | Define and document … tasks and timeline | GH | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
S6 | 5 | 2007-02-13 | <story description text> | [11 empty] | ?
| T1 | 2007-02-13 | Work with Ops. on server availability | E1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T2 | 2007-02-13 | Install ... server | E1 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0
| T3 | 2007-02-13 | Move ... to QA | E5 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 0
| T4 | 2007-02-13 | Modify & test Perl module to use QA | E5 | 4 | 4 | 4 | 4 | 3 | 2 | 4 | 4 | 4 | 1
S7 | 1 | 2007-02-13 | <story description text> | [11 empty] | DONE
| T1 | 2007-02-13 | ... change control introduction structure for … | E4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Accepted
S8 | 5 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Create dummy ... table | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| T2 | 2007-02-13 | Modify scripts to use dummy ... table | E2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T3 | 2007-02-13 | Insert dummy values for new … | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| T4 | 2007-02-13 | Migrate all stored procs, etc. to QA server | E2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| T5 | 2007-02-13 | Test and validate (QA version) | E2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| T6 | 2007-02-13 | Monitor in production | E2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
S9 | 2 | 2007-02-13 | <story description text> | [11 empty] | Returned to PB
| T1 | 2007-02-13 | Establish runbook framework | E4 SP | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| T2 | 2007-02-13 | Investigate new Oracle QA sys. availability | E1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S10 | 20 | 2007-02-13 | <story description text> |  | 2007-02-13: 2 | Returned to Product Backlog
| T1 | 2007-02-13 | Usage training | team | 5 | 5 | 4 | 5 | 4 | 4 | 5 | 5 | 5 | 4
| T2 | 2007-02-13 | Determine structure for SVN projects with Ops. | E4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| T3 | 2007-02-13 | Build process training | team | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
S11 | 1 | 2007-02-13 | <story description text>
| T1 | 2007-02-13 | Research tasks for adding POS to infrastructure | E1 | 2 | 2 | 2 | 2 | 2 | Moved to S-15 |  |  |  |  | Moved
S12 | 5 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Change ... build to use new infrastructure | E1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| T2 | 2007-02-13 | Add ... code to SVN | E1 | bar: 2007-02-13 to 2007-02-24
S13 | 2 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Change ... build to use new infrastructure | E1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| T2 | 2007-02-13 | Add … code to SVN | E1 | bar: 2007-02-13 to 2007-02-24
S14 | 2 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Change Dash Cube to use new infrastructure | E1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
| T2 | 2007-02-13 | Add ... Code to SVN | E1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4
S15 | 1 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 12-Feb BLOCKED | Investigate unit test creation | E4 | 4 | 4 | 4 | 4 | 4 | Returned to Product Backlog
| T2 | 2007-02-13 | Research tasks for adding POS to infrastructure | E1 | 2007-02-13: Moved from S-11
S16 | 1 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 2007-02-13 | Create Rally example story - REVISED to model Sprint 4 Stories, Releases and Projects. | SM | 2007-02-13: SM's time not in core team burndown
| T2 | 2007-02-13 | Train team in Rally usage | team | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
S17 | 1 | 2007-02-13 | <story description text>
| T1 | 2007-02-13 | Prepare workshop | SM | 2007-02-13: 0; 2007-02-14: Postponed - till Sprint #5 possibly a 1-hr presentation rather than a 2-hr workshop. | Postponed
| T2 | 2007-02-13 | Workshop with team | team | 2007-02-13: 12
S18 | 8 | 2007-02-13 | <story description text> | [11 empty] | Returned to Product Backlog
| T1 | 12-Feb BLOCKED | Modify Perl script to work with new tables and stored procs, which will check ... only | E5 | 3 | 3 | 3 | 3 | 2 | Returned to Product Backlog
| T2 | 2007-02-13 | Cleanup ... directory | E5 | bar: 2007-02-13 to 2007-02-24
| T3 | 2007-02-13 | Put ... code in SVN | E5 | bar: 2007-02-13 to 2007-02-24
| T4 | 2007-02-13 | Implement … | E5 | 2007-02-13: 21; 2007-02-14: 21; 2007-02-15: 21; 2007-02-16: 21; 2007-02-17: 21
Maint. | 10 | 2007-02-13 | <story description text>
| T1 | 2007-02-13 | Maximum Maintenance time commitment for Sprint | team | 43 | 39 | 36 | 33 | 30 | 28 | 23 | 23 | 19 | 14
Below Not in Burndown
Maintenance Burn-Up |  |  | MAINTENANCE actual hours totals |  | 0 | 4 | 7 | 10 | 13 | 15 | 20 | 20 | 24 | 29
| M1 |  | Category 1 | <initials> |  | 3 | 5 | 8 | 11 | 13 | 16 | 16 | 18 | 20
| M2 |  | Category 2 | <initials> |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| M3 |  | Category 3 | <initials>
| M4 |  | Category 4 | <initials> | bar: 2007-02-21 to 2007-02-24
| M8 |  | Other |  | 2007-02-21: 1; 2007-02-22: 1; 2007-02-23: 3; 2007-02-24: 6
Team Capacity Estimates
|  |  | Who | Tot.Hrs. | 2007-02-13: Maint.; 2007-02-14: Proj.; 2007-02-15: Tasks
|  |  | E1 | 49 | 2007-02-13: 7; 2007-02-14: 42; 2007-02-15: 47
|  |  | E2 | 53 | 2007-02-13: 5; 2007-02-14: 48; 2007-02-15: 67
|  |  | E4 | 30 | 2007-02-13: 8; 2007-02-14: 22; 2007-02-15: 15
|  |  | E5 | 49 | 2007-02-13: 15; 2007-02-14: 34; 2007-02-15: 39
|  |  | QA | 40 | 2007-02-13: 8; 2007-02-14: 32; 2007-02-15: 26
|  |  | Core Team Totals | 221 | 2007-02-13: 43; 2007-02-14: 178; 2007-02-15: 194
|  |  | PO | 5 | 2007-02-13: 0; 2007-02-14: 5; 2007-02-15: 5
|  |  | SM |  | 2007-02-14: 0; 2007-02-15: 15
|  |  | EM | 0 | 2007-02-13: 0; 2007-02-14: 0; 2007-02-15: 0
|  |  | SP |  | 2007-02-14: 0

## Sprint 5 Feb-27-Mar-10
| 56 | 20 |  | Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  |  | 2007-02-27 | 2007-02-28 | 2007-03-01 | 2007-03-02 | 2007-03-03 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-09 | 2007-03-10
|  |  | Total Estimated Hours to Complete: |  | 198 | 193 | 171 | 125 | 105 | 104 | 94 | 79 | 67 | 58 | 7 of 13
S1 | 2 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
| 1-1 | 2007-02-27 | Review ... with … cust. & SP. | PO | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
S2 | 8 | 2007-02-27 | <storydescription text> |  | 2007-03-02: Blocked; 2007-03-03: Blocked; 2007-03-06: Blocked | DONE Accepted
RT | 2-0 | 2007-02-27 | Find out how data structures are built | E5 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2-1 | 2007-02-27 | Create the Query | E1 EM | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| 2-2 | 2007-02-27 | Validate data | EM | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| 2-3 | 2007-02-27 | Change Perl Script | E5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
S3 | 1 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
| 3-1 | 2007-02-27 | Reload missing day | E5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 3 | 2007-02-27 | <storydescription text> |  | 2007-03-08: on Hold; 2007-03-09: on Hold; 2007-03-10: on Hold
| 4-0 | 2007-02-27 | Work with Ops. to create … | PO | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 4-1 | 2007-02-27 | Modify query and validate data | E2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4-2 | 2007-02-27 | Optimize query and recreate view | E2 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 4-3 | 2007-02-27 | Modify script | E2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 4-4 | 2007-02-27 | Get approval | E2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 4-5 | 2007-02-27 | Productionalize | E2 | bar: 2007-02-27 to 2007-03-10
S5 | 8 | 2007-02-27 | <storydescription text> |  | 2007-03-08: on Hold; 2007-03-09: on Hold; 2007-03-10: on Hold
| 5-1 | 2007-02-27 | Test / code new algorythm for … | E2 | 15 | 15 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| 5-2 | 2007-02-27 | Finish coding and clean up code | E2 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1
| 5-3 | 2007-02-27 | … | E2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 5-4 | 2007-02-27 | Create test cases for ... changes for … | QA | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5-5 | 2007-02-27 | Test cases execution | QA | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5-6 | 2006-09-14 | Productionalize | QA | 2007-03-06: 5; 2007-03-07: 5; 2007-03-08: 5; 2007-03-09: 5; 2007-03-10: 5
S6 | 5 | 2007-02-27 | <storydescription text> |  |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked
| 6-1 | 2007-02-27 | Database server | E5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| 6-2 | 2007-02-27 | Install some stuff | E1 | bar: 2007-02-27 to 2007-03-10
| 6-3 | 2007-02-27 | Test Perl script | E5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S7 | 5 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
| 7-1 | 2007-02-27 | Load ... to … dimension | E1 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 7-2 | 2007-02-27 | Create ... table to populate ... dimension | E1 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S8 | 5 | 2007-02-27 | <storydescription text>
| 8-1 | 2007-02-27 | Update … with ... | E1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 8-2 | 2007-02-27 | Regenerate redirect_cube files | E1 | bar: 2007-02-27 to 2007-03-10
| 8-3 | 2007-02-27 | Update ... dimension | E1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| 8-4 | 2007-02-27 | test … | E1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
S9 | 5 | 2007-02-27 | <storydescription text> |  | 2007-03-08: Blocked; 2007-03-09: Blocked; 2007-03-10: on Hold
| 9-1 | 2007-02-27 | Create layout and get approval | E2 | 4 | 4 | 4 | 4 | 3 | 1 | 1 | 1 | 1 | 1
| 9-2 | 2007-02-27 | … coding | E2 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 2 | 2 | 2
| 9-3 | 2007-02-27 | optimize query and create view | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| 9-4 | 2007-02-27 | create runbook | E2 | bar: 2007-02-27 to 2007-03-10
| 9-5 | 2007-02-27 | productionalize | E2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
S10 | 5 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
| 10-1 | 2007-02-27 | update ... table with … | E1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| 10-2 | 2007-02-27 | regenerate … | E1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| 10-3 | 2007-02-27 | update ... dimension | E1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| 10-4 | 2007-02-27 | test … | E1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
S11 | 3 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
| 11-1 | 2007-02-27 | convert ... to … | E1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 11-2 | 2007-02-27 | create ... build script | E5 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 2 | 1 | 0
S12 | 5 | 2007-02-27 | <storydescription text> |  | 2007-03-06: Blocked; 2007-03-07: Blocked; 2007-03-08: Blocked; 2007-03-09: Blocked; 2007-03-10: on Hold
| 12-1 | 2007-02-27 | Create test cases for ... change | QA | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 6 | 2 | 2
| 12-2 | 2007-02-27 | Test cases execution | QA | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 12-3 | 2006-09-14 | Modify Scripts to use dummy ... table | QA | 2007-03-06: 4; 2007-03-07: 4; 2007-03-08: 4; 2007-03-09: 4; 2007-03-10: 4
| 12-4 | 2006-09-14 | Insert dummy values for new … | QA | 2007-03-06: 2; 2007-03-07: 2; 2007-03-08: 2; 2007-03-09: 2; 2007-03-10: 2
| 12-5 | 2006-09-14 | Migrate all stored procs, etc. to QA server | QA | 2007-03-06: 3; 2007-03-07: 3; 2007-03-08: 3; 2007-03-09: 3; 2007-03-10: 3
| 12-6 | 2006-09-14 | Monitor in production | QA | 2007-03-06: 3; 2007-03-07: 3; 2007-03-08: 3; 2007-03-09: 3; 2007-03-10: 3
S13 | 1 | 2007-02-27 | <storydescription text> | [11 empty] | DONE Accepted
Cubes | 13-1 | 2007-02-27 | Finish changing the script | E5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13-2 | 2007-02-27 | Move to production | E5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Maint. |  | 2007-02-27 | Maintenance Commitment -- Maximum
| M-0 | 2007-02-27 | Maximum Maintenance time commitment for Sprint | team | 29 | 27 | 26 | 22 | 16 | 10 | 8 | 7 | 3 | 2
Below Not in Burndown
S-Maintenance |  |  | MAINTENANCE actual hours totals |  | 2 | 2 | 3 | 7 | 13 | 19 | 21 | 22 | 26 | 27
| M-1 |  |  | E5 E1 E2 |  |  |  | 1 | 2 | 4 | 5 | 6 | 9 | 10
| M-2 |  |  | E5 | 2 | 2 | 2 | 3 | 3 | 6 | 6 | 6 | 7 | 7
| M-3 |  |  | E2
| M-4 |  |  | E5
| M-5 |  |  | E1 E4 | bar: 2007-03-02 to 2007-03-10
| M-6 |  |  | E1 E4
| M-7 |  | Failed Jobs | E4 |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
| M-8 |  | Other |  |  |  |  | 1 | 5 | 6 | 7 | 7 | 7 | 7
Team Capacity Estimates
|  |  | Who | Tot.Hrs. | 2007-02-27: Maint.; 2007-02-28: Proj.; 2007-03-01: Tasks
|  |  | E1 | 54 | 2007-02-27: 10; 2007-02-28: 44
|  |  | E2 | 54 | 2007-02-27: 4; 2007-02-28: 50
|  |  | E4 | 30 | 2007-02-27: 5; 2007-02-28: 25
|  |  | E5 | 50 | 2007-02-27: 10; 2007-02-28: 40
|  |  | QA | 43 | 2007-02-27: 0; 2007-02-28: 43
|  |  | PO | 5 | 2007-02-27: 0; 2007-02-28: 5
|  |  | Totals | 236 | 2007-02-27: 29; 2007-02-28: 207; 2007-03-01: 198
|  |  | SM |  | 2007-02-28: 0
|  |  | EM |  | 2007-02-28: 0
|  |  | SP |  | 2007-02-28: 0

## Sprint 6 Mar-13-24
Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Stories Accepted
| Task # |  |  |  | 2006-03-13 | 2006-03-14 | 2006-03-15 | 2006-03-16 | 2006-03-17 | 2006-03-20 | 2006-03-21 | 2006-03-22 | 2006-03-23 | 2006-03-24
Total Estimated Hours: | [14 empty] | x of y
S1 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S2 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
| T6 | 2006-03-13
| T7 | 2006-03-13
| T8 | 2006-03-13
| T9 | 2006-03-13
S3 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S4 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S5 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S6 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S7 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S8 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
S9 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S10 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
| T5 | 2006-03-13
S11 |  | 2006-03-13 | <storydescription text>
| T1 | 2006-03-13
| T2 | 2006-03-13
| T3 | 2006-03-13
| T4 | 2006-03-13
Maint. |  | 2006-03-13 | Maintenance Commitment
| T1 | 2006-03-13 | Maximum Maintenance time commitment for Sprint | team | 2006-03-13: 0; 2006-03-14: 0
Below Not in Burndown
S-Maintenance |  |  | MAINTENANCE actual hours totals |  | 2006-03-13: 0
| M1 |  | Category 1
| M2 |  | Category 2
| M3 |  | Category 3
| M4 |  | Category 4
| M5 |  | Category 5
| M6 |  | Category 6
| M7 |  | Failed Jobs
| M8 |  | Other
Team Capacity Estimates
|  |  | Who | Tot.Hrs. | 2006-03-13: Maint.; 2006-03-14: Proj.; 2006-03-15: Tasks
E1
E2
E4
E5
QA
New
|  |  | Core Team Totals | 0 | 2006-03-13: 0; 2006-03-14: 0; 2006-03-15: 0
PO
SM
EM
SP

## Velocity
Sprint | Dates |  | User Stories |  | Story Points |  | Task Hours |  | Maint. Hrs. | Core Team
No. | Start | End | Accepted | Initial Commitment | Accepted | Initial Commitment | Initially | Left | Total | Staff | Proj. Hrs. | Maint. Hrs. | Goal / Changes
1 | 2006-01-02 | 2006-01-13 | 4 | 11 | 18 | 88 | 158 | 80 | 32 | 6 | 200 | 43 | Learn Scrum Process Complete inflight work
2 | 2006-01-16 | 2006-01-27 | 5 | 11 | 63 | 125 | 121 | 19 | 82 | 6 | 216 | 115 | Continue inflight / Track Maint.Time
3 | 2006-01-30 | 2006-02-10 | 5 | 13 | 41 | 101 | 211 | 91 | 29 | 6 | 226 | 60 | Corp. Initative 1 focus
4 | 2006-02-13 | 2006-02-24 | 4 | 18 | 11 | 87 | 267 | 124 | 29 | 5 | 178 | 43 | Corp. Initative 2 focus / Maint.Hrs.as LIMIT
5 | 2006-02-27 | 2006-03-10 | 7 | 13 | 20 | 56 | 198 | 58 | 27 | 5 | 207 | 29 | Focus on COMMITMENT size & Try Rally
6 | 2006-03-13 | 2006-03-24 | [7 empty] | 6 |  |  | Introduce Rally to team
7 | 2006-03-27 | 2006-04-07
8 | 2006-04-10 | 2006-04-21
9 | 2006-04-24 | 2006-05-05
10 | 2006-05-08 | 2006-05-19
11 | 2006-05-22 | 2006-06-02
12 | 2006-06-05 | 2006-06-16
Project Averages |  |  | 25 | 66 | 153 | 457 | 955 | 372 | 199 |  | 1027 | 290
|  |  | 37.88% |  | 33.48% |  |  | 38.95% |  |  |  | 28.24%
[11 empty] | 19.38% | 145.7%
Formulas:
End = [Dates]+11
Dates = [Dates, row above]+14

## Template
Note: Contact Person is SME, not the developer - the team owns all the tasks.
Story # | Points | Date Added | Description | Contact Person | Thr | Fri | Mon | Tue | Wed | Thr | Fri | Mon | Tue | Wed | Stories Accepted
| Task # |  |  |  | 2006-09-07 | 2006-09-08 | 2006-09-11 | 2006-09-12 | 2006-09-13 | 2006-09-14 | 2006-09-15 | 2006-09-18 | 2006-09-19 | 2006-09-20
Total Estimated Hours: | [14 empty] | x of y
S1 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S2 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
| T6 | 2006-09-07
| T7 | 2006-09-07
| T8 | 2006-09-07
| T9 | 2006-09-07
S3 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S4 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S5 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S6 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S7 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S8 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
S9 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07 | T
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S10 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
| T5 | 2006-09-07
S11 |  | 2006-09-07 | <storydescription text>
| T1 | 2006-09-07
| T2 | 2006-09-07
| T3 | 2006-09-07
| T4 | 2006-09-07
Maint. |  | 2006-09-07 | Maintenance Commitment
| T1 | 2006-09-07 | Maximum Maintenance time commitment for Sprint | team | 2006-09-07: 0; 2006-09-08: 0
Below Not in Burndown
S-Maintenance |  |  | MAINTENANCE actual hours totals |  | 2006-09-07: 0
| M1 |  | Category 1
| M2 |  | Category 2
| M3 |  | Category 3
| M4 |  | Category 4
| M5 |  | Category 5
| M6 |  | Category 6
| M7 |  | Failed Jobs
| M8 |  | Other
Team Capacity Estimates
|  |  | Who | Tot.Hrs. | 2006-09-07: Maint.; 2006-09-08: Proj.; 2006-09-11: Tasks
E1
E2
E4
E5
QA
New
|  |  | Core Team Totals | 0 | 2006-09-07: 0; 2006-09-08: 0; 2006-09-11: 0
PO
SM
EM
SP