## 1-1
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Total Time (hr) | Estimate Error %
1 | Attend Senior Project Expectations & Meet Faculty Coach Session | 2014-08-29 | All | 2 | 1 | Complete | 8.25 | 7.8 | -5.7692
2 | Hold Project Kick-off with Sponsor | 2014-08-29 | All | 1 | 0.3 | Complete
3 | Decide on Team name | 2014-08-29 | All | 0.15 | 0.15 | Complete
4 | Begin Tracking Time/Effort | 2014-08-29 | Rich | 1 | 1.25 | Complete
5 | Submit request to SE Admin to create team account | 2014-08-29 | Rich | 0.1 | 0.1 | Complete
6 | UI Mockup | None | Rich | 3 | 4 | Complete
7 | Requirements Questions Brainstorming | None | All | 1 | 1 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 2.75
[7 empty] | Jacob Siegel | 2.75
[7 empty] | James Fitzgerald | 2.75
[7 empty] | Richard Laughlin | 7.1

## 1-2
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Weekly Sponsor Meeting | 2014-09-05 | All | 1 | 1 | Complete | 2.6 | 3.3 | 21.2121
2 | Start Project Website | 2014-09-05 | Rich | 1 | 1 | Complete
3 | Inform Faculty Coach & Sponsor of Website URL | 2014-09-05 |  | 0.1 | 0.8 | Complete
4 | Setup Virtual Environment (Optional) | 2014-09-05 |  | 0 | 0 | Complete
5 | Publish first time tracking report | 2014-09-05 | Rich | 0.5 | 0.5 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 1
[7 empty] | Jacob Siegel | 1
[7 empty] | James Fitzgerald | 1
[7 empty] | Richard Laughlin | 1

## 1-3
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Weekly Sponsor Meeting | 2014-09-11 | All | 1 | 1 | Complete | 3.66 | 4.16 | 12.0192
2 | Get approval of project synopsis | 2014-09-11 | All | 1 | 1 | Complete
3 | Discuss overall project plan with sponsor | 2014-09-11 | All | 1 | 1 | Complete
4 | Begin detailed project discussions |  | All |  |  | Complete
5 | Submit project synopsis (<= 250 words) to sponsor and faculty coach | 2014-09-11 | Alex | 0.5 | 0.5 | Complete
6 | Publish team information including synopsis onto website. |  | Rich | 0.08 | 0.08 | Complete
7 | Complete project information survey form |  | Rich | 0.08 | 0.08 | Complete
8 | Submit first draft of development process and project plan for review |  | Jacob |  | 0.5 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 1
[7 empty] | Jacob Siegel | 2
[7 empty] | James Fitzgerald | 3
Richard Laughlin

## 1-4
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 4.5 | 4.5 | 0
2 | Specify development methodology |  |  | 1 | 1 | Complete
3 | Specify product/process metrics to be tracked |  |  | 0.5 | 0.5 | Complete
4 | Document development methodology on website. |  |  | 1 | 1 | Complete
5 | Document product/process metrics on website. |  |  | 1 | 1 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 3
[7 empty] | Jacob Siegel | 3
[7 empty] | James Fitzgerald | 3
Richard Laughlin

## 1-5
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 5 | 4.5 | -11.1111
2 | Risk Assessment | 2014-09-30 | All | 4 | 3.5 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 3.5
[7 empty] | Jacob Siegel | 3
[7 empty] | James Fitzgerald | 4.5
Richard Laughlin

## 1-6
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 4 | 3 | -33.3333
| Database Design |  |  | 1 | 1 | Complete
| System Architecture Design |  |  | 2 | 1 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 2.5
[7 empty] | Jacob Siegel | 3.5
James Fitzgerald
Richard Laughlin

## 1-7
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 1.5 | 1.5 | 0
2 | Mid Term Peer Evaluation |  |  | 0.5 | 0.5 | Complete
3 | R1 Implementation |  | All |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 5
[7 empty] | Jacob Siegel | 4
[7 empty] | James Fitzgerald | 5
Richard Laughlin

## 1-8
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 2 | 1.75 | -14.2857
2 | Mid term project review with sponsor and coach. |  |  | 1 | 0.75 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 2
[7 empty] | Jacob Siegel | 4
James Fitzgerald
Richard Laughlin

## 1-9
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 6 | 5 | -20
2 | Discuss adjustments with faculty coach |  |  | 1 | 0.5 | Complete
3 | Discuss Sponsor's attendance at the interim presentation |  |  |  |  | Complete
4 | Crawler Design |  | All | 1 | 1 | Complete
| Crawler API Research |  | James | 3 | 2.5 | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 4
[7 empty] | Jacob Siegel | 4
[7 empty] | James Fitzgerald | 3
Richard Laughlin

## 1-10
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 1 | 1 | 0
2 | Interim Presentation Scheduled |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 1
[7 empty] | Jacob Siegel | 2
James Fitzgerald
Richard Laughlin

## 1-11
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 1 | 1 | 0
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 4
[7 empty] | Jacob Siegel | 4
James Fitzgerald
Richard Laughlin

## 1-12
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 3
[7 empty] | Jacob Siegel | 2
James Fitzgerald
Richard Laughlin

## 1-13
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
2 | Draft Interim Presentation |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 3
[7 empty] | Jacob Siegel | 2
James Fitzgerald
Richard Laughlin

## 1-14
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
[7 empty] | Alex Kelley | 1
[7 empty] | Jacob Siegel | 2
James Fitzgerald
Richard Laughlin

## 1-15
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
[7 empty] | Jacob Siegel | 6
James Fitzgerald
Richard Laughlin

## 1-16
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  | 1 | 1 | Complete | 1 | 1 | 0
2 | Discuss sponsor's possible attendance at interim reflection meeting |  |  |  |  | Complete
3 | Interim Presentation Evaluations |  |  |  |  | Complete
4 | Interim Team Self Assessment |  |  |  |  | Complete
5 | Project website and repository on an SE machine up to-to-date |  |  |  |  | Complete
6 | Course Evaluation |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
[7 empty] | Jacob Siegel | 2
James Fitzgerald
Richard Laughlin

## 1-Fin
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
2 | Attend Interim Reflection Meeting |  |  |  |  | Complete
3 | Summary of Reflection Meeting |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## B-1
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
[7 empty] | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## B-2
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
[7 empty] | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## B-3
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
[7 empty] | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## B-4
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
[7 empty] | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## B-5
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
[7 empty] | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-1
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | State-of-project discussion with sponsor and coach |  |  | 1 | 1 | Complete | 1 | 1 | 0
2 | Project plan updated for second term |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-2
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-3
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-4
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-5
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-6
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-7
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
2 | Mid term peer evaluation |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-8
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Mid-term project review with sponsor and coach |  |  | 1 | 1 | Complete | 1 | 1 | 0
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-9
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0.5 | 0.5 | 0
2 | Discuss adjustments with faculty coach |  |  | 0.5 | 0.5 | Complete
3 | Coordinate with sponsor for attendance at final presentation |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-10
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 1 | 1 | 0
2 | Final Presentation Scheduled |  |  |  |  | Complete
3 | Project Poster Concept |  |  | 1 | 1 | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-11
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 1.5 | 2 | 25
2 | Preliminary project poster |  |  | 1.5 | 2 | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-12
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
2 | Project poster delivered to senior project coordinator |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-13
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 3 | 4.5 | 33.3333
2 | Poster Presentation During Software Engineering Project Day |  |  | 2 | 2.5 | Complete
3 | Draft Final Presentation |  |  | 1 | 2 | Complete
4 | Technical Report Outline |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-14
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-15
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 5 | 3 | -66.6667
2 | Discuss Sponsor's possible attendance at final reflection meeting |  |  |  |  | Incomplete
3 | Final Presentation Evaluations |  |  | 2 | 2 | Complete
4 | Draft Technical Report |  |  | 2 |  | Complete
5 | Team Final Self Assessment |  |  |  |  | Complete
6 | Summary of Project Reflection Meeting |  |  | 1 | 1 | Complete
7 | Project website and repository on SE machine up to date |  |  |  |  | Complete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin

## 2-Fin
Task | Description | Due Date | Team Members | Estimated Time (hr) | Actual Time (hr) | Status | Total Estimate (hr) | Actual Time (hr) | Estimate Error %
1 | Project Sponsor Meeting |  |  |  |  | Incomplete | 0 | 0 | #DIV/0!
2 | Attend final reflection meeting |  |  |  |  | Complete
3 | Final project artifacts |  |  |  |  | Incomplete
4 | Final technical report |  |  |  |  | Incomplete
5 | Summary of final reflection meeting |  |  |  |  | Incomplete
6 | Senior Survey |  |  |  |  | Incomplete
[7 empty] | Member Name | Total Time (hr)
Alex Kelley
Jacob Siegel
James Fitzgerald
Richard Laughlin