## Sheet1
ID | Description | % Chance | Impact (weeks) | Risk Exposure | Mitigated? | Mitigation Strategy | Total Risk Exposure
1 | Process Risks | [5 empty] | 16.01
1.1 | Change in customer requirements | 15% | 4 | 0.6 | Yes | Freeze requirements
1.2 | Scope creep | 5% | 4 | 0.2 | Yes | Determine comprehensive set of requirements and freeze them
1.3 | Configuration issues ; development hardware/software | 50% | 2 | 1 | Yes | Complete early
1.4 | Sponsor organization politics | 10% | 2 | 0.2 | Yes | Ignore
1.5 | Requirements misunderstood | 5% | 5 | 0.25 | Yes | Spend time to understand all requirements
1.6 | GOLD PLATING | 50% | 2 | 1 | No | Don't
1.7 | Artificial deadlines pushing back functionality | 70% | 4 | 2.8 | No | Freeze deadlines
1.8 | Microsoft SQL Server 2008 ; adaptation bydevelopment team | 10% | 1 | 0.1 | Yes | Complete early
1.9 | Specification Breakdown | 33% | 2 | 0.66 | Yes | 1.5
1.1 | Lack of interest from userbase -> missed requirements | 25% | 2 | 0.5 | Yes | Ignore & let VA solve
1.11 | Unrealistic estimation | 75% | 4 | 3 | No | Use statistics for similar systems to build estimates
0
2 | Product Risks
2.1 | Inability to provide sufficient input for web crawler | 90% | 5 | 4.5 | No | Design and determine appropriate sources early
2.2 | Change in required security | 8% | 1 | 0.08 | No | 2.5
2.3 | Accessibility requirements underestimated/unfulfilled | 10% | 1 | 0.1 | yes | Write from beginning with requirements in mind
2.4 | Difference between system and local process | 50% | 2 | 1 | yes | Determine process and freeze; early releases
2.5 | Insufficient system security ; vandalism | 2% | 1 | 0.02 | yes | Employ proper security to begin with; remove if unnecessary
2.6 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0