## Session Management
ID | Module | Problem | Priority | Status | Owner | Comments
1 | Warning Emails | Not finished | Medium | Open | Mark | Partially implemented - need to add setting in session selection screen and need to run warning email threads on server.
2 | All | Out of memory error | High | Open |  | After phases have been switched many times (upwards of 50) the phone starts to run out of memory and threads stop being started
3 | Login | htpasswd file cannot be read | Medium | Open | Bryan | Not feasible - Apache uses a Salt when encoding that is extremely difficult to duplicate in Java code

## Brainstorm
ID | Module | Problem | Priority | Status | Owner | Comments
5 | Topbar | Timerticker not always counting down | High | Open | Ryan | BS17 - probably related to the memory issue
10 | Grouping | After moving that item to a group, click and hold on that item. | Medium | Open | Rob | BS55
12 | Grouping | Edit group name does not refresh | High | Open | Rob | BS57 - only fails until you do an action
13 | Voting | + - should be disabled until the user clicks an item, - should be disabled when there are no votes cast, + should be disabled when there are no votes left | Low | Open | Mark | BS63, BS65, BS67

## Affinity Diagram
ID | Module | Problem | Priority | Status | Owner | Comments
| Grouping | Forum adapters are getting screwed up | High | Open | Ryan | AD48/49/67/68
| Needs Generation/Grouping | Group names go off the page | Low | Open | Mark
| Sentence Creation | Ideas should be highlighted instead of the circles | Low | Open | Mark