## Sheet1
Week: | Task: | Notes:
Week 1 - T | Intro
Week 1 - R | Info and Team Assignments
Brainstorming
Week 2 - T | Requirements + Set up Project Management
Week 2 - R | Requirements
Week 3 - T | Prototypes
Week 3 - R | Discuss Prototypes with Sponsor
Week 4 - T | Start Design
Week 4 - R | Finish Design
Week 5 - T | Start Coding | Idea Generation + Session Management
Week 5 - R | Coding
Week 6 - T | Coding | Voting/Grouping + Session Management, Ed's Vacation
Week 6 - R | Coding | Ed's Vacation
Week 7 - T | Coding | Result/Grouping + Session Management, Ed's Vacation
Week 7 - R | Coding | Meet with Ed for Iteration 3(Show Ed Login, Idea Generation, part of grouping and voting
Week 8 - T | Integration | Ed left for Dubai
Week 8 - R | Integration | Ed left for Dubai
Week 9 - T | Usability Test and Acceptance Test | Ed will be back + planned on meeting with Ed to go over working Prototype
Week 9 - R | Fix Remaining Defect + Prepare Presentation | Mid Quarter Presentation Preparation
Week 10 - T | Mid Quarter Presentation | Give Presentation
Week 10 - R | Post Presentation Meeting with Ludi
Finals Week | Coding + bug fix + break
Break | Possibly some coding and bug fixing, otherwise nothing
Fall Quarter
Week 1 - M | Affinity Diagram - Requirements | Meet with Ed to go over requirements for AD again
Week 1 - W | Requirements | Start requirments document
Week 2 - M | Prototypes | simple prototypes / present to Ed and get feedback
Week 2 - W | Prototypes | Revise prototypes and present to Ed for feedback
Week 3 - M | Discuss prototypes with sponsor
Week 3 - W | Start Design
Week 4 - M | Finish Design
Week 4 - W | Coding
Week 5 - M | Coding
Week 5 - W | Coding
Week 6 - M | Coding
Week 6 - W | Coding / Integration
Week 7 - M | Coding / Integration
Week 7 - W | Coding / Integration
Week 8 - M | Start Test Plan
Week 8 - W | Finish Test Plan | Fix bugs as time allows
Week 9 - M | Documentation / Poster / Presentation | Fix bugs as time allows
Week 9 - W | Documentation / Poster / Presentation | Poster presentation to SSE
Week 10 - M | Presentation
Week 10 - W | Post Mortem
End of Fall Quarter