Risk Plan©

For FACETs F4

Document Control

Document Information

| Document | Information |
| --- | --- |
| Document Owner | Team6g |
| Issue Date | 06/14/2010 |
| Last Saved Date | 06/21/2010 |
| File Name | Risk Plan |

Document History

| Version | Issue Date | Changes | Responsible |
| --- | --- | --- | --- |
| 1.0 | 06/14/2010 | Initial document creation | Arnold King |
| 1.1 | 06/15/2010 | General risks identified | Arnold King |
| 1.2 | 06/21/2010 | Complete risk category, risk quantification system and added more possible risks | Arnold King |
| 1.3 | 06/24/2010 | Filled in priority list | Arnold King |
| 1.4 | 06/29/2010 | Filled in risk mitigation | Arnold king |

Document Approvals

| Role | Name© | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor |  |  |  |

Table of Contents

1	Risk Identification	1

1.1	Definition	1

1.2	Categories	1

1.3	Risks	1

2	Risk Quantification	3

2.1	Likelihood	3

2.2	Impact	3

2.3	Priority	4

3	Risk Plan	6

3.1	Mitigation Strategy	6

4	Risk Process	7

4.1	Purpose	7

4.2	Procedures	7

4.3	Register	7

5	Appendix	7

# Risk Identification

A series of risk categories is identified and for each category a suite of potential risks is listed. This may take place during a ‘Risk Planning’ workshop, involving each of the key project stakeholders who are involved in / affected by the project. This may include the project sponsor, manager, team, suppliers, and in some cases, even the customer. Each of the risks identified is described in detail and documented within the Risk Plan.

## Definition

A formal definition of risk in this project.

“A risk is defined as any event which is likely to adversely affect the ability of the project to achieve the defined objectives”. ©

## Categories

Identify the likely categories of risks for this project. Each risk category is a particular aspect of the project which is likely to experience a risk during the lifecycle of the project.

- Requirements

- Schedule

- Deliverable

- Scope

- Issues

- Acceptance

- Communication

- Resource

- Technology

- Others

## Risks

Identify the likely risks for each category provided above by completing the following table. Each risk identified should be allocated a unique identifier (id) number.

| Category© | Description | ID |
| --- | --- | --- |
| Requirements | - The requirements have not been clearly specified - The requirements specified do not match the customer's needs - The requirements specified are not measurable© - Inability to handle requirements changes from customers | 1.1 1.2 1.3 1.4 |
| Schedule | - The schedule doesn’t provide enough time to complete the project - The schedule doesn’t list all of the activities and tasks required - The schedule doesn’t get integrated and followed through out the project. - The schedule cannot accommodate the requirements and scope changes | 2.1 2.2 2.3 2.4 |
| Deliverables | - The deliverables required by the project are not clearly defined - Clear quality and performance requirements for each deliverable have not been defined - The deliverable produced doesn’t meet the quality and performance requirements defined | 3.1 3.2 3.3 |
| Scope | - The scope of the project is not clearly outlined - The project is not undertaken within the agreed scope - Requirements and scope changes negatively impact on the project | 4.1 4.2 4.3 |
| Issues | - Project issues are not resolved within an appropriate timescale - Similar issues continually reappear throughout the project - Unresolved issues become new risks to the project© | 5.1 5.2 5.3 |
| Acceptance | - The criteria for accepting project deliverables aren’t clearly defined - Customers do not accept the final deliverables of the project - The acceptance process leaves the customer dissatisfied | 6.1 6.2 6.3 |
| Communication | - Lack of communication between team members causes project issues and delay project plan - Key project stakeholders are ‘left in the dark’ about progress - Lack of project sponsor’s feedback | 7.1 7.2 7.3 |
| Resource | - Team members allocated to the project are not suitably skilled - There is a shortage of equipment available when required | 8.1 8.2 |
| Technology | - Unfamiliarity with new technologies causing project schedule delay - Unfamiliarity with new technologies causing reduction of final product quality and performance - Unable to use existing technologies to produce deliverables defined | 9.1 9.2 9.3 |
| Others | - Developers gold-plating features resulting in delay schedule and unfinished functions | 10.1 |

# Risk Quantification

The likelihood of each risk's eventuating and its impact on the project and surrounding needs to be addressed. Each risk is prioritized according to the likelihood and impact rating and the low, medium and high priority risks are clearly marked for attention.

## Likelihood

Scoring system for measuring the ‘likelihood’ of the risk eventuating.

| Title | Score© | Description |
| --- | --- | --- |
| Very Low | 20 | Highly unlikely to occur; however, still needs to be monitored as certain circumstances could result in this risk becoming more likely to occur during the project |
| Low | 40 | Unlikely to occur, based on current information, as the circumstances likely to trigger the risk are also unlikely to occur© |
| Medium | 60 | Likely to occur as it is clear that the risk will probably eventuate |
| High | 80 | Very likely to occur, based on the circumstances of the project |
| Very High | 100 | Highly likely to occur as the circumstances which will cause this risk to eventuate are also very likely to be created |

## Impact

Scoring system for measuring the ‘impact’ of the risk.

| Title | Score | Description© |
| --- | --- | --- |
| Very Low | 20 | Insignificant impact on the project. It is not possible to measure the impact on the project as it is minimal |
| Low | 40 | Minor impact on the project; less than 5% deviation in scope, scheduled end-date or final product quality |
| Medium | 60 | Measurable impact on the project; 5-10% deviation in scope, scheduled end-date or final product quality |
| High | 80 | Significant impact on the project; 10-25% deviation in scope, scheduled end-date or final product quality |
| Very High | 100 | Major impact on the project; more than 25% deviation in scope, scheduled end-date or final product quality |

## Priority

Establish the priority of each risk by identifying the likelihood of the risk's eventuating and its impact on the project. The priority score should be calculated as follows:

- Priority equals the average Likelihood and Impact score

- This is calculated as Priority = (Likelihood + Impact) / 2©

| ID | Likelihood | Impact© | Priority Score | Rating |
| --- | --- | --- | --- | --- |
| 1.1 | 60 | 80 | 70 | High |
| 1.2 | 50 | 50 | 50 | Medium |
| 1.3 | 50 | 40 | 45 | Medium |
| 1.4 | 40 | 40 | 40 | Low |
| 2.1 | 80 | 100 | 90 | Very High |
| 2.2 | 20 | 20 | 20 | Very Low |
| 2.3 | 40 | 30 | 35 | Low |
| 2.4 | 50 | 80 | 65 | High |
| 3.1 | 40 | 50 | 45 | Medium |
| 3.2 | 30 | 20 | 25 | Low |
| 3.3 | 50 | 80 | 65 | High |
| 4.1 | 30 | 50 | 40 | Low |
| 4.2 | 20 | 40 | 30 | Low |
| 4.3 | 80 | 90 | 85 | Very High |
| 5.1 | 10 | 20 | 15 | Very Low |
| 5.2 | 10 | 10 | 10 | Very Low |
| 5.3 | 20 | 50 | 35 | Low |
| 6.1 | 30 | 50 | 40 | Low |
| 6.2 | 20 | 30 | 25 | Low |
| 6.3 | 50 | 40 | 45 | Medium |
| 7.1 | 30 | 40 | 35 | Low |
| 7.2 | 25 | 35 | 30 | Low |
| 7.3 | 40 | 60 | 50 | Medium |
| 8.1 | 60 | 80 | 70 | High |
| 8.2 | 30 | 40 | 35 | Low |
| 9.1 | 50 | 60 | 55 | Medium |
| 9.2 | 50 | 60 | 55 | Medium |
| 9.3 | 40 | 100 | 70 | High |
| 10.1 | 20 | 30 | 25 | Low |

Rating Table

The Rating is based on the calculated Priority score.

| Priority Score | Priority Rating | Color Code |
| --- | --- | --- |
| 0 – 20 | Very low | Blue |
| 21 – 40 | Low | Green |
| 41 – 60 | Medium | Yellow |
| 61 – 80 | High | Orange |
| 81 – 100 | Very High | Red |

# Risk Plan

A Risk Plan includes a set of actions to be taken to avoid, transfer or mitigate each risk, based on the priority of the risk assigned.

## Mitigation Strategy

For each risk identified and in priority order, list:

- the preventative actions to be taken to reduce the likelihood of the risk's occurring

- the contingent actions to be taken to reduce the impact should the risk eventuate©

Higher priority risks should be assigned more comprehensive actions where possible.

| Rating | ID | Preventative Actions | Contingent Actions |
| --- | --- | --- | --- |
| Very High | 2.1 | Consistently negotiate with project sponsor to develop a reachable scope and update the schedule based on scope | Complete the currently developing application as much as possible and re-negotiate scope with project sponsor |
| Very High | 4.3 | Re-evaluate requirements after each increment and negotiate with project sponsor for a reachable scope | Negotiate with project sponsor to reduce the deliverable scope of the product |
| High | 1.1 | Perform requirements evaluation after each increment and meet with project sponsor to clarify requirements | Meet with project sponsor to clarify the requirements and find a reachable solution |
| High | 8.1 | Gather and share resources among team members to reduce productivity downtime; assign an “expert” or experienced team member to assist others; choose a technology familiar to all team members | Research online for solution and negotiate with project sponsor to find an alternative solution |
| High | 9.3 | Create prototypes with existing technologies in the early stage of product development and re-evaluate the risk and technologies used | Negotiate with project sponsor to reduce scope and requirements to make use of the technologies chosen |
| High | 2.4 | Discuss with project sponsor after each increment to make sure changes is reasonable, then change scope and update schedule | Accommodate as many changes as possible based on existing schedule and re-negotiate scope with project sponsor |
| High | 3.3 | Re-evaluate performance and quality requirements after each increment and prototyping | Negotiate with project sponsor for possible future improvement or existing issues to be solved by next senior project team |
| Medium | 9.1 | Negotiate with project sponsor based on our understanding and skills available to find a reachable scope | Negotiate with project sponsor to reduce project scope |
| Medium | 9.2 | Negotiate with project sponsor based on our understanding and skills available to find a reachable and realistic scope for performance and quality | Negotiate with project sponsor to reduce product quality and performance |
| Medium | 7.3 | Ask for feedback after each prototype and increment, also meeting with project sponsor weekly to gather feedback | Gather feedback from other possible stakeholders, e.g. student user, project advisor etc. |
| Medium | 1.2 | Create prototypes and re-evaluate requirements based on feedback gathered from prototyping | Negotiate with project sponsor for possible future improvements from the next senior project team |
| Medium | 1.3 | Ask project sponsor for clarification of requirements and use prototype to measure the requirements | Ask for clarification and re-negotiate requirements |
| Medium | 3.1 | Every week, ask project sponsor and advisor to clarify properties of deliverables and update project milestone | Negotiate with project sponsor and advisor for a reachable project deliverables based on reaming time and schedule |
| Medium | 6.3 | Perform prototype and ask for customer satisfaction level after each prototypes and increments | Negotiate with project sponsor (customer) for possible future improvements and provide explanation for the element that dissatisfied the him |
| Low | 1.4 | Allocate time and process in the development plan for customer evaluation and requirements changes | Allocate additional time to fulfill scope and requirements changes; re-negotiate scope with project sponsor |
| Low | 4.1 | Ask project sponsor for project scope in the early stage of development, and re-evaluate and clarify scope after each prototype and increment | Ask project sponsor for clarification and negotiate scope based on remaining time |
| Low | 6.1 | Create acceptance test file and perform acceptance test based on requirements and re-evaluate acceptance test after each increment | Ask project sponsor for approval of acceptance test and update acceptance test based on feedback |
| Low | 2.3 | Use Redmine to track and update project schedule | Create new schedule or update existing schedule to fit current progress |
| Low | 5.3 | Keep track of a list of issues/bugs/unfinished tasks | Resolve each item of the list when possible and update risk plan |
| Low | 7.1 | Use project website, Redmine, Google Groups and emails to keep in contact | Perform team meeting to discuss possible changes to project schedule and update project plan |
| Low | 8.2 | Use resource from project advisor, project sponsor and use our own resources | Find possible resources from other stakeholders or developers |
| Low | 4.2 | Use prototype to gather feedback and meet with project sponsor to make sure the project is within scope | Re-negotiate deliverable scope with project sponsor |
| Low | 7.2 | Identify all stakeholders in SRS and provide update of the project progress through website/Redmine | Include stakeholders in meeting with developers |
| Low | 3.2 | Include performance and quality requirements in SRS and re-evaluate these properties after each increment | Meet with project sponsor to clarify quality and performance requirements as soon as possible |
| Low | 6.2 | Gather project sponsor feedback after every increment and update requirements and scope to deliver an acceptable deliverable | Suggest future improvements on the existing system and negotiate to implement additional changes based on project sponsor’s need |
| Low | 10.1 | Approval from project sponsor will be needed in order to add additional features. All additional features will be low priority features. It will only be implemented if approved and able to fit into the schedule without affecting any of the development plan | Prioritized additional features as the lowest priority features and update schedule and project plan if the features can be added, otherwise re-negotiate scope with project sponsor |
| Very Low | 2.2 | Keep a list of activities on Redmine as activities tracker. Also record the activities done in each meeting, project milestone and weekly status of each team member | Search Redmine and project milestone for tasks and activities information |
| Very Low | 5.1 | Determine the affect of the issue, update risk plan to keep track of issue | Add issue to a list of incomplete tasks/problems, which will need to be resolved in the next increment |
| Very Low | 5.2 | Keep a list of incomplete issue and use it to track similar issues. Search list to determine if similar issues have been resolved and apply solution to current issue | Add issue to a list of incomplete tasks/problems, which will need to be resolved in the next increment |

# Risk Process

## Purpose

Describe the purpose of risk management and the general process for the identification and mitigation of risks within the project.

## Procedures

Provide a diagrammatic representation of the processes undertaken to identify and mitigate risks within the project.

## Register

The ‘Risk Register’ is a database which records and tracks the progress of all risks through to completion. Insert a copy of the Risk Register here.

# Appendix

Attach any documentation you believe is relevant to the Risk Plan. For example:

- Other project documentation (Business Case, Feasibility Study, Terms of Reference, Project Plan, Resource Plan, Financial Plan, Quality Plan)

- Organizational Risk Management Policies, Standards, Guidelines or Procedures

- Risk documentation from other related projects

- Other relevant information or correspondence. ©