## SE361 Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Prevention Strategy | Migitation Plan | Status
1 | Outside workload increases and students can't commit the alloted hours | 0.6 | high | 6 | Commit to realistic hours. Frequent standup meetings (twice a week) to discuss roadblocks
2 | Optimization implementation is more complex than expected | 0.5 | medium | 2.5 | Do extensive research and planning before implementing the code | Proactively ask sponsors when questions come up
3 | Sponsor is not available for meeting(s) | 0.1 | low | 0.1 | Open communication about availability
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0
[8 empty] | Impact | Weight
0
[8 empty] | low | 1
[8 empty] | medium | 5
[8 empty] | high | 10