## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Y | 1.5 |  | Meet with Professor Reichlmayr a bit early to briefly discuss project, and attend senior project talk by Professor Valino
Y | 1.5 |  | Meet with Professor Reichlmayr and team to discuss project, what the team did last year, etc
| 3 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Meet with Project Sponsor to discuss Project
|  | 1 | Work on Project Website
|  | 2 | TOTAL TIME
Issues

## Instructions
Your Name: | Philip Rotoli
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Y | 1 | 1 | Meet with Project Sponsor to discuss Project
Y | 1 | 1 | Work on Project Website
Y | 1 |  | Completed Project Synopsis
| 3 | 2 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Publish Project Synopsis
|  | 1 | Complete Project Survey
|  | 2 | Continue project discussions and planning
|  | 4 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 1 | 1 | Complete Project Survey
| 1 | 1 | Complete Project Survey
| 2 | 2 | Continue project discussions and planning
| 4 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Complete Domain Model
|  | 2 | Meet with Beltz
|  | 3 | Complete Project Plan
|  | 2 | Other
|  | 10 | TOTAL TIME
Issues

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Complete Domain Model
| 2 | 2 | Meet with Beltz
| 3 | 3 | Complete Project Plan
| 3 | 3 | Coding back end
| 11 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Continue coding back end
|  | 3 | Meet with group
|  | 4 | Other
|  | 10 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Continue coding back end
| 3 | 3 | Meet with group
| 4 | 4 | Other
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Continue coding backened
|  | 2 | Meet with sponsors
|  | 10 | TOTAL TIME
Issues

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 8 | 8 | Continue coding backened
| 1 | 2 | Meet with sponsors
| 2 |  | Meet with group
| 11 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Complete APIs
|  | 5 | Complete Account Rules
|  | 10 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 5 | 5 | Worked on APIs
| 5 | 5 | Worked on Account Rules
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 5 | Work on APIs
|  | 5 | Work on Account Rules
|  | 1 | Meet with team
|  | 11 | TOTAL TIME
Issues

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 7 | 5 | Work on APIs
| 0 | 5 | Work on Account Rules
| 1 | 1 | Meet with team
| 8 | 11 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Work on APIs
|  | 5 | Work on Account Rules
|  | 3 | Meet with team/sponsor
|  | 10 | TOTAL TIME
Issues

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 2 | 2 | Work on APIs
| 5 | 5 | Work on Account Rules
| 3 | 3 | Meet with team/sponsor
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 2 | Work on APIs
|  | 5 | TOTAL TIME
Issues

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Meet with team/sponsor
| 2 | 2 | Work on APIs
| 5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 2 | Work on APIs
|  | 2 | Work on projection
|  | 7 | TOTAL TIME
Issues

## 1-Wk11
First Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Meet with team/sponsor
| 2 | 2 | Work on APIs
| 5 | 5 | Work on CODE
| 10 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 8 | WORK ON CODE
|  | 11 | TOTAL TIME
Issues

## 1-Wk12
First Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Meet with team/sponsor
| 8 | 2 | WORK ON CODE
| 11 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 8 | WORK ON CODE
|  | 11 | TOTAL TIME
Issues

## 1-Wk13
First Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Meet with team/sponsor
| 8 | 2 | Work on CODE
| 11 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
Thanksgiving Break
|  | 0 | TOTAL TIME
Issues

## 1-Wk14
First Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
| 0 | 3 | Meet with team/sponsor
| 0 | 2 | Work on APIs
| 0 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 8 | WORK ON CODE
|  | 11 | TOTAL TIME
Issues

## 1-Wk15
First Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
| 3 | 3 | Meet with team/sponsor
| 0 | 2 | Work on APIs
| 8 |  | WORK ON CODE
| 11 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Meet with team/sponsor
|  | 5 | Presentation
|  | 15 | WORK ON CODE
|  | 23 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
|  | 3 | Meet with team/sponsor
|  | 2 | Work on APIs
|  | 2 | Work on projection
| 0 | 7 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
| 0 | 0 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
3 | 2 | 3 | 4 | 4 | 11 | 11 | 10 | 10 | 10 | 11 | 10 | 10 | 11 | 8 | 10 | 10 | 5 | 5 | 7 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-fe | t2-fa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0