## Story Points
Story Points
Sprint | Brian H | Brian S | Maggie H | Jason G | Total | Other
Sprint #1 Estimated | 12 | 13 | 14 | 14 | 53
Sprint #1 Completed | 12 | 13 | 1 | 14 | 40
Sprint #2 Estimated | 15.25 | 16.25 | 17.25 | 13 | 61.75
Sprint #2 Completed | 3.25 | 1.25 | 4.25 | 1.25 | 10 | Many blocked stories pushed to next sprint
Sprint #3 Estimated | 25.5 | 26 | 26 | 24 | 101.5
Sprint #3 Completed | 25.5 | 26 | 26 | 16 | 93.5
Sprint #4 Estimated | 16 | 17 | 14 | 25 | 72
Sprint #4 Completed | 13 | 7 | 7 | 5 | 32
Estimated | Beginning of sprint
Completed | Completed by end of sprint

## Defects
Defects found per sprint
Moved to | https://github.com/themolecularmoose/the-moose/issues
Sprint # | Defect #
1 | 0
2 | 1
3 | 2
4 | 3