## SE361 Risks
Risk ID | Description of Risk | Probability (0 - 1) | Impact (low, med, high) | Exposure | Classification | Owner | Prevention Strategy | Migitation Plan | Status
9 | Scope creep due to lack of specific requirements | 0.75 | high | 7.5 | Requirements |  | None | make game design high priority to finish and solidify requirements well before game is completed | mitigation in progress
10 | Game is not playable or fun due to no requirements for playability of product | 0.75 | high | 7.5 | Requirements |  | None | (may not be conclusive) usability testing | mitigation planned for future
8 | Project ends incomplete due to poor estimation of schedule | 0.5 | high | 5 | Schedule |  | acquire feasability evaluation from IGM professor experienced with Unity | (Does not completely mitigate) scrum iteration deliverables ensure at least some deliverable | prevention in progress, mitigation on going
15 | Lack of 3D modeling experience stalls project | 0.75 | medium | 3.75 | Team Experience |  | continually learn about 3D modeling | Acquire artist or can't be mitigated | prevention on going
14 | Lack of game tool experience stalls project | 0.75 | medium | 3.75 | Team experience |  | None | start learning technologies before they are needed and continue learning throughout project | mitigation on going
1 | Requirement elicitaion churn stalls project progress | 0.75 | medium | 3.75 | Requirements |  | None | utilize process that expects requirements churn | mitigation on going
19 | Game has a difficulty curve that is too high (ex. tutorials are unhelpful) | 0.75 | medium | 3.75 | Requirements |  | None | perform usability testing and refactor accordingly | mitigation planned for future
11 | Scrum process is poorly executed and limits team productivity | 0.25 | high | 2.5 | Process |  | continually refine process | switch to a different process | prevention on going
12 | Poor code performance due to lack of experience in game coding | 0.25 | high | 2.5 | Team experience |  | monitor concrete game performance metrics to find performance issues as soon as possible | (May not be effective) refactor game code for performance | prevention not planned
5 | 3D performance costs limit platform flexibility | 0.25 | medium | 1.25 | Technology |  | test on lab computers | (may not be effective) refactor game for performance | prevention on going
17 | Sudden unexpected change in requirements | 0.25 | medium | 1.25 | Requirements |  | None | utilize process that deals with sudden change in requierments well | migation on going
3 | Project ends incomplete due to lack of defined schedule for components | 0.1 | high | 1 | Schedule |  | define schedule | can't be mitigated at project end | (mitigated) broad schedule defined, definition could still be in sufficient
4 | Final product does not meet customer expectations | 0.1 | high | 1 | Requiremets |  | continually deliver game iterations to customer and elicit customer feedback and expectations | (not planned) leave time after product finalization for adjustments | prevention on going
7 | Team is unable to create envisioned game due to lack of game development experience | 0.1 | high | 1 | Team experience |  | continually learn game development technologies and techniques to lower probability | true inability can't be mitigated | prevention on going
6 | Required licenses for development tools not obtainable | 0.05 | high | 0.5 | Technology |  | look at tool licenses to lower probability | (may not be effective) refactor development tools | (prevented) licenses do not apear to pose risk, probablility lowered from 0.2 to 0.05
13 | Chosen game development tools limit game performance | 0.1 | medium | 0.5 | Technology |  | Acquire feasability evaluation from IGM professor experience with Unity | (may not be effective) refactor game tools for performance | prevention in progress
16 | Platform specific issues (For multi platform deployment) | 0.25 | low | 0.25 | Technology |  | test on individual and lab computers | (may not be effective) fix platform specific issues | prevention on going
18 | Poor Documentation and coding practices | 0.25 | low | 0.25 | Process |  | continually increment on game documentation, ensure appropriate coding practices via code reviews via git pul requests | create documentation and refactor code | prevention on going
20 | Sudden equipment failures | 0.02 | medium | 0.1 | Technology |  | None | use source control | (mitigated) reduced impact through use of source control
2 | Game contains incorrect chemistry specifics | 0.1 | low | 0.1 | Domain |  | continually discuss chemistry specifics | refactor project to adjust chemestry specifics | prevention on going
21 |  |  | high | 0
22 |  |  | high | 0
23 |  |  | high | 0
24 |  |  | high | 0
25 |  |  | high | 0
26 |  |  | high | 0
27 |  |  | high | 0 | [5 empty] | Impact | Weight
28 |  |  | high | 0 | [6 empty] | 0
29 |  |  | high | 0 | [5 empty] | low | 1
30 |  |  | high | 0 | [5 empty] | medium | 5
31 |  |  | high | 0 | [5 empty] | high | 10
32 |  |  | high | 0