## Team Totals
Semester 1 | Brian Hansen |  | Maggie Hewitt |  | Brian Spates |  | Jason Greaves |  | Team Totals
Week | Estimate Time | Actual Time | Estimate Time | Actual Time | Estimate Time | Actual Time | Estimate Time | Actual Time | Estimate Time | Actual Time
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3.25 | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Semester Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Average Actual Time Per Week | N/A | #REF! | N/A | #REF! | N/A | #REF! | N/A | #REF! | Total Team Average Per Week | #REF!

## Brian Hansen
Tasks List |  |  |  | Semester 1
Week Number | Estimate Time | Actual Time | Task Description | Week Number | Estimate Time Total | Actual Time Total
1 | 0 | 2 | Look over course materials | 1 | 0 | 3.25
1 | 0 | 1.25 | Meet with sponser | 2 | 4 | 4
2 | 1.5 | 1.5 | Re-learn some basic chemestry | 3 | 6.75 | 4.75
2 | 1.25 | 1.25 | Meet with sponser | 4 | 5.5 | 5.75
2 | 1.25 | 1.25 | Team meeting | 5 | 10 | 10
3 | 2 | 2 | Come up with game ideas with wireframes | 6 | 11 | 9.5
3 | 1.5 | 0 | Project Plan | 7 | 8 | 8.25
3 | 0.5 | 0.25 | Complete project information survey | 8 | 10.75 | 8.5
3 | 1.5 | 1.25 | Team meeting | 9 | 14.5 | 10
3 | 0.25 | 0.25 | Find Survey | 10 | 8.5 | 10.5
3 | 1 | 1 | Create Time/Effort Spread sheet | 11 | 8.5 | 9.25
4 | 1.25 | 1.5 | Sponser Meeting | 12 | 8.5 | 11.25
4 | 1.25 | 1.25 | Thursday Meeting | 13 | 10 | 11
4 | 2 | 2 | Monday Meeting | 14 | 9 | 9.75
4 | 1 | 1 | Risk Table | 15 | 16.5 | 14
5 | 1.25 | 1.25 | Sponser Meeting | 16 | 6 | 7
5 | 0.5 | 0.5 | Install Unity | Semester Total | 137.5 | 136.75
5 | 2 | 2 | Project Plan work
5 | 1.5 | 0 | Weekend Meeting
5 | 1.5 | 1.5 | General work
5 | 1.25 | 1.25 | Thursday Meeting
5 | 2 | 3.5 | Unity Tutorials
6 | 1.25 | 1.25 | Sponser Meeting
6 | 1.25 | 1.25 | Thursday Meeting
6 | 2 | 2 | Unity Tutorials
6 | 1 | 0.5 | Create Metrics Page
6 | 2 | 1 | Create Initial Game Design Document
6 | 1 | 1 | Create git repository
6 | 2 | 2 | Create game start screen
6 | 0.5 | 0.5 | Look into REST and unity
7 | 1.25 | 1.25 | Sponser Meeting
7 | 1.25 | 1.25 | Team Meeting
7 | 1 | 2 | Finish game start screen task
7 | 2 | 2 | Figure and out how to and successfully POST from unity
7 | 0.5 | 0.5 | Update project plan
7 | 1.5 | 0.5 | Work on design document
7 | 0.25 | 0.5 | Peer Eval
7 | 0.25 | 0.25 | Various standups
8 | 1.25 | 0 | Thursday Meeting
8 | 2 | 2 | Working on posting from unity
8 | 1.5 | 1.5 | Weekend Meeting
8 | 2 | 1.5 | Setup molecule server to test posting
8 | 1 | 1 | Models/materials unity tutorial
8 | 1 | 1.5 | Modeling/blender research
8 | 1 | 1 | scrum overhead
8 | 1 | 0 | clean up / reorganize game design document
9 | 1 | 2 | clean up / reorganize game design document cont.
9 | 1.25 | 1.5 | Sponsor Meeting
9 | 1.25 | 1.5 | Thursday Meeting
9 | 6 | 3 | User story 12
9 | 4 | 1 | User story 8
9 | 1 | 1 | Weekend Meeting
10 | 3 | 4 | Finish User story 12 (also not finished)
10 | 3 | 4 | Finish User story 8 (needs timestamp)
10 | 1.25 | 1.25 | Sponser Meeting
10 | 1.25 | 1.25 | Thursday Meeting
11 | 1 | 1 | Monday Meeting
11 | 1.25 | 2 | Sponsor Meeting
11 | 1.25 | 1.25 | Thursday Meeting
11 | 1 | 1 | Pre-Sponsor Meeting
11 | 2 | 2 | Unblock and finish US8
11 | 1 | 1 | Redo Prefab Creation
11 | 1 | 1 | Scrum overhead
12 | 1.25 | 2 | Sponsor Meeting
12 | 1.25 | 1.25 | Thursday Meeting
12 | 2 | 4 | Friday Work Meeting / HUD
12 | 2 | 2 | Saturday Work Meeting / GDD
12 | 2 | 2 | Model Tetrahedral
13 | 1 | 1 | Updating Metrics / Time
13 | 0 | 1 | General
13 | 1.25 | 2 | Tuesday Meeting
13 | 1.25 | 1.5 | Sponsor Meeting
13 | 1.5 | 1.5 | Saturday Meeting
13 | 5 | 4 | US15 Modeling
14 | 6.5 | 7 | US38
14 | 1 | 1.5 | Finish US15
14 | 0.5 | 0.25 | Estimate task
14 | 1 | 1 | Update Game Design
15 | 1.25 | 1.25 | Presentations
15 | 1.5 | 0 | Scrum Planning
15 | 2 | 0 | Presentation Prep
15 | 1.25 | 1.25 | Sponsor Meeting
15 | 1 | 1 | Wednesday Meeting
15 | 1 | 1.5 | Various GIT merging conflicts
15 | 1 | 1.5 | Game Design work
15 | 0.5 | 0.5 | Entering evals
15 | 0.5 | 0.5 | Issue tracking, scrum updates, time updates
15 | 2 | 2 | Saturday Meeting
15 | 4 | 4 | Modeling / Defect Fixes
15 | 0.5 | 0.5 | dont remember what this was
16 | 3 | 4 | Presentation prep
16 | 2 | 2 | presentations
16 | 1 | 1 | Evals
17 | 2 | 0 | more evals
17 | 1.25 | 0 | last meeting
17 | 1 | 0 | deliverables

## Maggie Hewitt
Tasks List |  |  |  | Semester 1
Week Number | Estimate Time | Actual Time | Task Description | Week Number | Estimate Time Total | Actual Time Total
1 | 0 |  | Week 1 Estimate | 1 | 0 | 2.5
1 |  | 2.5 | Class | 2 | 4 | 4
2 | 4 |  | Week 2 Estimate | 3 | 8 | 4.5
2 |  | 2.5 | Class | 4 | 5 | 4.5
2 |  | 1.5 | Research | 5 | 5 | 2.5
3 | 8 |  | Week 3 Estimate | 6 | 10 | 4.5
3 |  | 2.5 | Class | 7 | 2 | 4
3 |  | 2 | Mockups | 8 | 10 | 7.75
4 | 5 |  | Week 4 Estimate | 9 | 6 | 4.5
4 |  | 2.5 | Class | 10 | 10 | 13
4 |  | 1 | Meeting | 11 | 10 | 13
4 |  | 1 | Research | 12 | 10 | 10
5 | 5 |  | Week 5 Estimate | 13 | 10 | 13.5
5 |  | 2.5 | Class | 14 | 10 | 10.5
6 | 10 |  | Week 6 Estimate | 15 | 5 | 12
6 |  | 2.5 | Class | 16 | 0 | 0
6 |  | 2 | Research | Semester Total | 105 | 110.75
7 | 2 |  | Week 7 Estimate
7 |  | 1 | Tracking/ Reporting
7 |  | 3 | Game Related Presentations
8 | 10 |  | Week 8 Estimate
8 |  | 2.75 | Class
8 |  | 2 | Collision with Collectable
8 |  | 1 | Collision with Obsticle
8 |  | 1 | Meeting
8 |  | 0.5 | Peer Eval
8 |  | 0.5 | Scrum Overhead
9 | 6 |  | Week 9 Estimate
9 |  | 2.5 | Class
9 |  | 2 | Test Research
10 | 10 |  | Week 10 Estimate
10 |  | 2.5 | Class
10 |  | 6 | Development
10 |  | 3 | Test Resarch
10 |  | 1 | Meeting
10 |  | 0.5 | Met with Professor
11 | 10 |  | Week 11 Estimate
11 |  | 2.5 | Class
11 |  | 2 | Design Document
11 |  | 2 | Test Document
11 |  | 4.5 | Meetings
11 |  | 2 | Development
12 | 10 |  | Week 12 Estimate
12 |  | 2.5 | Class
12 |  | 3 | Documentation
12 |  | 2 | Meetings
12 |  | 2.5 | Development
13 | 10 |  | Week 13 Estimate
13 |  | 2.5 | Class
13 |  | 5 | Meetings
13 |  | 2 | Documentation
13 |  | 4 | Development
14 | 10 |  | Week 14 Estimate
14 |  | 2.5 | Class
14 |  | 4 | Meetings
14 |  | 4 | Development
14
15 | 5 |  | Week 15 Estimate
15 |  | 4 | Class/Required presentations
15 |  | 6 | Meetings
15 |  | 2 | Deliverables

## Brian Spates
Tasks List |  |  |  | Semester 1
Week Number | Estimate Time | Actual Time | Task Description | Week Number | Estimate Time Total | Actual Time Total
1 |  | 4 |  | 1 | 0 | 4
2 |  | 8 |  | 2 | 0 | 8
3 |  | 10 |  | 3 | 0 | 10
4 |  | 12 |  | 4 | 0 | 12
5 | 12 | 8 |  | 5 | 12 | 8
6 | 8 | 8 |  | 6 | 8 | 8
7 | 12 | 10 | sprint 1 week 1 | 7 | 12 | 10
8 | 10 | 14 |  | 8 | 10 | 14
9 | 12 | 10 |  | 9 | 12 | 10
10 |  | 8 |  | 10 | 0 | 8
11 |  | 1 |  | 11 | 0 | 1
12 |  | 11 |  | 12 | 0 | 11
13 | 15 | 11 |  | 13 | 15 | 11
14 | 10 | 12 |  | 14 | 10 | 12
15 | 5 | 7 |  | 15 | 5 | 7
16 | 8 | 11 |  | 16 | 8 | 11
|  |  |  | Semester Total | 92 | 145

## Jason Greaves
Tasks List |  |  |  | Semester 1
Week Number | Estimate Time | Actual Time | Task Description | Week Number | Estimate Time Total | Actual Time Total
1 | 0 | 2 | Look Over Corse Materials | 1 | 0 | 3.25
1 | 0 | 1.25 | Meet With Sponsor | 2 | 3.5 | 3.5
2 | 1 | 1 | Research Game Dev Theory | 3 | 6.5 | 7
2 | 1.25 | 1.25 | Meet With Sponsor | 4 | 7.75 | 10.75
2 | 1.25 | 1.25 | Team Meeting | 5 | 7.5 | 9.75
3 | 1.25 | 1.25 | Team Meeting | 6 | 8.5 | 8.5
3 | 1 | 2 | Design Ideas | 7 | 16 | 11
3 | 2 | 1.5 | Flesh out Idea | 8 | 7.25 | 8.5
3 | 1.25 | 1.25 | Team Meeting | 9 | 7.75 | 8.25
3 | 1 | 1 | Download and Install Unity | 10 | 8.5 | 7.5
4 | 1.25 | 1.5 | Pre Meeting meeting | 11 | 14.5 | 10
4 | 1.25 | 1.5 | Team Meeting | 12 | 7.5 | 10
4 | 1.25 | 1.75 | Team Meeting | 13 | 7.75 | 9.25
4 | 4 | 6 | Learn Unity | 14 | 1 | 1
5 | 1.25 | 1.5 | Team Meeting | 15 | 15.5 | 10.5
5 | 1.25 | 1.25 | Team Meeting | 16 | 6.25 | 5.75
5 | 1 | 1 | Pre Meeting meeting | Semester Total | 125.75 | 124.5
5 | 4 | 6 | Learn Unity
6 | 1.25 | 1.25 | Team Meeting
6 | 1.25 | 1.25 | Team Meeting
6 | 2 | 2 | Research what makes a game fun
6 | 4 | 4 | More playing with Unity
7 | 1.25 |  | Team Meeting
7 | 1.25 |  | Team Meeting
7 | 1 | 1 | Link Start Screen element to switch to main game scene
7 | 1 | 1 | Setup 3D sandbox
7 | 2 | 3 | Setup 3D player-entity navigation
7 | 1 | 0.5 | Add collectibles to sandbox
7 | 3 | 1 | Create 3D model of player-entity
7 | 3 | 1 | Create 3D model of collectibles
7 | 2 | 3 | Research gaming, education, playability
7 | 0.5 | 0.5 | Look into app store licensing restrictions
8 | 1.25 | 1.25 | Team Meeting
8 | 1.25 | 1.25 | Team Meeting
8 | 1.25 | 1.5 | Team Meeting
8 | 0.5 | 0.5 | Peer Evaluations
8 | 1 | 1 | Scrum Overhead
8 | 2 | 3 | Finalizations on US3
9 | 1.25 | 1.5 | Team Meeting
9 | 1.25 | 1.5 | Team Meeting
9 | 1.25 | 1.25 | Team Meeting
9 | 2 | 2 | Create Win State
9 | 2 | 2 | Get score for collectables
10 | 1.25 | 1.25 | Team Meeting
10 | 1.25 | 1.25 | Team Meeting
10 | 1 | 1 | Team Meeting
10 | 2 | 2 | Created a way to get time to complete level
10 | 2 | 1 | Looked into posting
10 | 1 | 1 | Team Meeting
11 | 1.25 | 1.75 | Team Meeting
11 | 1.25 | 1.25 | Team Meeting
11 | 2 | 1 | Create Base
11 | 4 | 2 | Start Level at base
11 | 4 | 3 | Return to ship to deposit collectables
11 | 2 | 1 | Iterate on game design
12 | 1.25 | 1.25 | Team Meeting
12 | 1.25 | 1.25 | Team Meeting
12 | 1 | 1 | Iterate on game design
12 | 1 | 1 | HUDs
12 | 2 | 4 | Team Meeting/Dev Meeting
12 | 1 | 1.5 | Finish US9
13 | 1.25 | 1.75 | Team Meeting
13 | 1.25 | 1.25 | Team meeting
13 | 1.25 | 1.5 | Team Meeting
13 | 1 | 1 | Iterate on game design
13 | 1 | 1.75 | Issues with Git
13 | 2 | 2 | Research US23
14 | 1 | 1 | Iterate on game design
15 | 1.25 | 1.25 | Team Meeting
15 | 1.25 | 1.25 | Presentations
15 | 8 | 7 | US23
15 | 5 | 1 | Defect: Darth Vadering
14 | 0 | 0 | Week of Thanksgiving, didn't do anything
16 | 2.25 | 2.25 | Presentations
16 | 2 | 2 | Presentation practice
16 | 1 | 0.5 | Evaluations
16 | 1 | 1 | Last minute demo preperations and recording