## Instructions
Your Name: | Alex
Instructions
Enter your name above.
At the end of each week:
Under "Accomplished this week"
Make sure planned tasks from last week copied correctly with estimated times
Fill in the actual amount of time spent on each task and indicate whether it is done.
Add any other tasks you worked on this week
Teams seem to relate better to times in hours down to the 1/4 hour, but feel free to use minutes if that has more meaning to you.
Under "Planned for next week"
Enter unfinished tasks from this week that you will continue next week
Enter other planned tasks for next week
Estimate the time you will spend on each task. Estimate your time in minutes or hours down to the 1/4 hour.
Tasks and estimates will copy to next week's accomplished section
Under "Issues"
Enter any unexpected problems you encountered
Enter any issues that require discussion with your team

## Example
First Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Y | 0.5 |  | Attended expectations talk
Y | 1 |  | Prepared for first meeting with sponsor
Y | 1.75 |  | Met with sponsor
Y | 5.25 |  | Researched webservices
Y | 2 |  | Team meeting to assign initial roles and responsibilities
| 10.5 | 0 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Regular team meeting
|  | 2 | Meeting with project sponsor
|  | 1 | Write draft synopsis with Kate
|  | 4 | Look for webservices tutorials and work through them
|  | 2.5 | Work with Adam to make list of requirements questions
|  | 11.5 | TOTAL TIME
Issues
Hard disk on my computer died, had to restore from backup
Team is having trouble finding time to meet together
May need help coding error-handling subsystem

## 1-Wk1
First Term - Week 1
Accomplished this week
Done? | ACT |  | Task
Yes | 0.5 |  | Attended first class
Yes | 0.5 |  | Discussed expectations of team and team introductions
Yes | 1 |  | Went over the project at a high level
Yes | 1 |  | Met with the project sponsor
| 1 |  | Worked on synopsis
| 0.5 |  | Send meeting minutes and create next week's agenda
| 4.5 |  | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Submit a photo and resume
|  | 0.25 | Submit the project synopsis to Dr Ludi
|  | 1 | Introduction and familiarization with Asana
|  | 1 | Plan the roadmap
|  | 1 | Meet with the sponsor
|  | 1.5 | Discuss requirements and feedback from sponsor meeting
|  | 0.25 | Plan next agenda
|  | 0.5 | Submit meeting minutes
|  | 5.75 | TOTAL TIME
Issues

## 1-Wk2
First Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
YES | 0.25 | 0.25 | Submit a photo and resume
No | 0 | 0.25 | Submit the project synopsis to Dr Ludi
yes | 1.25 | 1 | Introduction and familiarization with Asana
Yes | 1.25 | 1 | Plan the roadmap
Yes | 0.75 | 1 | Meet with the sponsor
Yes | 1.25 | 1.5 | Discuss requirements and feedback from sponsor meeting
No | 0 | 0.25 | Plan next agenda
Yes | 0.25 | 0.5 | Submit meeting minutes
| 5 | 5.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.25 | Submit the project synopsis to Dr Ludi
|  | 0.5 | Think of product system requirements questions for Paul
|  | 1 | Review the documents sent from Paul for current biz practices
|  | 2 | Continue conceptualizing requirements and the app. Domain
|  | 1 | Meet with sponsor
|  | 1 | Discuss feedback and recap sponsor meeting
|  | 0.25 | Plan next agenda
|  | 0.25 | Submit meeting minutes
|  | 6.25 | TOTAL TIME
Issues

## 1-Wk3
First Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.25 | 0.25 | Submit the project synopsis to Dr Ludi
Yes | 0.5 | 0.5 | Think of product system requirements questions for Paul
Yes | 1.25 | 1 | Review the documents sent from Paul for current biz practices
Yes | 2 | 2 | Continue conceptualizing requirements and the app. Domain
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Discuss feedback and recap sponsor meeting
No | 0 | 0.25 | Plan next agenda
Yes | 0.25 | 0.25 | Submit meeting minutes
| 6.25 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Think of technology decisions and begin exploring Mongoose and NodeJS
|  | 1.25 | Review the attendance card sent from Paul
|  | 0.75 | Add risk planning and identify risks in Asana
|  | 1.25 | Continue refining product backlog
|  | 1 | Meet with sponsor
|  | 1 | Recap sponsor meeting
|  | 6.25 | TOTAL TIME
Issues
Nick is taking over as scribe and doing the meeting minutes
Still haven't been able to create agenda, we need to do this as team

## 1-Wk4
First Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.75 | 1 | Think of technology decisions and begin exploring Mongoose and NodeJS
Yes | 0.75 | 1.25 | Review the attendance card sent from Paul
Yes | 1 | 0.75 | Add risk planning and identify risks in Asana
Yes | 1.25 | 1.25 | Continue refining product backlog
Yes | 1 | 1 | Meet with sponsor
Yes | 1 | 1 | Recap sponsor meeting
| 5.75 | 6.25 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Create and upload website
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 0.5 | Think about the design strategies for required devices
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 13.5 | TOTAL TIME
Issues

## 1-Wk5
First Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
No | 0 | 8 | Create and upload website
No | 0 | 2 | Create low fidelity prototypes and flowcharts
Yes | 0.5 | 0.5 | Think about the design strategies for required devices
No | 0 | 1 | Continue product backlog and requirement development
No | 0 | 1 | Meet with the sponsor
No | 0 | 1 | Recap sponsor meeting
| 0.5 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Create and upload website
|  | 2 | Create low fidelity prototypes and flowcharts
|  | 1 | Continue product backlog and requirement development
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 1 | Research useful metrics and decide on some
|  | 1 | Discussion of the architecture
|  | 15 | TOTAL TIME
Issues
Was unable to get to the website this week, need to do next week
Did not meet with team and sponsor due to 4th of July

## 1-Wk6
First Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 7 | 8 | Create and upload website
Yes | 2 | 2 | Create low fidelity prototypes and flowcharts
Yes | 1.5 | 1 | Continue product backlog and requirement development
Yes | 1 | 1 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.75 | 1 | Research useful metrics and decide on some
Yes | 0.5 | 1 | Discussion of the architecture
Yes | 1 |  | Further talk about the requirements of workshops and classes
| 14.75 | 15 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Think about the pros and cons for different check-in methods
|  | 1 | Research PhoneGap and the feasability of using Phonegap
|  | 2 | Update the wireframes according to sponsor feedback
|  | 1 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 0.25 | Update the website
|  | 5.75 | TOTAL TIME
Issues

## 1-Wk7
First Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Think about the pros and cons for different check-in methods
Yes | 0.75 | 1 | Research PhoneGap and the feasability of using Phonegap
Yes | 2 | 2 | Update the wireframes according to sponsor feedback
No | 0 | 1 | Meet with the sponsor
No | 0 | 1 | Recap sponsor meeting
Yes | 0.25 | 0.25 | Update the website
| 3.5 | 5.75 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Update the attendance wireframe
|  | 1 | Do initial assessment of ramaining user stores
|  | 0.5 | Collect and highlight what has been done to this point
|  | 0.5 | Update check-in wireframe
|  | 0.75 | Meet with the sponsor
|  | 1 | Recap sponsor meeting
|  | 0.5 | Begin coding
|  | 0.25 | Update website
|  | 5 | TOTAL TIME
Issues
I was out of town for the Thursday meeting with the sponsor

## 1-Wk8
First Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Update the attendance wireframe
No | 0 | 1 | Do initial assessment of ramaining user stores
Yes | 0.5 | 0.5 | Collect and highlight what has been done to this point
Yes | 1 | 0.5 | Update check-in wireframe
Yes | 0.75 | 0.75 | Meet with the sponsor
Yes | 1 | 1 | Recap sponsor meeting
Yes | 0.75 | 0.5 | Begin coding
No | 0 | 0.25 | Update website
| 4.5 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Do object modeling diagrams and associations
|  | 1 | Prioritize the product backlog
|  | 1 | Continue coding
|  | 0.45 | Meet with the sponsor
|  | 0.5 | Recap sponsor meeting
|  | 0.25 | Update website
|  | 5.2 | TOTAL TIME
Issues
I didn't update the website this week, will need to update next week

## 1-Wk9
First Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.75 | 2 | Do object modeling diagrams and associations
Yes | 0.5 | 1 | Prioritize the product backlog
Yes | 1.5 | 1 | Continue coding
Yes | 0.45 | 0.45 | Meet with the sponsor
Yes | 0.5 | 0.5 | Recap sponsor meeting
No | 0 | 0.25 | Update website
| 4.7 | 5.2 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2.5 | Begin preparing for the presentation and do the powerpoint
|  | 0.5 | Update the website
|  | 0.5 | Do a dry run of the presentation with the sponsor
|  | 0.5 | Do the presentation
|  | 1 | Code the project
|  | 5 | TOTAL TIME
Issues
I again did not have time to update the website

## 1-Wk10
First Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 2.5 | Begin preparing for the presentation and do the powerpoint
Yes | 0.75 | 0.5 | Update the website
Yes | 0.5 | 0.5 | Do a dry run of the presentation with the sponsor
Yes | 0.5 | 0.5 | Do the presentation
Yes | 1 | 1 | Code the project
| 4.75 | 5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on and complete the CRUD user stories
|  | 3 | TOTAL TIME
Issues

## 1-Finals
First Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
No | 0 | 3 | Work on and complete the CRUD user stories
| 0 | 3 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Work on and complete the CRUD user stories
|  | 1.15 | Sponsor meeting
|  | 4.15 | TOTAL TIME
Issues
Didn't end up doing any project work

## 2-Wk1
Second Term - Week 1
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 3 | Work on and complete the CRUD user stories
Yes | 1 | 1.15 | Research ways for Paul to pull the code from dev/production
Yes | 2 |  | Created a proof of concept for creating/reading existing students from API
Yes | 2.15 | 1.15 | Meeting with sponsor and post meeting follow up
| 7.15 | 5.3 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Work on some of the user stories assigned
|  | 1 | Create the mock ui ratio for the tablet screen demonstration
|  | 1.25 | Team meeting on Monday
|  | 1.25 | Sponsor meeting on Thursday
|  | 5.5 | TOTAL TIME
Issues

## 2-Wk2
Second Term - Week 2
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.45 | 2 | Work on some of the user stories assigned
Yes | 1.5 | 1 | Create the mock ui ratio for the tablet screen demonstration
Yes | 1.25 | 1.25 | Team meeting on Monday
Yes | 1.45 | 1.25 | Sponsor meeting on Thursday
Yes | 2.75 | 2 | Client side development for creating a student (UI elements)
Yes | 2 | 2.5 | Start the implementation for the wizard pattern for client side
Yes | 4 | 3 | Add logic to client to add new student in server and add more entries for application
| 14.4 | 13 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.25 | Monday team meeting
|  | 2 | Client development for e-contact step of reg. form
|  | 3 | Add validation checks for the create student reg. form
|  | 3 | Add form signature steps (research feasability of actual signature canvas)
|  | 1.25 | Meeting with sponsor and post meeting follow-up
|  | 10.5 | TOTAL TIME
Issues
Met on Labor day over google hangouts

## 2-Wk3
Second Term - Week 3
Accomplished this week
Done? | ACT | EST | Task
yes | 1.25 | 1.25 | Monday team meeting
Yes | 1.75 | 2 | Client development for e-contact step of reg. form
Yes | 2 | 3 | Add validation checks for the create student reg. form
Yes | 2 | 3 | Add form signature steps (research feasability of actual signature canvas)
Yes | 2 | 1.25 | Meeting with sponsor and post meeting follow-up
| 9 | 10.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 3 | Re-factor the controller for the create student wizard
|  | 3 | Develop list view for students admin page
|  | 2 | Monday team meeting
|  | 2 | Thursday sponsor meeting and post meeting follow up
|  | 10 | TOTAL TIME
Issues

## 2-Wk4
Second Term - Week 4
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 3 | Re-factor the controller for the create student wizard
Yes | 2.5 | 3 | Develop list view for students admin page
Yes | 1.25 | 2 | Monday team meeting
Yes | 1.25 | 2 | Thursday sponsor meeting and post meeting follow up
| 8 | 10 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Monday team meeting
|  | 2 | Thursday sponsor meeting and follow up
|  | 2.5 | Integrate emergency contact into wizard to add e-contact data on server side
|  | 2 | Refactor student wizard
|  | 2 | Add individual student view and fix list view for all students
|  | 3 | Complete signature pad
|  | 13.5 | TOTAL TIME
Issues
was unable to work on project as much as anticipated (Friday-Sunday)

## 2-Wk5
Second Term - Week 5
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 2 | Monday team meeting
Yes | 2 | 2 | Thursday sponsor meeting and follow up
Yes | 3 | 2.5 | Integrate emergency contact into wizard to add e-contact data on server side
Yes | 1 | 2 | Refactor student wizard
Yes | 1 | 2 | Add individual student view and fix list view for all students
Yes | 4 | 3 | Complete signature pad
Yes | 3 | 4 | Add remove functionality and fix phone number formating on register form
| 17 | 17.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Monday team meeting
|  | 2 | Bug fixes for regsitering student to complete the user story for this sprint
|  | 2 | Thursday sponsor meeting
|  | 8 | Begin working on check into a class
|  | 3 | Begin working on listing attendance records
|  | 17 | TOTAL TIME
Issues

## 2-Wk6
Second Term - Week 6
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.25 | 2 | Monday team meeting
Yes | 4.5 | 2 | Bug fixes for regsitering student to complete the user story for this sprint
Yes | 2 | 2 | Thursday sponsor meeting
No | 0 | 8 | Begin working on check into a class
No | 0 | 3 | Begin working on listing attendance records
Yes | 4 | 3 | Added multiple email address support for registering students
| 11.75 | 20 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Begin working on check into a class
|  | 3 | Begin working on listing attendance records
|  | 1.5 | Monday team meeting
|  | 2 | Thursday sponsor meeting
|  | 14.5 | TOTAL TIME
Issues
Didn't get to the attendance/checkin user story for the week

## 2-Wk7
Second Term - Week 7
Accomplished this week
Done? | ACT | EST | Task
Yes | 3 | 8 | Begin working on check into a class
Yes | 0 | 3 | Begin working on listing attendance records
Yes | 1.5 | 1.5 | Monday team meeting
Yes | 2 | 2 | Thursday sponsor meeting
Yes | 2 | 3 | Student registration bug fixes
| 8.5 | 17.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Continue development on checking into a class
|  | 3 | Begin working on listing attendance records
|  | 1.5 | Monday team meeting
|  | 2 | Thursday sponsor meeting
|  | 14.5 | TOTAL TIME
Issues
Partially completed checking into a class
Did not start attendance records listing yet

## 2-Wk8
Second Term - Week 8
Accomplished this week
Done? | ACT | EST | Task
Yes | 5 | 8 | Continue development on checking into a class
Yes | 1.5 | 3 | Begin working on listing attendance records
Yes | 1.5 | 1.5 | Monday team meeting
Yes | 2 | 2 | Thursday sponsor meeting
| 10 | 14.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 10 | Continue development on checkin
|  | 1.5 | Monday team meeting
|  | 2 | Thursday sponsor meeting
|  | 13.5 | TOTAL TIME
Issues
Unable to work on attendance records in admin page due to time constraints

## 2-Wk9
Second Term - Week 9
Accomplished this week
Done? | ACT | EST | Task
Yes | 11 | 10 | Continue development on checkin
Yes | 2 | 1.5 | Monday team meeting
Yes | 2.5 | 2 | Thursday sponsor meeting
| 15.5 | 13.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 4 | Refactor the checkin module
|  | 5 | Add ability to checkin to workshop
|  | 1.5 | Monday team meeting
|  | 2 | Thursday sponsor meeting
|  | 12.5 | TOTAL TIME
Issues

## 2-Wk10
Second Term - Week 10
Accomplished this week
Done? | ACT | EST | Task
Yes | 7.5 | 4 | Refactor the checkin module
Yes | 3 | 5 | Add ability to checkin to workshop
Yes | 1.75 | 1.5 | Monday team meeting
Yes | 2 | 2 | Thursday sponsor meeting
| 14.25 | 12.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Fix ng-grid bug
|  | 1.5 | Monday team meeting
|  | 3 | Add ability to register student on check in page
|  | 3 | Work on poster deliverable
|  | 2 | Thursday sponsor meeting
|  | 2 | Do user interface testing for tablet
|  | 12.5 | TOTAL TIME
Issues

## 2-Wk11
Second Term - Week 11
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 1 | Fix ng-grid bug
Yes | 1.5 | 1.5 | Monday team meeting
Yes | 2 | 3 | Add ability to register student on check in page
Yes | 1 | 3 | Work on poster deliverable
Yes | 2 | 2 | Thursday sponsor meeting
Yes | 2 | 3 | Do user interface testing for tablet
Yes | 3 | 1 | Work on time effort tracking and website maintenance
Yes | 2.75 | 2 | Added support for one way communication
| 14.75 | 16.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1.5 | Monday meeting
|  | 1 | Website maintenance and effort tracking
|  | 1 | Poster deliverable
|  | 2 | Thursday meeting
|  | 4 | Client UI support fixes
|  | 9.5 | TOTAL TIME
Issues
Only fixed the ng-grid bug on the students list

## 2-Wk12
Second Term - Week 12
Accomplished this week
Done? | ACT | EST | Task
Yes | 2 | 1.5 | Monday meeting
Yes | 1 | 1 | Website maintenance and effort tracking
No |  | 1 | Poster deliverable
Yes | 1.5 | 2 | Thursday meeting
No |  | 4 | Client UI support fixes
| 4.5 | 9.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 8 | Client UI Support fixes
|  | 1.5 | Monday meeting
|  | 2 | Thursday meeting
|  | 11.5 | TOTAL TIME
Issues

## 2-Wk13
Second Term - Week 13
Accomplished this week
Done? | ACT | EST | Task
Yes | 8 | 8 | iPad checkin bug fix (debugging and actual fix)
Yes | 1.75 | 1.5 | Monday meeting
Yes | 2 | 2 | Thursday meeting
Yes | 0.5 | 1 | Powerpoint work
Yes | 2.75 | 3 | Preview image for student registration
| 15 | 15.5 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 2 | Monday (Thursday meeting)
|  | 3 | Continue debugging
|  | 1 | Presentation powerpoint work
|  | 6 | TOTAL TIME
Issues

## 2-Wk14
Second Term - Week 14
Accomplished this week
Done? | ACT | EST | Task
Yes | 1.5 | 2 | Monday (Thursday meeting)
Yes | 3 | 3 | Continue debugging
Yes | 1 | 1 | Presentation powerpoint work
| 5.5 | 6 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 1 | Presentation preperation
|  | 1 | Presentation
|  | 2 | TOTAL TIME
Issues

## 2-Wk15
Second Term - Week 15
Accomplished this week
Done? | ACT | EST | Task
Yes | 1 | 1 | Presentation preperation
Yes | 2 | 1 | Presentation
Yes | 1.5 | 2 | Implement student notes on each students page
| 4.5 | 4 | TOTAL TIME
Planned for next week
|  | EST | Task
|  | 0.5 | Meet with coach
|  | 4 | Technical report work
|  | 1 | Website work
|  | 5.5 | TOTAL TIME
Issues

## 2-Finals
Second Term - Finals Week
Accomplished this week
Done? | ACT | EST | Task
Yes | 0.5 | 0.5 | Meet with coach
Yes | 2.5 | 4 | Technical report work
Yes | 0.5 | 1 | Website work
| 3.5 | 5.5 | TOTAL TIME
Issues

## AllData
t1-1a | t1-2e | t1-2a | t1-3e | t1-3a | t1-4e | t1-4a | t1-5e | t1-5a | t1-6e | t1-6a | t1-7e | t1-7a | t1-8e | t1-8a | t1-9e | t1-9a | t1-10e | t1-10a | wt1-fe | t1-fa
4.5 | 5.75 | 5 | 6.25 | 6.25 | 6.25 | 5.75 | 13.5 | 0.5 | 15 | 14.75 | 5.75 | 3.5 | 5 | 4.5 | 5.2 | 4.7 | 5 | 4.75 | 3 | 0
t2-1e | t2-1a | t2-2e | t2-2a | t2-3e | t2-3a | t2-4e | t2-4a | t2-5e | t2-5a | t2-6e | t2-6a | t2-7e | t2-7a | t2-8e | t2-8a | t2-9e | t2-9a | t2-10e | t2-10a | t2-11e | t2-11a | t2-12e | t2-12a | t2-13e | t2-13a | t2-14e | t2-14a | t2-15e | t2-15a | t2-fe | t2-fa
5.3 | 7.15 | 13 | 14.4 | 10.5 | 9 | 10 | 8 | 17.5 | 17 | 20 | 11.75 | 17.5 | 8.5 | 14.5 | 10 | 13.5 | 15.5 | 12.5 | 14.25 | 16.5 | 14.75 | 9.5 | 4.5 | 15.5 | 15 | 6 | 5.5 | 4 | 4.5 | 5.5 | 3.5